## Genral
Request For Information Log form DP03-East Project | Request For Information - RFI DP03-East | [14 empty] | ALL | 189
[16 empty] | Response | 160
[16 empty] | Open | 26
Inovo TO HILL | [6 empty] | Hill to ECG (DAR) |  |  |  | ECG (DAR) to hill |  | hill TO Inovo
Mail No | RFI No | Rev. | Mail No | Subject | Date |  | Mail No | Date |  | Action By | Mail No | Date | Mail No | Date
CCCEGY-RFI-000001 | P1000-K03199-INNRED-HL-RFI-000001-00 | 0 | INN-RED-RFI-000001 | RFI-000001-00-Request for general clarifications on IFC design package (04-06-2026) for townhouses, villas, and retail buildings | 2026-06-17 | General | HillInt-RFI-000471 | 2026-06-17 | 5 | Dar | Darr-RTRFI-000002 | 2026-06-22 | HillInt-RTRFI-000580 | 2026-06-22 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000002-00 | 0 | INN-RED-RFI-000002 | P1000-K03199-INNRED-HL-RFI-ST-000001-00 - Clarification on Waterproofing for PC Footings & SOG | 2026-06-23 | Structure | HillInt-RFI-000505 | 2026-06-23 | 6 | Dar | Darr-RTRFI-000007 | 2026-06-29 | HillInt-RTRFI-000642 | 2026-06-29 | 0 | Response | يعدل إلى رقم 2
| P1000-K03199-INNRED-HL-RFI-ST-000002-01 | 0 | INN-RED-RFI-000018 | P1000-K03199-INNRED-HL-RFI-ST-000002-01 - Clarification on Waterproofing for PC Footings & SOG | 2026-07-14 | Structure | HillInt-RFI-000728 | 2026-07-14 | 15 | Dar | Darr-RTRFI-000063 | 2026-07-29 | HillInt-RTRFI-000891 | 2026-07-29 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000003-00 | 0 | INN-RED-RFI-000003 | P1000-K03199-INNRED-HL-RFI-000003-00-Clarification Required Regarding Foundation Level Reference | 2026-06-29 | General | HillInt-RFI-000540 | 2026-06-28 | 18 | Dar | Darr-RTRFI-000031 | 2026-07-16 | HillInt-RTRFI-000818 | 2026-07-16 | 0 | Response | reminder : HillInt-GNC-001613
| P1000-K03199-INNRED-HL-RFI-GE-000004-00 | 0 | INN-RED-RFI-000005 | P1000-K03199-INNRED-HL-RFI-GE-000004-00-Discrepancy in Locations and Mirroring of Some Townhouses Between Structural and Architectural IFC Packages. | 2026-07-01 | General | HillInt-RFI-000607 | 2026-07-01 | 7 | Dar | Darr-RTRFI-000010 | 2026-07-08 | HillInt-RTRFI-000727 | 2026-07-08 | 0 | Response | reminder : HillInt-GNC-001614
| P1000-K03199-INNRED-HL-RFI-GE-000005-00 | 0 | INN-RED-RFI-000006 | P1000-K03199-INNRED-HL-RFI-GE-000005-00-Confirm the levels indicated on the villa blocks | 2026-07-05 | General | HillInt-RFI-000644 | 2026-07-06 | 10 | Dar | Darr-RTRFI-000030 | 2026-07-16 | HillInt-RTRFI-000810 | 2026-07-16 | 0 | Response | reminder : HillInt-GNC-001735
| P1000-K03199-INNRED-HL-RFI-ST-000006-00 | 0 | INN-RED-RFI-000007 | P1000-K03199-INNRED-HL-RFI-ST-000006-00-Clarification of Foundation Type: Fence FO and. Retaining Wall | 2026-07-06 | Structure | HillInt-RFI-000645 | 2026-07-06 | 3 | Dar | Darr-RTRFI-000015 | 2026-07-09 | HillInt-RTRFI-000745 | 2026-07-09 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000007-00 | 0 | INN-RED-RFI-000008 | P1000-K03199-INNRED-HL-RFI-GE-000007-00-Discrepancies in the Architectural IFC Master Plan Layout of Townhouse Units | 2026-07-06 | General | HillInt-RFI-000646 | 2026-07-06 | 13 | Dar | Darr-RTRFI-000032 | 2026-07-19 | HillInt-RTRFI-000823 | 2026-07-19 | 0 | Response | reminder : HillInt-GNC-001736
| P1000-K03199-INNRED-HL-RFI-GE-000008-00 | 0 | INN-RED-RFI-000009 | P1000-K03199-INNRED-HL-RFI-GE-000008-00-Townhouses Mirrored units | 2026-07-06 | General | HillInt-RFI-000647 | 2026-07-06 | 22 | Dar | Darr-RTRFI-000054 | 2026-07-28 | HillInt-RTRFI-000881 | 2026-07-28 | 0 | Response | reminder : HillInt-GNC-001737
| P1000-K03199-INNRED-HL-RFI-GE-000009-00 | 0 | INN-RED-RFI-000010 | P1000-K03199-INNRED-HL-RFI-GE-000009-00-Clarification of Foundation Overlaps and Clashes with Excavation Boundaries and Fence Foundations Between Adjacent Townhouses | 2026-07-06 | General | HillInt-RFI-000648 | 2026-07-06 | 35 | Dar | Darr-RTRFI-000083 | 2026-08-10 | HillInt-RTRFI-000972 | 2026-08-10 | 0 | Response | reminder : HillInt-GNC-001738 ( stil open )
| P1000-K03199-INNRED-HL-RFI-ST-000010-00 | 0 | INN-RED-RFI-000011 | P1000-K03199-INNRED-HL-RFI-ST-000010-00-Check Design for Villa 3 Bedrooms | 2026-07-06 | Structure | HillInt-RFI-000656 | 2026-07-06 | 9 | Dar | Darr-RTRFI-000022 | 2026-07-15 | HillInt-RTRFI-000799 | 2026-07-15 | 0 | Response | reminder : HillInt-GNC-001739
| P1000-K03199-INNRED-HL-RFI-GE-000011-00 | 0 | INN-RED-RFI-000012 | P1000-K03199-INNRED-HL-RFI-GE-000011-00-Request for Builder’s Work Drawings (Interface Coordination) | 2026-07-08 | General | HillInt-RFI-000676 | 2026-07-08 | 4 | Dar | Darr-RTRFI-000019 | 2026-07-12 | HillInt-RTRFI-000765 | 2026-07-12 | 0 | Response | there are no comments on the PDFHillInt-GNC-001712
| P1000-K03199-INNRED-HL-RFI-GE-000011-01 | 1 | INN-RED-RFI-000022 | P1000-K03199-INNRED-HL-RFI-GE-000011-01-Request for Builder’s Work Drawings (Interface Coordination) | 2026-07-21 | General | HillInt-RFI-000774 | 2026-07-21 | 7 | Dar | Darr-RTRFI-000059 | 2026-07-28 | HillInt-RTRFI-000885 | 2026-07-28 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000012-00 | 0 | INN-RED-RFI-000013 | P1000-K03199-INNRED-HL-RFI-GE-000012-00-Proposed Stockpile Locations | 2026-07-09 | General | HillInt-RFI-000686 | 2026-07-09 | -46212 | Dar |  |  | HillInt-RTRFI-000860 | 2026-07-27 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000013-00 | 0 | INN-RED-RFI-000014 | P1000-K03199-INNRED-HL-RFI-GE-000013-00-Discrepancy in Foundation Level for Townhouses in the received IFC packages | 2026-07-09 | General | HillInt-RFI-000687 | 2026-07-09 | 6 | Dar | Darr-RTRFI-000028 | 2026-07-15 | HillInt-RTRFI-000804 | 2026-07-15 | 0 | Response | re send to dar Darr-RTRFI-000024 pdf
| P1000-K03199-INNRED-HL-RFI-GE-000013-01 | 1 | INN-RED-RFI-000021 | P1000-K03199-INNRED-HL-RFI-GE-000013-01-Discrepancy in Foundation Level for Townhouses in the received IFC packages | 2026-07-19 | General | HillInt-RFI-000745 | 2026-07-19 | 3 | Dar | Darr-RTRFI-000037 | 2026-07-22 | HillInt-RTRFI-000841 | 2026-07-22 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000014-00 | 0 | INN-RED-RFI-000015 | P1000-K03199-INNRED-HL-RFI-GE-000014-00-Discrepancies and Missing Data in Latest Master Plan (Received 06/07/2026) | 2026-07-11 | General | HillInt-RFI-000704 | 2026-07-11 | 17 | Dar | Darr-RTRFI-000043 | 2026-07-28 | HillInt-RTRFI-000873 | 2026-07-28 | 0 | Response | reminder : HillInt-GNC-002012
| P1000-K03199-INNRED-HL-RFI-GE-000015-00 | 0 | INN-RED-RFI-000016 | P1000-K03199-INNRED-HL-RFI-GE-000015-00-Confirmation of Ground Beam System Upgrade to Rigid Ground Beams (80cm depth) | 2026-07-11 | General | HillInt-RFI-000705 | 2026-07-11 | 4 | Dar | Darr-RTRFI-000023 | 2026-07-15 | HillInt-RTRFI-000798 | 2026-07-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000016-00 | 0 | INN-RED-RFI-000017 | P1000-K03199-INNRED-HL-RFI-GE-000016-00-Confirmation of Replacement: Sand/Aggregate (1:1) instead of Sand-only | 2026-07-11 | General | HillInt-RFI-000706 | 2026-07-11 | 11 | Dar | Darr-RTRFI-000041 | 2026-07-22 | HillInt-RTRFI-000847 | 2026-07-22 | 0 | Response | خطأ في الردHillInt-GNC-002042
| P1000-K03199-INNRED-HL-RFI-GE-000017-00 | 0 | INN-RED-RFI-000020 | P1000-K03199-INNRED-HL-RFI-GE-000017-00-Villa Excavation & Replacement Scope | 2026-07-18 | General | HillInt-RFI-000744 | 2026-07-19 | 3 | Dar | Darr-RTRFI-000038 | 2026-07-22 | HillInt-RTRFI-000842 | 2026-07-22 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000018-00 | 0 | INN-RED-RFI-000023 | P1000-K03199-INNRED-HL-RFI-GE-000018-00- Discrepancies in Master Plan Legend and Unit Types / Levels | 2026-07-21 | General | HillInt-RFI-000777 | 2026-07-21 | 7 | Dar | Darr-RTRFI-000056 | 2026-07-28 | HillInt-RTRFI-000883 | 2026-07-28 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000019-00 | 0 | INN-RED-RFI-000024 | P1000-K03199-INNRED-HL-RFI-ST-000019-00-Polyethylene Sheet under PC | 2026-07-28 | Structure | HillInt-RFI-000799 | 2026-07-28 | 1 | Dar | Darr-RTRFI-000068 | 2026-07-29 | HillInt-RTRFI-000893 | 2026-07-29 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000020-00 | 0 | INN-RED-RFI-000025 | P1000-K03199-INNRED-HL-RFI-GE-000020-00-Technical & Architectural Concern: Zero-Step Level Between Internal FFL and External Landscape | 2026-07-29 | General | HillInt-RFI-000802 | 2026-07-29 | 8 | Dar | Darr-RTRFI-000079 | 2026-08-06 | HillInt-RTRFI-000953 | 2026-08-06 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000021-00 | 0 | INN-RED-RFI-000026 | P1000-K03199-INNRED-HL-RFI-GE-000021-00-Clarification Required About Excavation and Foundation Levels for Townhouse No WE-95 | 2026-07-29 | General | HillInt-RFI-000813 | 2026-07-29 | 1 | Dar | Darr-RTRFI-000073 | 2026-07-30 | HillInt-RTRFI-000911 | 2026-08-03 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000022-00 | 0 | INN-RED-RFI-000027 | P1000-K03199-INNRED-HL-RFI-AR-000022-00-Discrepancy in Masonry Wall Types and Thicknesses between Contract Priced BOQ , unpriced BOQ and IFC Drawings | 2026-08-01 | Arch | HillInt-RFI-000817 | 2026-08-02 | 2 | Dar | Darr-RTRFI-000075 | 2026-08-04 | HillInt-RTRFI-000930 | 2026-08-04 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000023-00 | 0 | INN-RED-RFI-000028 | P1000-K03199-INNRED-HL-RFI-AR-000023-00-Discrepancy between Drawings and Specifications regarding Masonry-to-Column Connection (Dovetail Anchors vs. Standard L-Angles) | 2026-08-01 | Arch | HillInt-RFI-000818 | 2026-08-02 | 2 | Dar | Darr-RTRFI-000077 | 2026-08-04 | HillInt-RTRFI-000933 | 2026-08-04 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000024-00 | 0 | INN-RED-RFI-000029 | P1000-K03199-INNRED-HL-RFI-AR-000024-00-Clarification on EIFS Details and Discrepancy with Architectural IFC Drawings | 2026-08-01 | Arch | HillInt-RFI-000819 | 2026-08-02 | 2 | Dar | Darr-RTRFI-000076 | 2026-08-04 | HillInt-RTRFI-000932 | 2026-08-04 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000025-00 | 0 | INN-RED-RFI-000031 | Re: P1000-K03199-INNRED-HL-RFI-GE-000025-00-Evaluation Report: Impact of Variable Foundation Depths for Villas and Townhouses | 2026-08-03 | General | HillInt-RFI-000828 | 2026-08-03 | 2 | Dar | Darr-RTRFI-000078 | 2026-08-05 | HillInt-RTRFI-000946 | 2026-08-05 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000025-01 | 1 | INN-RED-RFI-000037 | P1000-K03199-INNRED-HL-RFI-GE-000025-01-Evaluation Report: Impact of Variable Foundation Depths for Villas and Townhouses | 2026-08-08 | General | HillInt-RFI-000852 | 2026-08-09 | 25 | Dar | Darr-RTRFI-000178 | 2026-09-03 | HillInt-GNC-004529 | 2026-09-06 | 0 | Response | send by outlook
| P1000-K03199-INNRED-HL-RFI-AR-000026-00 | 0 | INN-RED-RFI-000032 | P1000-K03199-INNRED-HL-RFI-AR-000026-00-Discrepancy Between Architectural Drawings and BOQ Regarding Wall Types and Thicknesses for Four-Plex / Six-Plex And Villa Units | 2026-08-04 | Arch | HillInt-RFI-000832 | 2026-08-05 | 6 | Dar | Darr-RTRFI-000094 | 2026-08-11 | HillInt-RTRFI-000989 | 2026-08-11 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-EL-000027-00 | 0 | INN-RED-RFI-000033 | P1000-K03199-INNRED-HL-RFI-EL-000027-00-Confirmation of Motorized Curtain Type and Installation Location | 2026-08-06 | Elec | HillInt-RFI-000848 | 2026-08-06 | 4 | Dar | Darr-RTRFI-000089 | 2026-08-10 | HillInt-RTRFI-000982 | 2026-08-10 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000028-00 | 0 | INN-RED-RFI-000034 | P1000-K03199-INNRED-HL-RFI-GE-000028-00-Clarification required on the type and statical system of the external staircase. | 2026-08-06 | General | INN-RED-RFI-000034 | 2026-08-06 | 6 | Dar | Darr-RTRFI-000098 | 2026-08-12 | HillInt-RTRFI-000992 | 2026-08-12 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000029-00 | 0 | INN-RED-RFI-000035 | P1000-K03199-INNRED-HL-RFI-GE-000029-00-Clarification Regarding Ground Beams Below External Walls | 2026-08-06 | General | HillInt-RFI-000850 | 2026-08-06 | 6 | Dar | Darr-RTRFI-000099 | 2026-08-12 | HillInt-RTRFI-000993 | 2026-08-12 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000030-00 | 0 | INN-RED-RFI-000036 | P1000-K03199-INNRED-HL-RFI-GE-000030-00-Clarification Regarding the Extension of the Reinforced Concrete Staircase into the Adjacent Masonry Walls | 2026-08-06 | General | HillInt-RFI-000851 | 2026-08-06 | 5 | Dar | Darr-RTRFI-000092 | 2026-08-11 | HillInt-RTRFI-000988 | 2026-08-11 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000031-00 | 0 | INN-RED-RFI-000038 | P1000-K03199-INNRED-HL-RFI-GE-000031-00-4 Plex Flat Townhouse - Discrepancy in axes spacing. | 2026-08-08 | General | HillInt-RFI-000853 | 2026-08-09 | 3 | Dar | Darr-RTRFI-000097 | 2026-08-12 | HillInt-RTRFI-000994 | 2026-08-12 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000032-00 | 0 | INN-RED-RFI-000039 | P1000-K03199-INNRED-HL-RFI-AR-000032-00-Townhouses - 3 & 4-Bedroom type - Openings’ Naming Conflict. | 2026-08-08 | General | HillInt-RFI-000854 | 2026-08-09 | 3 | Dar | Darr-RTRFI-000096 | 2026-08-12 | HillInt-RTRFI-000995 | 2026-08-12 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000033-00 | 0 | INN-RED-RFI-000040 | P1000-K03199-INNRED-HL-RFI-ME-000033-00-Floor Drain in The Kitchen | 2026-08-09 | Mechanical | HillInt-RFI-000882 | 2026-08-09 | 1 | Dar | Darr-RTRFI-000087 | 2026-08-10 | HillInt-RTRFI-000980 | 2026-08-10 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000034-00 | 0 | INN-RED-RFI-000042 | P1000-K03199-INNRED-HL-RFI-ME-000034-00-Bedroom Toilet Soil Pipe Unvented | 2026-08-09 | Mechanical | HillInt-RFI-000883 | 2026-08-09 | 2 | Dar | Darr-RTRFI-000091 | 2026-08-11 | HillInt-RTRFI-000987 | 2026-08-11 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000035-00 | 0 | INN-RED-RFI-000043 | P1000-K03199-INNRED-HL-RFI-ME-000035-00-Water Supply Small Size | 2026-08-09 | Mechanical | HillInt-RFI-000884 | 2026-08-10 | 1 | Dar | Darr-RTRFI-000090 | 2026-08-11 | HillInt-RTRFI-000986 | 2026-08-11 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000035-01 | 1 | INN-RED-RFI-000112 | P1000-K03199-INNRED-HL-RFI-ME-000035-01-Water Supply Small Size | 2026-09-06 | Mechanical | HillInt-GNC-003225 | 2026-09-07 | 5 | ECG | SHKECGCR-RTRFI-000059 | 2026-09-12 | HillInt-RTRFI-001244 | 2026-03-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000036-00 | 0 | INN-RED-RFI-000044 | P1000-K03199-INNRED-HL-RFI-000036-00-Water Meter Box Layout | 2026-08-09 | Mechanical | HillInt-RFI-000885 | 2026-08-10 | 0 | Dar | Darr-RTRFI-000088 | 2026-08-10 | HillInt-RTRFI-000981 | 2026-08-10 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000037-00 | 0 | INN-RED-RFI-000045 | P1000-K03199-INNRED-HL-RFI-ST-000037-00-Ground beam supporting stair starter in 6 Plex Flat Townhouses | 2026-08-12 | Structural | HillInt-RFI-000887 | 2026-08-12 | 5 | Dar | Darr-RTRFI-000107 | 2026-08-17 | HillInt-RTRFI-001029 | 2026-08-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000038-00 | 0 | INN-RED-RFI-000046 | P1000-K03199-INNRED-HL-RFI-AR-000038-00-Townhouse - Discrepancy Between Facade Details and Architectural Plans - Recess Around Openings | 2026-08-12 | Architectural | HillInt-RFI-000888 | 2026-08-12 | 5 | Dar | Darr-RTRFI-000105 | 2026-08-17 | HillInt-RTRFI-001027 | 2026-08-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000039-00 | 0 | INN-RED-RFI-000047 | P1000-K03199-INNRED-HL-RFI-AR-000039-00-Town houses / Missing life safety plans | 2026-08-12 | Architectural | HillInt-RFI-000889 | 2026-08-12 | 5 | Dar | Darr-RTRFI-000102 | 2026-08-17 | HillInt-RTRFI-001024 | 2026-08-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000040-00 | 0 | INN-RED-RFI-000048 | P1000-K03199-INNRED-HL-RFI-ME-000040-00-Fire Blanket in Kitchen | 2026-08-12 | Mechanical | HillInt-RFI-000891 | 2026-08-12 | 1 | Dar | Darr-RTRFI-000100 | 2026-08-13 | HillInt-RTRFI-001008 | 2026-08-13 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000041-00 | 0 | INN-RED-RFI-000049 | P1000-K03199-INNRED-HL-RFI-GE-000041-00-Townhouses (6-Plex Flat)-Columns of type (C2) alignment with Arch Walls | 2026-08-12 | General | HillInt-RFI-000892 | 2026-08-12 | 5 | Dar | Darr-RTRFI-000104 | 2026-08-17 | HillInt-RTRFI-001025 | 2026-08-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000042-00 | 0 | INN-RED-RFI-000050 | P1000-K03199-INNRED-HL-RFI-AR-000042-00-Townhouse - Clarification on Door Schedule Dimensions and Window Fixation Tolerances | 2026-08-12 | Architectural | HillInt-RFI-000893 | 2026-08-12 | 5 | Dar | Darr-RTRFI-000108 | 2026-08-17 | HillInt-RTRFI-001034 | 2026-08-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000043-00 | 0 | INN-RED-RFI-000051 | P1000-K03199-INNRED-HL-RFI-AR-000043-00- Sub-Grade Masonry / Under SOG Blockwork Clarification | 2026-08-16 | Architectural | HillInt-RFI-000946 | 2026-08-16 | 8 | Dar | Darr-RTRFI-000122 | 2026-08-24 | HillInt-RTRFI-001088 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000044-00 | 0 | INN-RED-RFI-000052 | P1000-K03199-INNRED-HL-RFI-ST-000044-00-Ground Beam Depth Adjustment | 2026-08-17 | Structural | HillInt-RFI-000951 | 2026-08-17 | 7 | Dar | Darr-RTRFI-000123 | 2026-08-24 | HillInt-RTRFI-001089 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000045-00 | 0 | INN-RED-RFI-000053 | P1000-K03199-INNRED-HL-RFI-ST-000045-00-Discrepancy in Axes/Gridlines for 4-Bedroom Villas between Master Plan and Enabling Drawings | 2026-08-17 | Structural | HillInt-RFI-000953 | 2026-08-17 | 7 | Dar | Darr-RTRFI-000121 | 2026-08-24 | HillInt-RTRFI-001087 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000046-00 | 0 | INN-RED-RFI-000054 | P1000-K03199-INNRED-HL-RFI-GE-000046-00-Lack of Grade Beams under External Walls – Coordination Issue | 2026-08-17 | General | HillInt-RFI-000954 | 2026-08-17 | 7 | Dar | Darr-RTRFI-000124 | 2026-08-24 | HillInt-RTRFI-001090 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000047-00 | 0 | INN-RED-RFI-000055 | P1000-K03199-INNRED-HL-RFI-AR-000047-00-Tie Beam Alignment with External Blockwork and Under-SOG Blockwork Arrangement for Villas | 2026-08-18 | Architectural | HillInt-RFI-000971 | 2026-08-18 | 6 | Dar | Darr-RTRFI-000129 | 2026-08-24 | HillInt-RTRFI-001092 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000048-00 | 0 | INN-RED-RFI-000056 | P1000-K03199-INNRED-HL-RFI-ST-000048-00-Discrepancy in Footing F4 Dimensions between Foundation Layout and Schedule – DP03 Villas 3 Bedroom | 2026-08-18 | Structural | HillInt-RFI-000972 | 2026-08-18 | 5 | Dar | Darr-RTRFI-000125 | 2026-08-23 | HillInt-RTRFI-001091 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000049-00 | 0 | INN-RED-RFI-000057 | P1000-K03199-INNRED-HL-RFI-ME-000049-00 - Water Closet Type in Ground floor | 2026-08-17 | Mechanical | HillInt-RFI-000973 | 2026-08-18 | 1 | Dar | Darr-RTRFI-000116 | 2026-08-19 | HillInt-RTRFI-001055 | 2026-08-19 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000050-00 | 0 | INN-RED-RFI-000058 | P1000-K03199-INNRED-HL-RFI-ME-000050-00-Water Closets Missing Flush Tank and Flush Tank Tie-In | 2026-08-17 | Mechanical | HillInt-RFI-000974 | 2026-08-18 | 1 | Dar | Darr-RTRFI-000117 | 2026-08-19 | HillInt-RTRFI-001058 | 2026-08-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000051-00 | 0 | INN-RED-RFI-000059 | P1000-K03199-INNRED-HL-RFI-GE-000051-00-Townhouse - Discrepancy Regarding Stair Finish Build-Up and Fixation Method | 2026-08-17 | General | HillInt-RFI-000975 | 2026-08-18 | 1 | Dar | Darr-RTRFI-000110 | 2026-08-19 | HillInt-RTRFI-001059 | 2026-08-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000052-00 | 0 | INN-RED-RFI-000060 | P1000-K03199-INNRED-HL-RFI-GE-000052-00-Pedestal (PD1) Top level | 2026-08-17 | General | HillInt-RFI-000976 | 2026-08-18 | 6 | Dar | Darr-RTRFI-000130 | 2026-08-24 | HillInt-RTRFI-001093 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000053-00 | 0 | INN-RED-RFI-000061 | P1000-K03199-INNRED-HL-RFI-000053-00-Villas Fire Rating Requirements for Doors and Walls – BOQ, Specifications & Drawings Clarification | 2026-08-18 | Architectural | HillInt-RFI-000977 | 2026-08-18 | 6 | Dar | Darr-RTRFI-000120 | 2026-08-24 | HillInt-RTRFI-001086 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000054-00 | 0 | INN-RED-RFI-000062 | P1000-K03199-INNRED-HL-RFI-GE-000054-00-Revision of Concrete Slab Depression Boundaries to Suit Drainage Works | 2026-08-18 | General | HillInt-RFI-000978 | 2026-08-18 | 7 | Dar | Darr-RTRFI-000132 | 2026-08-25 | HillInt-RTRFI-001110 | 2026-08-25 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000055-00 | 0 | INN-RED-RFI-000063 | P1000-K03199-INNRED-HL-RFI-000055-00-Clarification Required – Intercom Outlet Location | 2026-08-18 | General | HillInt-RFI-000979 | 2026-08-18 | 2 | Dar | Darr-RTRFI-000111 | 2026-08-20 | HillInt-RTRFI-001060 | 2026-08-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000056-00 | 0 | INN-RED-RFI-000064 | P1000-K03199-INNRED-HL-RFI-GE-000056-00-Wi-Fi Access Point Location | 2026-08-18 | General | HillInt-RFI-000980 | 2026-08-18 | 2 | Dar | Darr-RTRFI-000113 | 2026-08-20 | HillInt-RTRFI-001061 | 2026-08-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000057-00 | 0 | INN-RED-RFI-000065 | P1000-K03199-INNRED-HL-RFI-GE-000057-00-Missing TV Data Outlet | 2026-08-18 | General | HillInt-RFI-000983 | 2026-08-18 | 2 | Dar | Darr-RTRFI-000114 | 2026-08-20 | HillInt-RTRFI-001062 | 2026-08-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000058-00 | 0 | INN-RED-RFI-000066 | P1000-K03199-INNRED-HL-RFI-AR-000058-00-Villas 4 Bedroom Mediterranean Stair Conflict | 2026-08-18 | General | HillInt-RFI-000984 | 2026-08-18 | 6 | Dar | Darr-RTRFI-000119 | 2026-08-24 | HillInt-RTRFI-001100 | 2026-08-24 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000058-01 | 1 | INN-RED-RFI-000169 | P1000-K03199-INNRED-HL-RFI-AR-000058-01-4 BDR Mediterranean Villas – stairs conflict between plans and section Re: P1000-K03199-INNRED-HL-RFI-AR-000058-00-Villas 4 Bedroom Mediterranean Stair Conflict | 2026-09-26 | Architectural | HillInt-GNC-004319 | 2026-09-28 | 9 | ECG | SHKECGCR-RTRFI-000188 | 2026-10-07 | HillInt-GNC-004943 | 2026-10-07 | 0 | Response | HillInt-GNC-004772 : reminder
| P1000-K03199-INNRED-HL-RFI-000059-00 | 0 | INN-RED-RFI-000067 | P1000-K03199-INNRED-HL-RFI-000059-00-Villa 4 Bedroom Mediterranean Wall Height Support | 2026-08-18 | Architectural | HillInt-RFI-000985 | 2026-08-18 | 1 | Dar | Darr-RTRFI-000112 | 2026-08-19 | HillInt-RTRFI-001063 | 2026-08-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000060-00 | 0 | INN-RED-RFI-000068 | P1000-K03199-INNRED-HL-RFI-AR-000060-00-5BR Villa - Stair Level, Riser Calculation and Numbering Clarification | 2026-08-21 | Architectural | HillInt-RFI-001046 | 2026-08-23 | 4 | Dar | Darr-RTRFI-000133 | 2026-08-27 | HillInt-RTRFI-001165 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000061-00 | 0 | INN-RED-RFI-000069 | P1000-K03199-INNRED-HL-RFI-AR-000061-00-Unidentified Element at Handrail – 3BR & 5BR Villas | 2026-08-21 | Architectural | HillInt-RFI-001047 | 2026-08-23 | 4 | Dar | Darr-RTRFI-000134 | 2026-08-27 | HillInt-RTRFI-001166 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ME-000062-00 | 0 | INN-RED-RFI-000070 | P1000-K03199-INNRED-HL-RFI-ME-000062-00-Clarification of House Connection Levels and External Infrastructure Connection | 2026-08-21 | Mechanical | HillInt-RFI-001048 | 2026-08-23 | 8 | Dar | Darr-RTRFI-000157 | 2026-08-31 | HillInt-RTRFI-001189 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000063-00 | 0 | INN-RED-RFI-000071 | P1000-K03199-INNRED-HL-RFI-AR-000063-00-Villas Stair Marble Bedding Material – BOQ and General Detail Conflict | 2026-08-21 | Architectural | HillInt-RFI-001049 | 2026-08-23 | 8 | Dar | Darr-RTRFI-000147 | 2026-08-31 | HillInt-RTRFI-001180 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000064-00 | 0 | INN-RED-RFI-000072 | P1000-K03199-INNRED-HL-RFI-AR-000064-00-Villas IFC Package – Landscape & Irrigation Files | 2026-08-21 | Architectural | HillInt-RFI-001050 | 2026-08-23 | 7 | Dar | Darr-RTRFI-000137 | 2026-08-30 | HillInt-RTRFI-001171 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000065-00 | 0 | INN-RED-RFI-000073 | P1000-K03199-INNRED-HL-RFI-000065-00- All Villas - Aluminum Glass Door Type and Dimension Discrepancies | 2026-08-21 | Architectural | HillInt-RFI-001051 | 2026-08-23 | 7 | Dar | Darr-RTRFI-000142 | 2026-08-30 | HillInt-RTRFI-001178 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000066-00 | 0 | INN-RED-RFI-000074 | P1000-K03199-INNRED-HL-RFI-AR-000066-00- 3 BR-MED Villas – Missing Aluminum Glass Doors Type (CW-05) | 2026-08-21 | Architectural | HillInt-RFI-001052 | 2026-08-23 | 8 | Dar | Darr-RTRFI-000146 | 2026-08-31 | HillInt-RTRFI-001179 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000067-00 | 0 | INN-RED-RFI-000075 | P1000-K03199-INNRED-HL-RFI-ST-000067-00-Discrepancy in Footing F3 Dimensions between Foundation Layout and Schedule – DP03 Villas 4 Bedroom-Spanish | 2026-08-21 | Architectural | HillInt-RFI-001053 | 2026-08-23 | 8 | Dar | Darr-RTRFI-000149 | 2026-08-31 | HillInt-RTRFI-001182 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000068-00 | 0 | INN-RED-RFI-000076 | P1000-K03199-INNRED-HL-RFI-AR-000068-00- Aluminum Glass Door Type and Dimension Discrepancies Villa 3 Bedroom Spanish | 2026-08-21 | Architectural | HillInt-RFI-001054 | 2026-08-23 | 7 | Dar | Darr-RTRFI-000138 | 2026-08-30 | HillInt-RTRFI-001174 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000069-00 | 0 | INN-RED-RFI-000077 | P1000-K03199-INNRED-HL-RFI-AR-000069-00-Aluminum Glass Door Size Discrepancies Villa 4Bedroom Mediterranean | 2026-08-21 | Architectural | HillInt-RFI-001055 | 2026-08-23 | 8 | Dar | Darr-RTRFI-000148 | 2026-08-31 | HillInt-RTRFI-001181 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000070-00 | 0 | INN-RED-RFI-000078 | P1000-K03199-INNRED-HL-RFI-AR-000070-00-Aluminum Glass Door Size Discrepancies Villa 4Bedroom Spanish | 2026-08-21 | Architectural | HillInt-RFI-001056 | 2026-08-23 | 10 | Dar | Darr-RTRFI-000172 | 2026-09-02 | HillInt-RTRFI-001232 | 2026-09-02 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000071-00 | 0 | INN-RED-RFI-000079 | P1000-K03199-INNRED-HL-RFI-AR-000071-00-Door & Window Frame-to-Wall Clearance – Villa Scope Clarification | 2026-08-21 | Architectural | HillInt-RFI-001057 | 2026-08-23 | 11 | Dar | Darr-RTRFI-000173 | 2026-09-03 | HillInt-GNC-004531 | 2026-09-06 | 0 | Response | send by outlook
| P1000-K03199-INNRED-HL-RFI-TE-000072-00 | 0 | INN-RED-RFI-000080 | P1000-K03199-INNRED-HL-RFI-TE-000072-00-Active or Passive Subwoofer | 2026-08-21 | Telecommunication | HillInt-RFI-001058 | 2026-08-23 | 7 | Dar | Darr-RTRFI-000139 | 2026-08-30 | HillInt-GNC-004532 | 2026-09-06 | 0 | Response | send by outlook
| P1000-K03199-INNRED-HL-RFI-AR-000073-00 | 0 | INN-RED-RFI-000081 | P1000-K03199-INNRED-HL-RFI-AR-000073-00-Clarification Required – External Timber Doors for Villas and Townhouses | 2026-08-25 | Architectural | HillInt-RTRFI-001110 | 2026-08-25 | 6 | Dar | Darr-RTRFI-000159 | 2026-08-31 | HillInt-RTRFI-001190 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000074-00 | 0 | INN-RED-RFI-000082 | P1000-K03199-INNRED-HL-RFI-ST-000074-00-Proposed Ground Beams under External Walls for Townhouses (4-Plex and 6-Plex) | 2026-08-25 | Structural | HillInt-RFI-001074 | 2026-08-25 | 0 | ECG | SHKECGCR-RFI-000057 | 2026-08-25 | HillInt-RTRFI-001163 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000075-00 | 0 | INN-RED-RFI-000083 | P1000-K03199-INNRED-HL-RFI-GE-000075-00-Insufficient Clearance for Ground Floor Drainage Pipes | 2026-08-25 | General | HillInt-RFI-001078 | 2026-08-26 | 5 | Dar | Darr-RTRFI-000155 | 2026-08-31 | HillInt-RTRFI-001183 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000076-00 | 0 | INN-RED-RFI-000084 | P1000-K03199-INNRED-HL-RFI-ST-000076-00-Ground Beam Proposal for External Walls – Villa Types | 2026-08-26 | General |  |  | 46261 | ECG | SHKECGCR-RTRFI-000014 | 2026-08-27 | HillInt-RTRFI-001162 | 2026-08-31 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000077-00 | 0 | INN-RED-RFI-000085 | P1000-K03199-INNRED-HL-RFI-AR-000077-00-External Skirting Requirement – Architectural Clarification | 2026-08-30 | Architectural | HillInt-RFI-001097 | 2026-08-31 | 3 | Dar | Darr-RTRFI-0001777 | 2026-09-03 | HillInt-RTRFI-001264 | 2026-09-16 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000078-00 | 0 | INN-RED-RFI-000086 | P1000-K03199-INNRED-HL-RFI-AR-000078-00-Garbage Room Gate Width Discrepancies and Missing Details | 2026-08-30 | Architectural | HillInt-RFI-001098 | 2026-08-31 | 36 | DAR | SHKECGCR-RTRFI-000145 | 2026-10-06 | HillInt-GNC-004848 | 2026-10-06 | 0 | Response | HillInt-GNC-003170 : send to darHillInt-GNC-004533 reminder
| P1000-K03199-INNRED-HL-RFI-ST-000079-00 | 0 | INN-RED-RFI-000087 | P1000-K03199-INNRED-HL-RFI-ST-000079-00-Feasibility and Connection Details for Staircase Wall Posts on SOG | 2026-08-30 | Structural | HillInt-RFI-001107 | 2026-08-31 | 2 | Dar | Darr-RTRFI-000165 | 2026-09-02 | HillInt-RTRFI-001231 | 2026-09-02 | 0 | Response | send to dar
| P1000-K03199-INNRED-HL-RFI-AR-000080-00 | 0 | INN-RED-RFI-000092 | P1000-K03199-INNRED-HL-RFI-AR-000080-00-Clarification of BOH Internal Doors Finish for Villas | 2026-08-31 | Architectural | HillInt-RFI-001102 | 2026-08-31 | 17 | Dar | Darr-GNC-001140 | 2026-09-17 | HillInt-RTRFI-001273 | 2026-09-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000081-00 | 0 | INN-RED-RFI-000089 | P1000-K03199-INNRED-HL-RFI-AR-000081-00- Clarification Required for Electric closet Door - (Townhouses & Villas) | 2026-08-30 | Architectural | HillInt-RFI-001103 | 2026-08-31 | 21 | Dar | INN-RED-RFI-000089 | 2026-09-21 | HillInt-GNC-004032 | 2026-09-22 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-00082-00 | 0 | INN-RED-RFI-000090 | P1000-K03199-INNRED-HL-RFI-AR-00082-00-Confirmation of FOH Internal Door Frame and Leaf Details | 2026-08-30 | Architectural | HillInt-RFI-001104 | 2026-08-31 | 30 | Dar | Darr-GNC-001239 | 2026-09-30 | HillInt-GNC-004505 | 2026-09-30 | 0 | Response | HillInt-GNC-004333 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-00083-00 | 0 | INN-RED-RFI-000091 | P1000-K03199-INNRED-HL-RFI-AR-00083-00-Clarification Required for Laundry Room External Door for Villas | 2026-08-30 | Architectural | HillInt-RFI-001105 | 2026-08-31 | 8 | Dar | Darr-GNC-001085 | 2026-09-08 | HillInt-RTRFI-001256 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000084-00 | 0 | INN-RED-RFI-000093 | P1000-K03199-INNRED-HL-RFI-AR-000084-00-Missing IFC Drawings – Roof Access Hatch, Roof Hatch Ladders & External Handrails | 2026-08-31 | Architectural | HillInt-RFI-001130 | 2026-08-31 | 14 | Dar | Darr-GNC-001111 | 2026-09-14 | HillInt-RTRFI-001255 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000085-00 | 0 | INN-RED-RFI-000094 | P1000-K03199-INNRED-HL-RFI-AR-000085-00-Roof Access Hatch Door & Ladder – Clarification | 2026-08-31 | Architectural | HillInt-RFI-001131 | 2026-08-31 | 14 | Dar | Darr-GNC-001113 | 2026-09-14 | HillInt-RTRFI-001254 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000086-00 | 0 | INN-RED-RFI-000095 | P1000-K03199-INNRED-HL-RFI-AR-000086-00-4BR Stair Wall-Mounted Handrail – Missing Details and BOQ Clarification | 2026-08-31 | Architectural | HillInt-RFI-001132 | 2026-08-31 | 14 | Dar | Darr-GNC-001116 | 2026-09-14 | HillInt-RTRFI-001248 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000087-00 | 0 | INN-RED-RFI-000096 | P1000-K03199-INNRED-HL-RFI-AR-000087-00-Villas 3BR & 5BR Glass Stair Handrails Not Identified in BOQ | 2026-08-31 | Architectural | HillInt-RFI-001133 | 2026-08-31 | 15 | Dar | Darr-GNC-001127 | 2026-09-15 | HillInt-RTRFI-001253 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000088-00 | 0 | INN-RED-RFI-000097 | P1000-K03199-INNRED-HL-RFI-AR-000088-00- Stair Level and Riser Height Clarification – 3BR Villa | 2026-08-31 | Architectural | HillInt-RFI-001134 | 2026-08-31 | 6 | ECG | SHKECGCR-RTRFI-000027 | 2026-09-06 | send by outlook | 2026-09-06 | 0 | Response | send by outlook
| P1000-K03199-INNRED-HL-RFI-AR-000089-00 | 0 | INN-RED-RFI-000098 | P1000-K03199-INNRED-HL-RFI-AR-000089-00-Villas Threshold Criteria – Clarification | 2026-08-31 | Architectural | HillInt-RFI-001135 | 2026-08-31 | 5 | ECG | SHKECGCR-RTRFI-000025 | 2026-09-05 | HillInt-GNC-004535 | 2026-09-06 | 0 | Response | send by outlook
| P1000-K03199-INNRED-HL-RFI-AR-00090-00 | 0 | INN-RED-RFI-000099 | P1000-K03199-INNRED-HL-RFI-AR-00090-00-Garbage Room Aluminum Pergola – Missing Details & Drawing Reference Clarification | 2026-08-31 | Architectural | HillInt-RFI-001136 | 2026-08-31 | 17 | Dar | Darr-GNC-001139 | 2026-09-17 | HillInt-RTRFI-001272 | 2026-09-17 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000091-00 | 0 | INN-RED-RFI-000100 | P1000-K03199-INNRED-HL-RFI-AR-000091-00-5 BR-SP Villas - Aluminum Glass Doors Discrepancies | 2026-08-31 | Architectural | HillInt-RFI-001137 | 2026-08-31 | 9 | ECG | SHKECGCR-RFI-000060 | 2026-09-09 | HillInt-GNC-003406 | 2026-09-09 | 0 | Response | open in dar :SHKECGCR-RFI-000060
| P1000-K03199-INNRED-HL-RFI-AR-000092-00 | 0 | INN-RED-RFI-000101 | P1000-K03199-INNRED-HL-RFI-AR-000092-00- 5 BR-MED Villas - Aluminum Glass Doors Clarification | 2026-08-31 | Architectural | HillInt-RFI-001138 | 2026-08-31 | 8 | Dar | Darr-GNC-001083 | 2026-09-08 | HillInt-RTRFI-001252 | 2026-09-15 | 0 | Response | open in dar : SHKECGCR-RFI-000062
| P1000-K03199-INNRED-HL-RFI-AR-000093-00 | 0 | INN-RED-RFI-000102 | P1000-K03199-INNRED-HL-RFI-AR-000093-00-5 BR-MEDITERRANEAN Villas - Aluminum Windows Discrepancies | 2026-08-31 | Architectural | HillInt-RFI-001139 | 2026-08-31 | 11 | ECG | SHKECGCR-RTRFI-000038 | 2026-09-11 | HillInt-GNC-003951 | 2026-09-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000094-00 | 0 | INN-RED-RFI-000103 | P1000-K03199-INNRED-HL-RFI-AR-000094-00-5 BR-SPANISH Villas - Aluminum Windows Clarification | 2026-08-31 | Architectural | HillInt-RFI-001140 | 2026-08-31 | 14 | ECG | SHKECGCR-RTRFI-000065 | 2026-09-14 | HillInt-RTRFI-001251 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000095-00 | 0 | INN-RED-RFI-000104 | P1000-K03199-INNRED-HL-RFI-ST-000095-00-Grid Discrepancy– DP03 Villas 5 Bedroom Spanish | 2026-08-31 | Structural | HillInt-RFI-001141 | 2026-08-31 | 8 | Dar | Darr-GNC-001084 | 2026-09-08 | HillInt-RTRFI-001250 | 2026-09-15 | 0 | Response | open in dar : SHKECGCR-RFI-000061
| P1000-K03199-INNRED-HL-RFI-AR-000096-00 | 0 | INN-RED-RFI-000105 | P1000-K03199-INNRED-HL-RFI-AR-000096-00-Garbage Room & Boundary Fence Walls – Missing Details & Finish Clarification | 2026-08-31 | Architectural | HillInt-RFI-001142 | 2026-08-31 | 21 | Dar | Darr-GNC-001149 | 2026-09-21 | HillInt-GNC-004001 | 2026-09-21 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000097-00 | 0 | INN-RED-RFI-000106 | P1000-K03199-INNRED-HL-RFI-AR-000097-00-Villas – Aluminum Windows Discrepancies | 2026-08-31 | Architectural | HillInt-RFI-001143 | 2026-08-31 | 14 | ECG | SHKECGCR-RTRFI-000063 | 2026-09-14 | HillInt-RTRFI-001249 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000098-00 | 0 | INN-RED-RFI-000107 | P1000-K03199-INNRED-HL-RFI-AR-000098-00-Villas – Aluminum Window WN10 size conflict | 2026-08-31 | Architectural | HillInt-RFI-001155 | 2026-09-01 | 13 | ECG | SHKECGCR-RTRFI-000064 | 2026-09-14 | HillInt-RTRFI-001246 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000099-00 | 0 | INN-RED-RFI-000108 | P1000-K03199-INNRED-HL-RFI-ST-000099-00-Clarification on whether it is structurally acceptable to connect fence footings with building footings—partially in townhouses and fully in villas—in areas where they intersect. | 2026-09-06 | Structural | HillInt-GNC-003220 | 2026-09-07 | 16 | Dar | Darr-GNC-001167 | 2026-09-23 | HillInt-GNC-004133 | 2026-09-23 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000100-00 | 0 | INN-RED-RFI-000109 | P1000-K03199-INNRED-HL-RFI-ST-000100-00-Ground Beam Depth Discrepancy for Villa 5 BR (Mediterranean Type) | 2026-09-02 | Structural | HillInt-GNC-003221 | 2026-09-07 | 8 | Dar | Darr-GNC-001131 | 2026-09-15 | HillInt-RTRFI-001263 | 2026-09-16 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000101-00 | 0 | INN-RED-RFI-000110 | P1000-K03199-RFI-GE-0000101 -00-Townhouse - Landscape Boundary Conditions for 4-Plex and 6-Plex Townhouses | 2026-09-06 | General | HillInt-GNC-003222 | 2026-09-07 | 7 | Dar | Darr-GNC-001112 | 2026-09-14 | HillInt-RTRFI-001245 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000101-01 | 1 | HillInt-GNC-004029 | Re: P1000-K03199-INNRED-HL-RFI-000101-01-Townhouse - Landscape Boundary Conditions for 4-Plex and 6-Plex Townhouses | 2026-09-29 | General | HillInt-GNC-004408 | 2026-09-29 | -46294 | DAR |  |  |  |  | 1 | Open | HillInt-GNC-004029 :RFI Rev. 01 shall be resubmitted through the same email thread used for Rev. 00. Please do not create a new email thread. You are also required to ensure that the RFI REF is correctly stated and that the Discipline is properly included in the reference prior to resubmission
| P1000-K03199-INNRED-HL-RFI-00102-00 | 0 | INN-RED-RFI-000111 | P1000-K03199-INNRED-HL-RFI-00102-00-Additional Wall for Concealment of Plumbing Pipes | 2026-09-06 | Mechanical | HillInt-GNC-003223 | 2026-09-07 | 7 | ECG | SHKECGCR-RTRFI-000044 | 2026-09-14 | HillInt-RTRFI-001247 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000103-00 | 0 | INN-RED-RFI-000113 | P1000-K03199-INNRED-HL-RFI-ST-000103-00-Structural Interconnection of Fence Foundations with 4-Plex & 6-Plex Townhouses | 2026-09-07 | Structural | HillInt-GNC-003226 | 2026-09-07 | 14 | ECG | SHKECGCR-RTRFI-000072 | 2026-09-21 | HillInt-GNC-003976 | 2026-09-21 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000104-00 | 0 | INN-RED-RFI-000114 | P1000-K03199-INNRED-HL-RFI-GE-000104-00-Sunken Slab Required in All Wet Areas | 2026-09-07 | General | HillInt-RFI-001182 | 2026-09-08 | 5 | ECG | SHKECGCR-RTRFI-000061 | 2026-09-13 | HillInt-RTRFI-001242 | 2026-09-15 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000105-00 | 0 | INN-RED-RFI-000115 | P1000-K03199-INNRED-HL-RFI-GE-000105-00-Missing Infrastructure Services and Utilities Packages in DD 100% Submission | 2026-09-10 | General | HillInt-GNC-003485 | 2026-09-10 | -46275 | DAR |  |  |  |  | 20 | Open | HillInt-GNC-004335 : reminder
| P1000-K03199-INNRED-HL-RFI-GE-000106-00 | 0 | INN-RED-RFI-000116 | P1000-K03199-INNRED-HL-RFI-GE-000106-00 - Plumbing work clash with Structural wall | 2026-09-14 | General | HillInt-GNC-003884 | 2026-09-20 | 7 | ECG | SHKECGCR-RTRFI-000088 | 2026-09-27 | HillInt-GNC-004270 | 2026-09-27 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000107-00 | 0 | INN-RED-RFI-000117 | P1000-K03199-INNRED-HL-RFI-GE-000107-00-Townhouses – Discrepancies in Balcony Floor Levels. | 2026-09-14 | General | HillInt-GNC-003885 | 2026-09-20 | 11 | ECG | SHKECGCR-RTRFI-000117 | 2026-10-01 | HillInt-GNC-004576 | 2026-10-01 | 0 | Response | HillInt-GNC-004336 : reminder
| P1000-K03199-INNRED-HL-RFI-GE-000108-00 | 0 | INN-RED-RFI-000118 | P1000-K03199-INNRED-HL-RFI-GE-000108-00-Townhouses – 4-Bedroom Entrance Opening Head Level. | 2026-09-14 | General | HillInt-GNC-003888 | 2026-09-20 | 7 | ECG | SHKECGCR-RTRFI-000093 | 2026-09-27 | HillInt-GNC-004274 | 2026-09-27 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000109-00 | 0 | INN-RED-RFI-000119 | P1000-K03199-INNRED-HL-RFI-AR-000109-00-5 BR MED Villas – Clarification of External Limestone Finish | 2026-09-14 | Architectural | HillInt-GNC-003889 | 2026-09-20 | 13 | Dar | Darr-GNC-001248 | 2026-10-03 | HillInt-GNC-004626 | 2026-10-04 | 0 | Response | HillInt-GNC-004341: reminder
| P1000-K03199-INNRED-HL-RFI-ME-000110-00 | 0 | INN-RED-RFI-000120 | P1000-K03199-INNRED-HL-RFI-ME-000110-00-Clarification of Water Supply Pipe Diameter | 2026-09-14 | Mechanical | HillInt-GNC-003890 | 2026-09-20 | 10 | Dar | Darr-GNC-001240 | 2026-09-30 | HillInt-GNC-004506 | 2026-09-30 | 0 | Response | HillInt-GNC-004342: reminder
| P1000-K03199-INNRED-HL-RFI-AR-000111-00 | 0 | INN-RED-RFI-000121 | P1000-K03199-INNRED-HL-RFI-AR-000111-00-3 BR MED Villas – Discrepancy in External Limestone Finish | 2026-09-14 | Architectural | HillInt-GNC-003892 | 2026-09-20 | 13 | Dar | Darr-GNC-001250 | 2026-10-03 | HillInt-GNC-004631 | 2026-10-04 | 0 | Response | HillInt-GNC-004536 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000112-00 | 0 | INN-RED-RFI-000122 | P1000-K03199-INNRED-HL-RFI-AR-000112-00-Villas All Types – DT02 size Discrepancy | 2026-09-14 | Architectural | HillInt-GNC-003893 | 2026-09-20 | 8 | ECG | SHKECGCR-RTRFI-000097 | 2026-09-28 | HillInt-GNC-004320 | 2026-09-28 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000113-00 | 0 | INN-RED-RFI-000123 | P1000-K03199-INNRED-HL-RFI-000113-00-Villas All Types – Wooden Doors Size Discrepancies | 2026-09-14 | Architectural | HillInt-GNC-003894 | 2026-09-20 | 11 | ECG | SHKECGCR-RTRFI-000112 | 2026-10-01 | HillInt-GNC-004537 | 2026-10-01 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000114-00 | 0 | INN-RED-RFI-000124 | P1000-K03199-INNRED-HL-RFI-000114-00-5 BR-MED Villas – Wooden Doors Discrepancies | 2026-09-14 | Architectural | HillInt-GNC-003895 | 2026-09-20 | 17 | DAR | SHKECGCR-RTRFI-000182 | 2026-10-07 | HillInt-GNC-004934 | 2026-10-07 | 0 | Response | HillInt-GNC-004538 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000115-00 | 0 | INN-RED-RFI-000125 | P1000-K03199-INNRED-HL-RFI-000115-00-5 BR-SPA Villas – Wooden Doors Discrepancies | 2026-09-14 | Architectural | HillInt-GNC-003896 | 2026-09-20 | 17 | DAR | SHKECGCR-RTRFI-000180 | 2026-10-07 | HillInt-GNC-004929 | 2026-10-07 | 0 | Response | HillInt-GNC-004540 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000116-00 | 0 | INN-RED-RFI-000126 | P1000-K03199-INNRED-HL-RFI-000116-00-Villas All Types – Missing Single-Leaf Telecom Closet Door Details | 2026-09-14 | Architectural | HillInt-GNC-003897 | 2026-09-20 | 13 | Dar | Darr-GNC-001256 | 2026-10-03 | HillInt-GNC-004650 | 2026-10-04 | 0 | Response | HillInt-GNC-004541 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000117-00 | 0 | INN-RED-RFI-000127 | P1000-K03199-INNRED-HL-RFI-AR-000117-00-5 BR Villas – Clarification of Garbage Room Location and Arrangement | 2026-09-14 | Architectural | HillInt-GNC-003898 | 2026-09-20 | 14 | Dar | Darr-GNC-001249 | 2026-10-04 | HillInt-GNC-004630 | 2026-10-04 | 0 | Response | HillInt-GNC-004542 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000118-00 | 0 | INN-RED-RFI-000128 | P1000-K03199-INNRED-HL-RFI-000118-00-Villas All Types – Electrical & Telecom Closet Doors Discrepancies | 2026-09-15 | Architectural | HillInt-GNC-003899 | 2026-09-20 | 17 | DAR | SHKECGCR-RTRFI-000183 | 2026-10-07 | HillInt-GNC-004935 | 2026-10-07 | 0 | Response | HillInt-GNC-004544 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000119-00 | 0 | INN-RED-RFI-000129 | P1000-K03199-INNRED-HL-RFI-000119-00-3BR & 4BR Villas – Flush Tank Accommodation & Wall Arrangement Clarification | 2026-09-15 | Architectural | HillInt-GNC-003900 | 2026-09-20 | 13 | Dar | Darr-GNC-001255 | 2026-10-03 | HillInt-GNC-004648 | 2026-10-04 | 0 | Response | HillInt-GNC-004545 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000120-00 | 0 | INN-RED-RFI-000130 | P1000-K03199-INNRED-HL-RFI-AR-000120-00-5 BR MED – Electrical & Telecom Closet Doors Size Discrepancies | 2026-09-15 | Architectural | HillInt-GNC-003901 | 2026-09-20 | 13 | Dar | Darr-GNC-001257 | 2026-10-03 | HillInt-GNC-004652 | 2026-10-04 | 0 | Response | HillInt-GNC-004546 : reminder
| P1000-K03199-INNRED-HL-RFI-ELE-000121-00 | 0 | INN-RED-RFI-000131 | P1000-K03199-INNRED-HL-RFI-ELE-000121-00-Official Confirmation on Electrical Low Current Scope for Townhouses/Villas | 2026-09-15 | Electrical | HillInt-GNC-003902 | 2026-09-20 | -46285 | DAR |  |  |  |  | 15 | Open | HillInt-GNC-004547 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000122-00 | 0 | INN-RED-RFI-000132 | P1000-K03199-INNRED-HL-RFI-000122-00-Villas Openings – Missing Schedule, Tags & Rough Opening Details | 2026-09-15 | Architectural |  |  |  | ECG | SHKECGCR-GNC-000293 | 2026-09-17 | HillInt-GNC-003903 | 2026-09-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000123-00 | 0 | INN-RED-RFI-000133 | P1000-K03199-INNRED-HL-RFI-AR-000123-00-3 BR Villas - Wooden Doors Discrepancies | 2026-09-15 | Architectural | HillInt-GNC-003905 | 2026-09-20 | 14 | ECG | SHKECGCR-RTRFI-000123 | 2026-10-04 | HillInt-GNC-004624 | 2026-10-04 | 0 | Response | HillInt-GNC-004548 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000124-00 | 0 | INN-RED-RFI-000134 | P1000-K03199-INNRED-HL-RFI-AR-000124-00-Villas All Types – Fence Gate Width Discrepancy | 2026-09-15 | Architectural | HillInt-GNC-003912 | 2026-09-20 | 15 | Dar | Darr-GNC-001266 | 2026-10-05 | HillInt-GNC-004768 | 2026-10-05 | 0 | Response | HillInt-GNC-004549 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000125-00 | 0 | INN-RED-RFI-000135 | P1000-K03199-INNRED-HL-RFI-AR-000125-00-5 BR - Villas – Wooden Doors Discrepancies | 2026-09-15 | Architectural | HillInt-GNC-003926 | 2026-09-20 | 14 | ECG | SHKECGCR-RTRFI-000122 | 2026-10-04 | HillInt-GNC-004616 | 2026-10-04 | 0 | Response | HillInt-GNC-004556 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000126-00 | 0 | INN-RED-RFI-000136 | P1000-K03199-INNRED-HL-RFI-000126-00-4 BR - Mediterranean Villas - Door Type Discrepancy Between Plan & Elevation | 2026-09-15 | Architectural | HillInt-GNC-003929 | 2026-09-20 | 12 | ECG | SHKECGCR-RTRFI-000119 | 2026-10-02 |  | 2026-10-04 | 0 | Response | HillInt-GNC-004555 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000127-00 | 0 | INN-RED-RFI-000137 | P1000-K03199-INNRED-HL-RFI-AR-000127-00-4 BR Villas – Wooden Doors Discrepancies | 2026-09-15 | Architectural | HillInt-GNC-003930 | 2026-09-20 | 14 | ECG | SHKECGCR-RTRFI-000125 | 2026-10-04 | HillInt-GNC-004625 | 2026-10-04 | 0 | Response | HillInt-GNC-004557 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000128-00 | 0 | INN-RED-RFI-000173 | P1000-K03199-INNRED-HL-RFI-000128-00-Villas All Types – DT11 & Fence Gate Discrepancy | 2026-09-30 | Architectural | HillInt-GNC-004448 | 2026-09-30 | -46295 | DAR |  |  |  |  | 0 | Open | HillInt-GNC-004737 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000129-00 | 0 | INN-RED-RFI-000139 | P1000-K03199-INNRED-HL-RFI-000129-00 - Villas All Types – DT01 Discrepancy | 2026-09-15 | Architectural | HillInt-GNC-003932 | 2026-09-20 | 13 | ECG | SHKECGCR-RTRFI-000129 | 2026-10-03 | HillInt-GNC-004651 | 2026-10-04 | 0 | Response | HillInt-GNC-004558 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000130-00 | 0 | INN-RED-RFI-000140 | P1000-K03199-INNRED-HL-RFI-AR-000130-00 - Villas All Types – DT07 Discrepancy | 2026-09-15 | Architectural | HillInt-GNC-003933 | 2026-09-20 | 14 | ECG | SHKECGCR-RTRFI-000131 | 2026-10-04 | HillInt-GNC-004663 | 2026-10-04 | 0 | Response | HillInt-GNC-004559 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000131-00 | 0 | INN-RED-RFI-000141 | P1000-K03199-INNRED-HL-RFI-AR-000131-00 - Villas All Types – Missing Wooden Door Details In The Doors & Windows Detail | 2026-09-15 | Architectural | HillInt-GNC-003934 | 2026-09-20 | 15 | Dar | Darr-GNC-001267 | 2026-10-05 | HillInt-GNC-004769 | 2026-10-05 | 0 | Response | HillInt-GNC-004560 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000132-00 | 0 | INN-RED-RFI-000142 | P1000-K03199-INNRED-HL-RFI-AR-000132-00 - Villas Stair–Curtain Wall Door Interface and CW-02 Arrangement Clarification | 2026-09-15 | Architectural | HillInt-GNC-003935 | 2026-09-20 | 7 | ECG | SHKECGCR-RTRFI-000079 | 2026-09-27 | HillInt-GNC-004272 | 2026-09-27 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000133-00 | 0 | INN-RED-RFI-000143 | P1000-K03199-INNRED-HL-RFI-AR-000133-00 - Roof Waterproofing Discrepancy – 3BR Villa | 2026-09-15 | Architectural | HillInt-GNC-003939 | 2026-09-20 | 13 | ECG | SHKECGCR-RTRFI-000127 | 2026-10-03 | HillInt-GNC-004634 | 2026-10-04 | 0 | Response | HillInt-GNC-004561 :reminder
| P1000-K03199-INNRED-HL-RFI-AR-000134-00 | 0 | INN-RED-RFI-000144 | P1000-K03199-INNRED-HL-RFI-AR-000134-00 - Elevation Groove – Missing Details & Reveal Reference | 2026-09-15 | Architectural | HillInt-GNC-003940 | 2026-09-20 | 14 | Dar | Darr-GNC-001251 | 2026-10-04 | HillInt-GNC-004632 | 2026-10-04 | 0 | Response | HillInt-GNC-004562 : reminder
| P1000-K03199-INNRED-HL-RFI-ELE-000135-00 | 0 | INN-RED-RFI-000145 | P1000-K03199-INNRED-HL-RFI-000135-00- Lighting Installation Coordination with Pergola Steel Structure | 2026-09-16 | Electrical | HillInt-GNC-003942 | 2026-09-20 | 10 | Dar | Darr-GNC-001241 | 2026-09-30 | HillInt-GNC-004507 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000136-00 | 0 | INN-RED-RFI-000146 | P1000-K03199-INNRED-HL-RFI-000136-00-Townhouses – Missing External Skirting | 2026-09-16 | Architectural | HillInt-GNC-003943 | 2026-09-20 | 10 | ECG | SHKECGCR-RTRFI-000104 | 2026-09-30 | HillInt-GNC-004465 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000137-00 | 0 | INN-RED-RFI-000147 | P1000-K03199-INNRED-HL-RFI-000137-00-Townhouses – Discrepancies Between ID and Façade IFC Packages – Terraces Floor Finish. | 2026-09-16 | Architectural | HillInt-GNC-003944 | 2026-09-20 | 10 | ECG | SHKECGCR-RTRFI-000110 | 2026-09-30 | HillInt-GNC-004473 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-AR-000138-00 | 0 | INN-RED-RFI-000148 | P1000-K03199-INNRED-HL-RFI-000138-00-Townhouses – Missing External Handrail Details | 2026-09-16 | Architectural | HillInt-GNC-003945 | 2026-09-20 | 13 | Dar | Darr-GNC-001254 | 2026-10-03 | HillInt-GNC-004644 | 2026-10-04 | 0 | Response | HillInt-GNC-004563 : reminder
| P1000-K03199-INNRED-HL-RFI-AR--000139-00 | 0 | INN-RED-RFI-000149 | P1000-K03199-INNRED-HL-RFI-000139-00-Townhouses – 4Bedroom Entrance Opening Head Level | 2026-09-16 | Architectural | HillInt-GNC-003946 | 2026-09-20 | -46285 |  |  |  | HillInt-GNC-003946 | 2026-09-20 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000140-00 | 0 | INN-RED-RFI-000150 | P1000-K03199-INNRED-HL-RFI-ST-000140-00-Discrepancy in Floor Levels and Missing IFC Drawings for Plexes Nos. 101, 97, 99, 76, and 68 | 2026-09-17 | Structural | HillInt-GNC-003817 | 2026-09-20 | 2 | Dar | Darr-GNC-001163 | 2026-09-22 | HillInt-GNC-004130 | 2026-09-23 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ELE-000141-00 | 0 | INN-RED-RFI-000151 | P1000-K03199-INNRED-HL-RFI-000141-00-Missing Lighting Switch for Wardrobe Lighting | 2026-09-20 | Electrical | HillInt-GNC-003947 | 2026-09-20 | 10 | Dar | Darr-GNC-001242 | 2026-09-30 | HillInt-GNC-004508 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000142-00 | 0 | INN-RED-RFI-000152 | P1000-K03199-INNRED-HL-RFI-000142-00-Location and Elevation of Sockets and Façade Lighting | 2026-09-20 | General | HillInt-GNC-003948 | 2026-09-20 | 13 | Dar | Darr-GNC-001252 | 2026-10-03 | HillInt-GNC-004633 | 2026-10-04 | 0 | Response | HillInt-GNC-004565 : reminder
| P1000-K03199-INNRED-HL-RFI-ME-000143-00 | 0 | INN-RED-RFI-000153 | P1000-K03199-INNRED-HL-RFI-ME-000143-00-Clarification of Airflow Requirements for Exhaust & Fresh Air Fans | 2026-09-20 | Mechanical | HillInt-GNC-004000 | 2026-09-21 | 9 | Dar | Darr-GNC-001236 | 2026-09-30 | HillInt-GNC-004504 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-GE-000144-00 | 0 | INN-RED-RFI-000155 | P1000-K03199-INNRED-HL-RFI-000144-00-Conflict Between Electrical IFC and ID Drawings for Appliance | 2026-09-21 | General | HillInt-GNC-004030 | 2026-09-22 | 8 | Dar | Darr-GNC-001245 | 2026-09-30 | HillInt-GNC-004509 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-ST-000145-00 | 0 | INN-RED-RFI-000156 | P1000-K03199-INNRED-HL-RFI-000145-00-Request for IFC Drawings and Foundation Package for 4plex 1 Step Mirror (Plex No. 66) | 2026-09-21 | Structural | HillInt-GNC-004031 | 2026-09-22 | 11 | Dar | Darr-GNC-001253 | 2026-10-03 | HillInt-GNC-004642 | 2026-10-04 | 0 | Response | HillInt-GNC-004575 :reminder
| P1000-K03199-INNRED-HL-RFI-000146-00 | 0 | INN-RED-RFI-000157 | Clash Duct with Sunken Slab | 2026-09-22 | General | HillInt-GNC-004128 | 2026-09-23 | 5 | ECG | SHKECGCR-RTRFI-000098 | 2026-09-28 | HillInt-GNC-004321 | 2026-09-28 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000146-01 | 0 | INN-RED-RFI-000174 | Clash Duct with Sunken Slab | 2026-10-01 | General | HillInt-GNC-004583 | 2026-10-01 | 5 | ECG | SHKECGCR-RTRFI-000148 | 2026-10-06 | HillInt-GNC-004855 | 2026-10-06 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000147-00 | 0 | INN-RED-RFI-000158 | P1000-K03199-INNRED-HL-RFI-000147-00-Raceway Routing Criteria for Roof Electrical Circuits | 2026-09-25 | General | HillInt-GNC-004266 | 2026-09-27 | 10 | DAR | SHKECGCR-RTRFI-000168 | 2026-10-07 | HillInt-GNC-004918 | 2026-10-07 | 0 | Response | HillInt-GNC-004739 : reminder
| P1000-K03199-INNRED-HL-RFI-000148-00 | 0 | INN-RED-RFI-000159 | P1000-K03199-INNRED-HL-RFI-000148-00-STRUCTURAL DETAIL FOR 50 CM LEVEL STEPS IN SOG – STEPPED TOWNHOUSES | 2026-09-25 | Structural | HillInt-GNC-004269 | 2026-09-27 | 10 | DAR | SHKECGCR-RTRFI-000179 | 2026-10-07 | HillInt-GNC-004926 | 2026-10-07 | 0 | Response | HillInt-GNC-004740 : reminder
| P1000-K03199-INNRED-HL-RFI-000149-00 | 0 | INN-RED-RFI-000160 | P1000-K03199-INNRED-HL-RFI-000149-00-5 Bedroom Villas – Discrepancy in Masonry Wall Type | 2026-09-25 | Architectural | HillInt-GNC-004271 | 2026-09-27 | -46292 | ECG |  |  |  |  | 5 | Open | HillInt-GNC-004774 : reminder
| P1000-K03199-INNRED-HL-RFI-000150-00 | 0 | INN-RED-RFI-000161 | P1000-K03199-INNRED-HL-RFI-000150-00-Mediterranean Villas – Clarification on External Paint Finishes | 2026-09-25 | Architectural | HillInt-GNC-004273 | 2026-09-27 | -46292 | ECG |  |  |  |  | 5 | Open | HillInt-GNC-004775 : reminder
| P1000-K03199-INNRED-HL-RFI-000151-00 | 0 | INN-RED-RFI-000162 | P1000-K03199-INNRED-HL-RFI-000151-00-Villas All Types – Cement and Sand Plaster Thickness Discrepancies | 2026-09-25 | Architectural | HillInt-GNC-004275 | 2026-09-27 | 3 | ECG | HillInt-GNC-004471 | 2026-09-30 | HillInt-GNC-004471 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000152-00 | 0 | INN-RED-RFI-000163 | P1000-K03199-INNRED-HL-RFI-000152-00-3 BR SPA VILLAS – Handrail Not Indicated in IFC Drawings | 2026-09-25 | Architectural | HillInt-GNC-004277 | 2026-09-27 | 10 | DAR | SHKECGCR-RTRFI-000173 | 2026-10-07 | HillInt-GNC-004919 | 2026-10-07 | 0 | Response | HillInt-GNC-004736 : reminder
| P1000-K03199-INNRED-HL-RFI-000153-00 | 0 | INN-RED-RFI-000164 | P1000-K03199-INNRED-HL-RFI-000153-00-Villas External Windows & Doors Wall Type Identification & BOQ Discrepancy | 2026-09-25 | Architectural | HillInt-GNC-004279 | 2026-09-27 | 9 | ECG | SHKECGCR-RTRFI-000163 | 2026-10-06 | HillInt-GNC-004871 | 2026-10-07 | 0 | Response | HillInt-GNC-004776 : reminder
| P1000-K03199-INNRED-HL-RFI-000154-00 | 0 | INN-RED-RFI-000165 | P1000-K03199-INNRED-HL-RFI-000154-00-Villas All Types – Handrail Height Discrepancy and Missing Reference Drawing | 2026-09-25 | Architectural | HillInt-GNC-004281 | 2026-09-27 | 6 | Dar | Darr-GNC-001258 | 2026-10-03 | HillInt-GNC-004654 | 2026-10-04 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000155-00 | 0 | INN-RED-RFI-000166 | P1000-K03199-INNRED-HL-RFI-000155-00-Villas All Types – Terrace Floor Tile Discrepancy | 2026-09-26 | Architectural | HillInt-GNC-004280 | 2026-09-27 | 9 | ECG | SHKECGCR-RTRFI-000146 | 2026-10-06 | HillInt-GNC-004851 | 2026-10-06 | 0 | Response | HillInt-GNC-004777 : reminder
| P1000-K03199-INNRED-HL-RFI-000156-00 | 0 | INN-RED-RFI-000167 | P1000-K03199-INNRED-HL-RFI-000156-00-Stair Tread Thickness Discrepancy – 3BR & 5BR Villas | 2026-09-26 | Architectural | HillInt-GNC-004282 | 2026-09-27 | 3 | ECG | SHKECGCR-RTRFI-000105 | 2026-09-30 | HillInt-GNC-004470 | 2026-09-30 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000157-00 | 0 | INN-RED-RFI-000168 | P1000-K03199-INNRED-HL-RFI-000157-00-Clarification of Swimming Pool Drainage Level and House Connection | 2026-09-26 | Mechanical | HillInt-GNC-004285 | 2026-09-27 | 8 | Dar | Darr-GNC-001265 | 2026-10-05 | HillInt-GNC-004704 | 2026-10-05 | 0 | Response
| P1000-K03199-INNRED-HL-RFI-000158-00 | 0 | INN-RED-RFI-000170 | P1000-K03199-INNRED-HL-RFI-000158-00-Conflict Between( cg.Columns & cg.Footing)– DP03 Villas 5 Bedroom Spanish | 2026-09-29 | Structural | HillInt-GNC-004412 | 2026-09-29 | -46294 | ECG |  |  |  |  | 1 | Open | HillInt-GNC-004741 : reminder
| P1000-K03199-INNRED-HL-RFI-000159-00 | 0 | INN-RED-RFI-000171 | P1000-K03199-INNRED-HL-RFI-000159-00-Missing Data Outlet in Electrical IFC Drawing. | 2026-09-29 | All Disciplines | HillInt-GNC-004413 | 2026-09-29 | 8 | DAR | SHKECGCR-RTRFI-000177 | 2026-10-07 | HillInt-GNC-004922 | 2026-10-07 | 0 | Response | HillInt-GNC-004738 : reminder
| P1000-K03199-INNRED-HL-RFI-AR-000160-00 | 0 | INN-RED-RFI-000175 | P1000-K03199-INNRED-HL-RFI-AR-000160-00-Request for Missing B.O.Q Quantities for Porcelain Tiles | 2026-10-05 | All Disciplines | HillInt-GNC-004688 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000161-00 | 0 | INN-RED-RFI-000176 | P1000-K03199-INNRED-HL-RFI-000161-00-Request for Missing B.O.Q Quantities for Mirrors | 2026-10-05 | Architectural | HillInt-GNC-004689 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000162-00 | 0 | INN-RED-RFI-000177 | P1000-K03199-INNRED-HL-RFI-AR-000162-00-Request for Missing IFC Drawings and B.O.Q Quantities for Shower Area Glazed Partitions | 2026-10-05 | Architectural | HillInt-GNC-004691 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000163-00 | 0 | INN-RED-RFI-000178 | P1000-K03199-INNRED-HL-RFI-AR-000163-00-Request for Missing B.O.Q Quantities for General Signage | 2026-10-05 | Architectural | HillInt-GNC-004693 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000164-00 | 0 | INN-RED-RFI-000179 | P1000-K03199-INNRED-HL-RFI-AR-000164-00-Request for Missing B.O.Q Quantities for Toilet Accessories | 2026-10-05 | Architectural | HillInt-GNC-004695 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000165-00 | 0 | INN-RED-RFI-000180 | P1000-K03199-INNRED-HL-RFI-AR-000165-00-Request for Missing B.O.Q Quantities for White Goods | 2026-10-05 | Architectural | HillInt-GNC-004696 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000166-00 | 0 | INN-RED-RFI-000181 | P1000-K03199-INNRED-HL-RFI-AR-000166-00-Request for Missing B.O.Q, IFC Drawings, and B.O.Q Quantities for Glazing Work and Ironmongery Package | 2026-10-05 | Architectural | HillInt-GNC-004697 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000167-00 | 0 | INN-RED-RFI-000182 | P1000-K03199-INNRED-HL-RFI-AR-000167-00-Request for Confirmation on Final Bill of Quantities (BOQ) Version | 2026-10-05 | Architectural | HillInt-GNC-004701 | 2026-10-05 | -46300 | [5 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000168-00 | 0 | INN-RED-GNC-000012 | P1000-K03199-INNRED-HL-RFI-AR-000168-00- Missing IFC Drawings for GRC Windows in Façade Elements | 2026-10-06 | Architectural | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000169-00 | 0 | INN-RED-GNC-000013 | P1000-K03199-INNRED-HL-RFI-AR-000169-00-Curtain Wall Conflict Between Codes, BOQ, and Drawings. | 2026-10-06 | Architectural | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000170-00 | 0 | INN-RED-GNC-000014 | P1000-K03199-INNRED-HL-RFI-GE-000170-00-Terrace Pipework Clash with Structural Slab | 2026-10-06 | Architectural | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-000172-00 | 0 | INN-RED-GNC-000015 | P1000-K03199-INNRED-HL-RFI-000172-00-Townhouses – Confirmation of Material Finish Codes | 2026-10-06 | Architectural | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000173-00 | 0 | INN-RED-GNC-000016 | P1000-K03199-INNRED-HL-RFI-GE-000173-00-Townhouses – 6 plex Arch & Str. Elevations Discrepancy | 2026-10-06 | Architectural | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-AR-000174-00 | 0 | INN-RED-GNC-000017 | P1000-K03199-INNRED-HL-RFI-AR-000174-00-Townhouses – Missing Steel Ladder & Roof Access Door Details | 2026-10-06 | Architectural | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000175-00 | 0 | INN-RED-RFI-000189 | P1000-K03199-INNRED-HL-RFI-GE-000175-00-Terrace Pipework Clash with Structural Slab | 2026-10-06 | All Disciplines | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000176-00 | 0 | INN-RED-RFI-000189 | P1000-K03199-INNRED-HL-RFI-GE-000176-00-ROOF SPOUT OVERFLOW LEVEL APPROVAL | 2026-10-06 | All Disciplines | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000177-00 | 0 |  | P1000-K03199-INNRED-HL-RFI-GE-000177-00-Clash Between First Floor Terrace Drainage Pipe, Concrete Upstand and Handrail FOR (4BEDROOM MEDITERRANEAN &5BEDROOM MEDITERRANEAN) | 2026-10-06 | All Disciplines | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000178-00 | 0 |  | P1000-K03199-INNRED-HL-RFI-GE-000178-00-Clarification on Structural Details – Stepped Townhouses | 2026-10-06 | All Disciplines | [8 empty] | 0 | Open
| P1000-K03199-INNRED-HL-RFI-GE-000179-00 | 0 | INN-RED-RFI-000193 | P1000-K03199-INNRED-HL-RFI-GE-000179-00-Request for Revised IFC MEP Drawings for Townhouses Following New Specifications for Centralized Water Heating Replacement | 2026-10-07 | All Disciplines | [8 empty] | 0 | Open