## Dashboard
RFI LOG DASHBOARD DP06
TOTAL ITEMS |  | PENDING |  | RESPONDED
96 |  | 35 |  | 61
Discipline | Total | Pending | Responded | Response Rate
Architectural | 10 | #VALUE! | #VALUE! | 0%
Structural | 61 | #VALUE! | #VALUE! | 0%
Mechanical | 4 | #VALUE! | #VALUE! | 0%
Electrical | 5 | #VALUE! | #VALUE! | 0%
General | 1 | #VALUE! | #VALUE! | 0%
GRAND TOTAL | 81 | #VALUE! | #VALUE! | 0%
Month | Total | Pending | Responded
2026-06-01 | 6 | #VALUE! | #VALUE!
2026-07-01 | 9 | #VALUE! | #VALUE!
2026-08-01 | 21 | #VALUE! | #VALUE!
2026-09-01 | 41 | #VALUE! | #VALUE!
2026-10-01 | 4 | #VALUE! | #VALUE!
Discipline |  | Pending | Responded
Architectural |  | #VALUE! | #VALUE!
Structural |  | #VALUE! | #VALUE!
Mechanical |  | #VALUE! | #VALUE!
Electrical |  | #VALUE! | #VALUE!
General |  | #VALUE! | #VALUE!
Formulas:
Total = COUNTIFS(RFI!$R5:R4998,">="&[TOTAL ITEMS],RFI!$R5:R4998,"<"&EDATE([TOTAL ITEMS],1))
PENDING = COUNTIFS(RFI!$R5:R4998,">="&[TOTAL ITEMS],RFI!$R5:R4998,"<"&EDATE([TOTAL ITEMS],1),RFI!$O5:O5012,"open*")
Responded = COUNTIFS(RFI!$R5:R4998,">="&[TOTAL ITEMS],RFI!$R5:R4998,"<"&EDATE([TOTAL ITEMS],1),RFI!$O5:O5012,"Response*")

## RFI
(RFI) - Request For Information Log For Design Pakage DP06 | [13 empty] | ALL | 96
[14 empty] | Response | 61
HAC TO HILL | [5 empty] | Hill to shaker |  | Hill to AEDAS |  | Dewan to hill |  | hill TO HAC |  | open | 35
Mail No | Mail No | REV | RFI No | Subject | Date | Mail No2 | Date3 | Mail No4 | Date5 | Mail No6 | Date7 | Mail No8 | Date9 | Status | Notes | Discipline (Auto) | RFI Date (Auto)
| HAC-RFI-000057 | 0 | P1000-K03206-HA-HI-ST-RFI-000001 | for Missing Details Related to Hotel Excavation and Blinding Works (DP6-Hotel). | 2026-06-20 | HillInt-RFI-000587 | 24/06/2026 |  |  |  |  | HillInt-RTRFI-000754 | 2026-07-09 | Response |  | Structural | 2026-06-20
| HAC-RFI-000058 | 0 | P1000-K03206-HA-HI-ST-RFI-000002 | for Proposed Project Sign Board Location for Approval (At the entrance of DP06 project). | 2026-06-20 | HillInt-RFI-000588 | 24/06/2026 |  |  |  |  | HillInt-RTRFI-000750 3 39 1 | 2026-07-09 | Response |  | Structural | 2026-06-20
| HAC-RFI-000146 | 1 | P1000-K03206-HA-HI-ST-RFI-000002 | for Proposed Project Sign Board Location for Approval (At the entrance of DP06 project). | 2026-10-08 | HillInt-RFI-000910 | 2026-08-12 | HillInt-RFI-000910 | 2026-08-12 |  |  | HillInt-GNC-004142 |  | Response |  | Structural | 2026-10-08
CCCEGY-RFI-000001 | HAC-RFI-000059 | 0 | P1000-K03206-HA-HI-ST-RFI-000003 | for DP06 Dump area, Main Mobilizations and Site Mobilization Location. | 2026-06-20 | HillInt-RFI-000589 | 24/06/2026 |  |  |  |  | HillInt-RTRFI-000751 | 2026-07-09 | Response |  | Structural | 2026-06-20
CCCEGY-RFI-000002 | HAC-RFI-000060 | 0 | P1000-K03206-HA-HI-ST-RFI-000004 | for DP06 Access Roads approval (At the entrance of DP06 project). | 2026-06-20 | HillInt-RFI-000590 | 24/06/2026 | [6 empty] | open |  | Structural | 2026-06-20
CCCEGY-RFI-000003 | HAC-RFI-000061 | 0 | P1000-K03206-HA-HI-ST-RFI-000005 | for Request for Temporary 12 m Boundary Offset for Construction Access (DP6). | 2026-06-20 | HillInt-RFI-000591 | 24/06/2026 |  |  |  |  | SHKECGCR-RTRFI-000010 | 2026-07-01 | Response |  | Structural | 2026-06-20
| HAC-RFI-000069 | 0 | P1000-K03206-HA-HI-ST-RFI-000006 | for Existing Military Building Obstructing Villa C1-25 and Access Road (DP6-Villa C1-25). | 2026-06-20 | HAC-RFI-000069 | 25/06/2026 |  |  |  |  | HillInt-RTRFI-000753 | 2026-07-09 | Response |  | Structural | 2026-06-20
| HAC-RFI-000080 | 0 | P1000-K03206-HA-HI-AR-RFI-000007 | for Request for Approval of Proposed Hotel Mock-Up Strategy ( At Hotel of DP06 project). | 2026-07-03 |  |  | HillInt-RFI-000622 | 2026-07-04 |  |  |  |  | open |  | Architectural | 2026-07-03
| HAC-RFI-000081 | 0 | P1000-K03206-HA-HI-AR-RFI-000008 | Request for Approval of Proposed Villas Mock-Up Strategy (Villa mockups). | 2026-07-03 |  |  | HillInt-RFI-000621 | 2026-07-04 |  |  | HillInt-RTRFI-001118 | 2026-08-27 | Response |  | Architectural | 2026-07-03
| HAC-RFI-000097 | 0 | P1000-K03206-HA-HI-GE-RFI-000009 | P1000-K03206-HA-HI-GE-RFI-000009 for DP6 Drawing Naming Convention. | 2026-07-13 |  |  | HillInt-RFI-001084 | 2026-08-27 |  |  |  |  | open |  | General | 2026-07-13
| HAC-RFI-000117 | 0 | P1000-K03206-HA-HI-GE-RFI-000010 | P1000-K03206-HA-HI-EL-RFI-000010 for Mockup's Lighting Shopdrawing Requirement (3BR VIP suit mockup). | 2026-07-30 |  |  | HillInt-RFI-000895 | 2026-08-14 |  |  |  |  | open |  | Electrical | 2026-07-30
| HAC-RFI-000118 | 0 | P1000-K03206-HA-HI-GE-RFI-000011 | P1000-K03206-HA-HI-EL-RFI-000011 for Mockup's Emergency Lighting Shopdrawing Requirement (3BR VIP suit mockup). | 2026-07-30 |  |  | HillInt-RFI-000896 | 2026-08-14 |  |  |  |  | open |  | Electrical | 2026-07-30
| HAC-RFI-000119 | 0 | P1000-K03206-HA-HI-GE-RFI-000012 | P1000-K03206-HA-HI-EL-RFI-000012 for Mockup's Voice and Data Shopdrawing Requirement (3BR VIP suit mockup). | 2026-07-30 |  |  | HillInt-RFI-000897 | 2026-08-14 |  |  |  |  | open |  | Electrical | 2026-07-30
| HAC-RFI-000120 | 0 | P1000-K03206-HA-HI-GE-RFI-000013 | P1000-K03206-HA-HI-EL-RFI-000013 for Mockup's Fire Alarm Shop drawing Requirement (3BR VIP suit mockup). | 2026-07-30 |  |  | HillInt-RFI-000898 | 2026-08-14 |  |  |  |  | open |  | Electrical | 2026-07-30
| HAC-RFI-000121 | 0 | P1000-K03206-HA-HI-GE-RFI-000014 | P1000-K03206-HA-HI-EL-RFI-000014 for Mockup's Power Shop drawing Requirement (3BR VIP suit mockup). | 2026-07-30 |  |  | HillInt-RFI-000899 | 2026-08-14 |  |  |  |  | open |  | Electrical | 2026-07-30
| HAC-RFI-000122 | 0 | P1000-K03206-HA-HI-GE-RFI-000015 | P1000-K03206-HA-HI-ST-RFI-000015 for Clarification of Structural Reinforcement Details - DP06 project–Villa Type ( A&D). | 2026-07-30 |  |  | HillInt-RFI-000876 | 2026-08-09 |  |  | HillInt-RTCL-001037 | 2026-08-14 | Response |  | Structural | 2026-07-30
| HAC-RFI-000123 | 0 | P1000-K03206-HA-HI-GE-RFI-000016 | P1000-K03206-HA-HI-ME-RFI-000016 for 3BR VIP Suite Type 1 Guest Room Mockup (drainage plan). | 2026-08-02 |  |  | HillInt-RFI-000900 | 2026-08-14 |  |  |  |  | open |  | Mechanical | 2026-08-02
| HAC-RFI-000124 | 0 | P1000-K03206-HA-HI-GE-RFI-000017 | P1000-K03206-HA-HI-ME-RFI-000017 for 3BR VIP Suite Type 1 Guest Room Mockup (fire protection systems plan) | 2026-08-02 |  |  | HillInt-RFI-000901 | 2026-08-14 |  |  |  |  | open |  | Mechanical | 2026-08-02
| HAC-RFI-000125 | 0 | P1000-K03206-HA-HI-GE-RFI-000018 | P1000-K03206-HA-HI-ME-RFI-000018 for 3BR VIP Suite Type 1 Guest Room Mockup (HVAC plan). | 2026-08-02 |  |  | HillInt-RFI-000902 | 2026-08-14 |  |  |  |  | open |  | Mechanical | 2026-08-02
| HAC-RFI-000126 | 0 | P1000-K03206-HA-HI-GE-RFI-000019 | P1000-K03206-HA-HI-ME-RFI-000019 for 3BR VIP Suite Type 1 ater supply systems plan).Guest Room Mockup (w | 2026-08-02 |  |  | HillInt-RFI-000903 | 2026-08-14 |  |  |  |  | open |  | Mechanical | 2026-08-02
| HAC-RFI-000127 | 0 | P1000-K03206-HA-HI-GE-RFI-000020 | P1000-K03206-HA-HI-AR-RFI-000020 For Conflicts Between Structural IFC and Architectural Schematic Design. | 2026-08-02 |  |  | HillInt-RFI-000877 | 9 August 2026 |  |  | HillInt-RTCL-001036 | 2026-08-14 | Response |  | Architectural | 2026-08-02
| HAC-RFI-000130 | 0 | P1000-K03206-HA-HI-GE-RFI-000021 | P1000-K03206-HA-HI-ST-RFI-000021-00 For Conflict Between Excavation IFC and Structural IFC for Villas | 2026-08-08 |  |  | HillInt-RFI-000878 | 2026-09-08 |  |  | HillInt-RTCL-001038 | 14/08/2026 | Response |  | Structural | 2026-08-08
| HAC-RFI-000131 | 0 | P1000-K03206-HA-HI-GE-RFI-000022 | P1000-K03206-HA-HI-ST-RFI-000022-00 For Missing Stair Starter Details in Villas Foundation IFC. | 2026-08-03 |  |  | HillInt-RFI-000879 | 2026-08-09 |  |  | HillInt-RTCL-001039 | 14/08/2026 | Response |  | Structural | 2026-08-03
| HAC-RFI-000132 | 0 | P1000-K03206-HA-HI-GE-RFI-000023 | P1000-K03206-HA-HI-ST-RFI-000023-00 For Conflict Between BOQ and IFC Concrete Grade | 2026-08-03 |  |  | HillInt-RFI-000880 | 2026-08-09 |  |  | HillInt-RTCL-001035 | 14/08/2026 | Response |  | Structural | 2026-08-03
| HAC-RFI-000166 | 1 | P1000-K03206-HA-HI-GE-RFI-000023 | P1000-K03206-HA-HI-ST-RFI-000023-00 For Conflict Between BOQ and IFC Concrete Grade | 2026-08-19 |  |  | HillInt-RFI-001013 | 2026-08-19 |  |  | HillInt-RTCL-001138 | 2026-08-24 | Response |  | Structural | 2026-08-19
| HAC-RFI-000133 | 0 | P1000-K03206-HA-HI-GE-RFI-000024 | P1000-K03206-HA-HI-AR-RFI-000024-00 For Hotel Room Mock-Up Selection. | 2026-08-03 | HillInt-RFI-000904 | 2026-08-12 | HillInt-RFI-000904 | 2026-08-12 |  |  |  |  | open |  | Architectural | 2026-08-03
| HAC-RFI-000134 | 0 | P1000-K03206-HA-HI-GE-RFI-000025 | P1000-K03206-HA-HI-AR-RFI-000025-00 For Missing Details for ID Build-Up Wall Types for Hotel Room Mock-Up. | 2026-08-03 | HillInt-RFI-000905 | 2026-08-12 | HillInt-RFI-000905 | 2026-08-12 |  |  |  |  | open |  | Architectural | 2026-08-03
| HAC-RFI-000135 | 0 | P1000-K03206-HA-HI-GE-RFI-000026 | P1000-K03206-HA-HI-AR-RFI-000026-00 for Conflict Between Architectural and Interior Drawings – Hotel Room Mock-Up. | 2026-08-03 | HillInt-RFI-000906 | 2026-08-12 | HillInt-RFI-000906 | 2026-08-12 |  |  |  |  | open |  | Architectural | 2026-08-03
| HAC-RFI-000136 | 0 | P1000-K03206-HA-HI-GE-RFI-000027 | P1000-K03206-HA-HI-AR-RFI-000027-00 for Missing Architectural Opening Details for Hotel Room Mock-Up. | 2026-08-03 | HillInt-RFI-000907 | 2026-08-12 | HillInt-RFI-000907 | 2026-08-12 |  |  |  |  | open |  | Architectural | 2026-08-03
| HAC-RFI-000137 | 0 | P1000-K03206-HA-HI-GE-RFI-000028 | P1000-K03206-HA-HI-ST-RFI-000028-00 for Construction sequence for DP06 project – All Villa’s. | 2026-08-03 | HillInt-RFI-000908 | 2026-08-12 | HillInt-RFI-000908 | 2026-08-12 |  |  | HillInt-RTCL-001040 | 2026-08-14 | Response |  | Structural | 2026-08-03
| HAC-RFI-000203 | 1 | P1000-K03206-HA-HI-GE-RFI-000028 | P1000-K03206-HA-HI-ST-RFI-000028-00 for Construction sequence for DP06 project – All Villa’s. | 2026-09-09 |  |  | HillInt-GNC-003454 | 2026-09-10 |  |  |  |  | open |  | Structural | 2026-09-09
| HAC-RFI-000144 | 0 | P1000-K03206-HA-HI-GE-RFI-000029 | P1000-K03206-HA-HI-AR-RFI-000029-00 for Villa Mockup Location as per site condition DP6-Villas. | 2026-08-05 | HillInt-RFI-000909 | 2026-08-12 | HillInt-RFI-000909 | 2026-08-12 |  |  |  |  | open |  | Architectural | 2026-08-05
| HAC-RFI-000155 | 0 | P1000-K03206-HA-HI-GE-RFI-000030 | P1000-K03206-HA-HI-ST-RFI-000030 for Confirmation of Lift Type and Lift Pit Dimensions & Levels. (DP06 project – All Villa’s) | 2026-08-13 |  |  | HillInt-RFI-000916 | 14 August 202 |  |  | HillInt-RTCL-001082 | 2026-08-19 | Response |  | Structural | 2026-08-13
| HAC-RFI-000156 | 0 | P1000-K03206-HA-HI-GE-RFI-000031 | P1000-K03206-HA-HI-ST-RFI-000031 for Clarification on Villa Type Discrepancy in Villas IFC Excavation Drawings. (DP06 project – All Villa’s) | 2026-08-13 |  |  | HillInt-RFI-000917 | 14 August 202 |  |  | HillInt-RTCL-001083 | 2026-08-19 | Response |  | Structural | 2026-08-13
| HAC-RFI-000160 | 0 | P1000-K03206-HA-HI-ST-RFI-000032 | P1000-K03206-HA-HI-ST-RFI-000032 for Foundation Level Conflict in IFC Foundation Package (DP06 project – All Villas) | 2026-08-13 |  |  | HillInt-RFI-000918 | 14 August 202 |  |  | HillInt-RTCL-001084 | 2026-08-19 | Response |  | Structural | 2026-08-13
| HAC-RFI-000159 | 0 | P1000-K03206-HA-HI-ST-RFI-000033 | P1000-K03206-HA-HI-ST-RFI-000033 for Foundation Level Conflict in IFC Foundation Package (DP06 project – villa type A & B) | 2026-08-13 |  |  | HillInt-RFI-000919 | 2026-08-14 |  |  | HillInt-RTCL-001085 | 2026-08-19 | Response |  | Structural | 2026-08-13
| HAC-RFI-000178 | 0 | P1000-K03206-HA-HI-ST-RFI-000034 | P1000-K03206-HA-HI-ST-RFI-000034 for Discrepancy in Levels Between the Received Excavation IFC and Foundation IFC Drawings. | 2026-08-31 |  |  | HillInt-RFI-001145 | 2026-09-01 |  |  | HillInt-GNC-003426 | 2026-09-14 | Response |  | Structural | 2026-08-31
| HAC-RFI-000179 | 0 | P1000-K03206-HA-HI-ST-RFI-000035 | P1000-K03206-HA-HI-ST-RFI-000035 for Discrepancy in Column Dimensions Between the Foundation and Superstructure IFC Packages. | 2026-08-31 |  |  | HillInt-RFI-001147 | 2026-09-01 |  |  | HillInt-RTRFI-001219 | 2026-09-14 | Response |  | Structural | 2026-08-31
| HAC-RFI-000186 | 0 | P1000-K03206-HA-HI-ST-RFI-000036 | P1000-K03206-HA-HI-ST-RFI-000036 for Identification of Walls Requiring Foundation Upstands in all villas. | 2026-09-07 |  |  | HillInt-GNC-003399 | 2026-09-10 |  |  | HAC-RFI-000186 | 2026-09-14 | Response |  | Structural | 2026-09-07
| HAC-RFI-000187 | 0 | P1000-K03206-HA-HI-ST-RFI-000037 | P1000-K03206-HA-HI-ST-RFI-000037 for B1 & B2 Reinforcement Sizes for Footing F3 – Villa D. | 2026-09-07 |  |  | HillInt-GNC-003400 | 2026-09-10 |  |  | HAC-RFI-000187 | 2026-09-14 | Response |  | Structural | 2026-09-07
| HAC-RFI-000189 | 0 | P1000-K03206-HA-HI-ST-RFI-000038 | P1000-K03206-HA-HI-ST-RFI-000038 for Missing Column Details– Villa Type B. | 2026-09-07 |  |  | HillInt-GNC-003401 | 2026-09-10 |  |  | HillInt-GNC-003401 | 2026-09-09 | Response |  | Structural | 2026-09-07
| HAC-RFI-000190 | 0 | P1000-K03206-HA-HI-ST-RFI-000039 | P1000-K03206-HA-HI-ST-RFI-000039 for Missing RC Pedestal Details – Villa Types C1, C2 & D. | 2026-09-07 |  |  | HillInt-GNC-003402 | 2026-09-10 |  |  | HillInt-GNC-003402 | 2026-09-09 | Response |  | Structural | 2026-09-07
| HAC-RFI-000191 | 0 | P1000-K03206-HA-HI-ST-RFI-000040 | P1000-K03206-HA-HI-ST-RFI-000040 for Foundation Thickness and Excavation Level Discrepancies at the Hotel building | 2026-09-07 |  |  | HillInt-GNC-003404 | 2026-09-09 |  |  | HillInt-GNC-003404 | 2026-09-09 | Response |  | Structural | 2026-09-07
| HAC-RFI-000192 | 0 | P1000-K03206-HA-HI-ST-RFI-000041 | P1000-K03206-HA-HI-ST-RFI-000041 for Basement 02 Staircase Starter Wall & Starter Bar Details – Hotel Building | 2026-09-07 |  |  | HillInt-GNC-003523 | 2026-09-13 |  |  | HillInt-GNC-003523 | 2026-09-13 | Response |  | Structural | 2026-09-07
| HAC-RFI-000235 | 1 | P1000-K03206-HA-HI-ST-RFI-000041 | P1000-K03206-HA-HI-ST-RFI-000041 for Basement 02 Staircase Starter Wall & Starter Bar Details – Hotel Building | 2026-09-27 |  |  | HillInt-GNC-004246 | 2026-09-27 |  |  | HillInt-GNC-003523 | 2026-09-27 | Response |  | Structural | 2026-09-27
| HAC-RFI-000193 | 0 | P1000-K03206-HA-HI-ST-RFI-000042 | P1000-K03206-HA-HI-ST-RFI-000042 for Missing Walls and Drawing / View Name Discrepancies in SPA Foundation IFC Package. | 2026-09-07 |  |  | HillInt-GNC-003524 | 2026-09-13 |  |  | HillInt-GNC-003524 | 2026-09-13 | Response |  | Structural | 2026-09-07
| HAC-RFI-000194 | 0 | P1000-K03206-HA-HI-ST-RFI-000043 | P1000-K03206-HA-HI-ST-RFI-000043 for Clarification on Foundation Levels and Corresponding Excavation Levels in Beach House. | 2026-09-07 |  |  | HillInt-GNC-003526 | 2026-09-13 |  |  | HillInt-GNC-003526 | 2026-09-13 | Response |  | Structural | 2026-09-07
| HAC-RFI-000197 | 0 | P1000-K03206-HA-HI-ST-RFI-000044 | P1000-K03206-HA-HI-ST-RFI-000044 for MEP Required Information for Water Tank & Pump Room. | 2026-09-09 |  |  | HillInt-GNC-003436 | 2026-09-10 |  |  | HillInt-GNC-004845 | 2026-10-06 | Response |  | Structural | 2026-09-09
| HAC-RFI-000199 | 0 | P1000-K03206-HA-HI-ST-RFI-000045 | P1000-K03206-HA-HI-ST-RFI-000045 for Connection between concrete & steel works in villas. | 2026-09-09 |  |  | HillInt-GNC-003435 | 2026-09-10 |  |  | HillInt-GNC-004035 | 2026-09-22 | Response |  | Structural | 2026-09-09
| HAC-RFI-000198 | 0 | P1000-K03206-HA-HI-ST-RFI-000046 | P1000-K03206-HA-HI-ST-RFI-000046 For Clarification on Ancillary Buildings Locations – Villas C1 & C2 | 2026-09-09 |  |  | HillInt-GNC-003437 | 2026-09-10 |  |  | HillInt-GNC-003875 | 2026-09-20 | Response |  | Structural | 2026-09-09
| HAC-RFI-000199 | 0 | P1000-K03206-HA-HI-ST-RFI-000047 | P1000-K03206-HA-HI-ST-RFI-000047 For Clarification of Retaining Wall Thickness in Beach House. | 2026-09-09 |  |  | HillInt-GNC-003439 | 2026-09-10 |  |  | HillInt-GNC-003792 | 2026-09-16 | Response |  | Structural | 2026-09-09
| HAC-RFI-000205 | 0 | P1000-K03206-HA-HI-ST-RFI-000048 | P1000-K03206-HA-HI-ST-RFI-000048 for Clarification of Final Shoreline Alignment and Water Levels – Bathymetric Study. | 2026-09-10 |  |  | HillInt-GNC-003527 | 2026-09-13 |  |  | HillInt-GNC-004069 | 2026-09-22 | Response |  | Structural | 2026-09-10
| HAC-RFI-000206 | 0 | P1000-K03206-HA-HI-ST-RFI-000049 | P1000-K03206-HA-HI-ST-RFI-000049 for Alternative Waterproofing System – Tanking System. | 2026-09-10 |  |  | HillInt-GNC-003528 | 2026-09-13 |  |  | HillInt-GNC-003796 | 2026-09-16 | Response |  | Structural | 2026-09-10
| HAC-RFI-000210 | 0 | P1000-K03206-HA-HI-ST-RFI-000050 | P1000-K03206-HA-HI-ST-RFI-000050 for Club House – Missing Details & Level Coordination for Retaining Wall. | 2026-09-12 | [6 empty] | HillInt-GNC-003812 | 2026-09-17 | Response |  | Structural | 2026-09-12
| HAC-RFI-000207 | 0 | P1000-K03206-HA-HI-ST-RFI-000051 | P1000-K03206-HA-HI-ST-RFI-000051 for Residents Club coordination with the surrounded building & walls. | 2026-09-12 |  |  | HillInt-GNC-003529 | 2026-09-19 |  |  | HillInt-GNC-004053 | 2026-09-22 | Response |  | Structural | 2026-09-12
| HAC-RFI-000208 | 0 | P1000-K03206-HA-HI-ST-RFI-000052 | P1000-K03206-HA-HI-ST-RFI-000052 for Residents Club Missing Topographic Survey documents. | 2026-09-12 | [6 empty] | HillInt-GNC-003747 | 2026-09-15 | Response |  | Structural | 2026-09-12
| HAC-RFI-000209 | 0 | P1000-K03206-HA-HI-ST-RFI-000053 | P1000-K03206-HA-HI-ST-RFI-000053 For SPA Building – Proposed Temporary Protection Wall. | 2026-09-12 | [6 empty] | HillInt-GNC-003751 | 2026-09-15 | Response |  | Structural | 2026-09-12
| HAC-RFI-000211 | 0 | P1000-K03206-HA-HI-ST-RFI-000054 | P1000-K03206-HA-HI-ST-RFI-000054 For Villa C1- SW3 Reinforcement Values Clarification. | 2026-09-12 | [6 empty] | HillInt-RTCL-001439 | 2026-09-17 | Response |  | Structural | 2026-09-12
| HAC-RFI-000212 | 0 | P1000-K03206-HA-HI-ST-RFI-000055 | P1000-K03206-HA-HI-ST-RFI-000055 For Foundation Level Difference in villas. | 2026-09-12 | [6 empty] | HillInt-GNC-003809 | 2026-09-17 | Response |  | Structural | 2026-09-12
| HAC-RFI-000213 | 0 | P1000-K03206-HA-HI-ST-RFI-000056 | P1000-K03206-HA-HI-ST-RFI-000056 For Stair Starter proposal in villas. | 2026-09-12 | [6 empty] | HillInt-GNC-003795 | 2026-09-16 | Response |  | Structural | 2026-09-12
| HAC-RFI-000214 | 0 | P1000-K03206-HA-HI-ST-RFI-000057 | P1000-K03206-HA-HI-ST-RFI-000057 for Clarification of Sump Pit RC Slab and Access Hatch Details At Hotel Building. | 2026-09-13 | [6 empty] | HillInt-GNC-003811 | 2026-09-17 | Response |  | Structural | 2026-09-13
| HAC-RFI-000214 | 1 | P1000-K03206-HA-HI-ST-RFI-000057 | Fwd: P1000-K03206-HA-HI-ST-RFI-000057-01 for Clarification of Sump Pit RC Slab and Access Hatch Details At Hotel Building. | 2026-09-27 |  |  | HillInt-GNC-004297 | 2026-09-27 |  |  | HillInt-GNC-004622 | 2026-10-04 | Response |  | Structural | 2026-09-27
| HAC-RFI-000223 | 0 | P1000-K03206-HA-HI-ST-RFI-000058 | P1000-K03206-HA-HI-ST-RFI-000058 for Villas- missing Structural levels in all Villa Types. | 2026-09-22 | HillInt-GNC-004083 | 2026-09-22 |  |  |  |  | HillInt-GNC-004215 | 2026-09-27 | Response |  | Structural | 2026-09-22
| HAC-RFI-000224 | 0 | P1000-K03206-HA-HI-ST-RFI-000059 | P1000-K03206-HA-HI-ST-RFI-000059 for villa C1 – first floor beams conflict between L01-B32 & L01-B35. | 2026-09-22 | HillInt-GNC-004084 | 2026-09-22 |  |  |  |  | HillInt-GNC-004216 | 2026-09-27 | Response |  | Structural | 2026-09-22
| HAC-RFI-000225 | 0 | P1000-K03206-HA-HI-ST-RFI-000060 | P1000-K03206-HA-HI-ST-RFI-000060 for Villa (A) Coordination Issue | 2026-09-22 | HillInt-GNC-004085 | 2026-09-22 |  |  |  |  | HillInt-GNC-004217 | 2026-09-27 | Response |  | Structural | 2026-09-22
| HAC-RFI-000226 | 0 | P1000-K03206-HA-HI-ST-RFI-000061 | P1000-K03206-HA-HI-AR-RFI-000061 for Villas- missing Stairs finishes. | 2026-09-22 | HillInt-GNC-004833 | 2026-10-06 | HillInt-GNC-004833 | 2026-10-06 |  |  |  |  | open |  | Architectural | 2026-09-22
| HAC-RFI-000230 | 0 | P1000-K03206-HA-HI-ST-RFI-000062 | P1000-K03206-HA-HI-ST-RFI-000062 for Villas-Drop panel issue in villa C1 | 2026-09-24 |  |  | HillInt-GNC-004162 | 2026-09-24 |  |  | HillInt-GNC-004201 | 2026-09-27 | Response |  | Structural | 2026-09-24
| HAC-RFI-000231 | 0 | P1000-K03206-HA-HI-ST-RFI-000063 | P1000-K03206-HA-HI-ST-RFI-000063 for Beach House - Missing Foundations and Retaining Walls in Substructure Package | 2026-09-24 | HillInt-GNC-004164 | 2026-09-24 |  |  |  |  | HillInt-GNC-004203 | 2026-09-27 | Response |  | Structural | 2026-09-24
| HAC-RFI-000232 | 0 | P1000-K03206-HA-HI-ST-RFI-000064 | P1000-K03206-HA-HI-ST-RFI-000064 for Club House - Clarification of Column Layout Discrepancies Between Superstructure and Substructure IFC Drawings. | 2026-09-24 | HillInt-GNC-004170 | 2026-09-24 |  |  |  |  | HillInt-GNC-004205 | 2026-09-27 | Response |  | Structural | 2026-09-24
| HAC-RFI-000233 | 0 | P1000-K03206-HA-HI-ST-RFI-000065 | P1000-K03206-HA-HI-ST-RFI-000065 for Club House Clarification of Foundation Levels and Corresponding Excavation Levels. | 2026-09-24 | HillInt-GNC-004174 | 2026-09-24 |  |  |  |  | HAC-RFI-000233 | 2026-09-24 | Response |  | Structural | 2026-09-24
| HAC-RFI-000277 | 1 | P1000-K03206-HA-HI-ST-RFI-000065 | REH-DP6/ Re: P1000-K03206-HA-HI-ST-RFI-000065-01 for Club House Clarification of Foundation Levels and Corresponding Excavation Levels. | 2026-10-08 |  |  | HillInt-GNC-004956 | 2026-10-09 |  |  |  |  | open
| HAC-RFI-000234 | 0 | P1000-K03206-HA-HI-ST-RFI-000066 | P1000-K03206-HA-HI-ST-RFI-000066 for Beach House - Missing Column C46 in Substructure Package | 2026-09-24 | HillInt-GNC-004175 | 2026-09-24 |  |  |  |  | HillInt-GNC-004206 | 2026-09-27 | Response |  | Structural | 2026-09-24
| HAC-RFI-000236 | 0 | P1000-K03206-HA-HI-ST-RFI-000067 | P1000-K03206-HA-HI-ST-RFI-000067 For Hotel_Step-In Level Reinforcement detail. | 2026-09-27 |  |  | HillInt-GNC-004247 | 2026-09-27 |  |  | HillInt-GNC-004383 | 2026-09-29 | Response |  | Structural | 2026-09-27
| HAC-RFI-000237 | 0 | P1000-K03206-HA-HI-ST-RFI-000068 | P1000-K03206-HA-HI-ST-RFI-000068 For HOTEL – Clarification of Isolation Joint Between Retaining Walls and Adjacent Structure | 2026-09-27 |  |  | HillInt-GNC-004249 | 2026-09-27 |  |  | HillInt-GNC-004383 | 2026-09-29 | Response |  | Structural | 2026-09-27
| HAC-RFI-000238 | 0 | P1000-K03206-HA-HI-ST-RFI-000069 | P1000-K03206-HA-HI-ST-RFI-000069 For Hotel: Missing Location and Details of Ramps Starter Walls at Basement 01. | 2026-09-27 |  |  | HillInt-GNC-004250 | 2026-09-27 |  |  | HillInt-GNC-004381 | 2026-09-29 | Response |  | Structural | 2026-09-27
| HAC-RFI-000240 | 0 | P1000-K03206-HA-HI-ST-RFI-000070 | P1000-K03206-HA-HI-ST-RFI-000070 for Hotel Clarification Required for Stair Starter Walls in basement 01 | 2026-09-27 |  |  | HillInt-GNC-004298 | 2026-09-27 |  |  | HillInt-GNC-004621 | 2026-10-04 | Response |  | Structural | 2026-09-27
| HAC-RFI-000241 | 0 | P1000-K03206-HA-HI-ST-RFI-000071 | P1000-K03206-HA-HI-ST-RFI-000071 for Villas – Missing Columns Details in Villa D. | 2026-09-27 |  |  | HillInt-GNC-004301 | 2026-09-27 |  |  | HillInt-GNC-004385 | 2026-09-29 | Response |  | Structural | 2026-09-27
| HAC-RFI-000242 | 0 | P1000-K03206-HA-HI-ST-RFI-000072 | P1000-K03206-HA-HI-ST-RFI-000072 for HOTEL – Clarification of Foundation Reinforcement Directions | 2026-09-27 |  |  | HillInt-GNC-004304 | 2026-09-27 |  |  | HillInt-GNC-004386 | 2026-09-29 | Response |  | Structural | 2026-09-27
| HAC-RFI-000243 | 0 | P1000-K03206-HA-HI-ST-RFI-000073 | P1000-K03206-HA-HI-ST-RFI-000073 for columns splice location | 2026-09-27 |  |  | HillInt-GNC-004330 | 2026-09-27 |  |  | HillInt-GNC-004376 | 2026-09-29 | Response |  | Structural | 2026-09-27
| HAC-RFI-000247 | 0 | P1000-K03206-HA-HI-ST-RFI-000074 | P1000-K03206-HA-HI-ST-RFI-000074 For VILLAS - Pump Room relocation. | 2026-10-01 |  |  | HillInt-GNC-004526 | 2026-10-01 |  |  | HillInt-GNC-004844 | 2026-10-06 | Response |  | Structural | 2026-10-01
| HAC-RFI-000249 | 0 | P1000-K03206-HA-HI-ST-RFI-000075 | P1000-K03206-HA-HI-ST-RFI-000075 for VILLAS - Reinforcement Values Discrepancy | 2026-10-04 |  |  | HillInt-GNC-004646 | 2026-10-04 |  |  | HillInt-GNC-004761 | 2026-10-05 | Response |  | Structural | 2026-10-04
| HAC-RFI-000262 | 0 | P1000-K03206-HA-HI-ST-RFI-000076 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000076 for Villa C1 Mock Up Detailed Design – Contradiction in Block Work Types and Structure Package. | 2026-10-07 |  |  | HillInt-GNC-004878 | 2026-10-07 |  |  |  |  | open |  | Architectural | 2026-10-07
| HAC-RFI-000263 | 0 | P1000-K03206-HA-HI-ST-RFI-000077 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000077 for Villa Mock-Up –Confirmation of 100% DD Package as Reference | 2026-10-08 |  |  | HillInt-GNC-004968 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000264 | 0 | P1000-K03206-HA-HI-ST-RFI-000078 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000078 for Villa C1 Mock-Up – Proposed Location Change from C1-38 to C1-31 | 2026-10-08 |  |  | HillInt-GNC-004969 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000265 | 0 | P1000-K03206-HA-HI-ST-RFI-000079 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000079 for DP6 – Confirmation of Low-Iron Glass Omission for all buildings | 2026-10-08 |  |  | HillInt-GNC-004970 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000266 | 0 | P1000-K03206-HA-HI-ST-RFI-000080 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000080 for Villas– Confirmation of External Wall System | 2026-10-08 |  |  | HillInt-GNC-004971 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000267 | 0 | P1000-K03206-HA-HI-ST-RFI-000081 | REH-DP6/ P1000-K03206-HA-HI-ST-RFI-000081 for VILLAs - Clarification on Top Reinforcement of Stair Flights. | 2026-10-08 |  |  | HillInt-GNC-004957 | 2026-10-09 |  |  |  |  | open |  | Other
| HAC-RFI-000268 | 0 | P1000-K03206-HA-HI-ST-RFI-000082 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000082 for VILLAS - RFI – Soil Replacement for Villas on Fill < 5.0 m. | 2026-10-08 |  |  | HillInt-GNC-004972 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000269 | 0 | P1000-K03206-HA-HI-ST-RFI-000083 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000083 for Villas-Confirmation of using local porcelain instead of ballas in villas roof | 2026-10-08 |  |  | HillInt-GNC-004973 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000270 | 0 | P1000-K03206-HA-HI-ST-RFI-000084 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000084 for Villas Mockup – Confirmation of Mirror Detail. | 2026-10-08 |  |  | HillInt-GNC-004974 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000271 | 0 | P1000-K03206-HA-HI-ST-RFI-000085 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000085 for Villas–Aluminum Profile Minimum Thickness required. | 2026-10-08 |  |  | HillInt-GNC-004976 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000272 | 0 | P1000-K03206-HA-HI-ST-RFI-000086 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000086 for Villas – Confirmation of Aluminum Thermal Break System Omission. | 2026-10-08 |  |  | HillInt-GNC-004977 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000273 | 0 | P1000-K03206-HA-HI-ST-RFI-000087 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000087 for Villas – Confirmation of External ِ Aluminium cladding Fire-Rated Requirements Omission. | 2026-10-08 |  |  | HillInt-GNC-004978 | 2026-10-11 |  |  |  |  | open |  | Other
| HAC-RFI-000276 | 0 | P1000-K03206-HA-HI-ST-RFI-000088 | REH-DP6/ P1000-K03206-HA-HI-ST-RFI-000088 for Villas – Foundation thickness in Villa D. | 2026-10-08 |  |  | HillInt-GNC-004959 | 2026-10-09 |  |  |  |  | open |  | Other
| HAC-RFI-000275 | 0 | P1000-K03206-HA-HI-ST-RFI-000089 | REH-DP6/ P1000-K03206-HA-HI-ST-RFI-000089 for Residents club Retaining walls levels confirmation | 2026-10-08 |  |  | HillInt-GNC-004958 | 2026-10-09 |  |  |  |  | open |  | Other
| HAC-RFI-000278 | 0 | P1000-K03206-HA-HI-ST-RFI-000090 | REH-DP6/ P1000-K03206-HA-HI-AR-RFI-000090 for Villa C1 Mock Up– Contradiction Between Aluminum Doors Elevation and Schedule. | 2026-10-08 |  |  | HillInt-GNC-004979 | 2026-10-11 |  |  |  |  | open |  | Other
Formulas:
RFI Date (Auto) = IF([Date]="","",IFERROR(IF(ISNUMBER([Date]),[Date],DATEVALUE([Date])),""))