## RO
Request For Information Log form West Canal Project |  |  | Package No : (3045) Design and Build with option to operate for Potable Water RO Plant in REH | [5 empty] | ALL | 19
[9 empty] | Response | 12
HAC TO HILL | [6 empty] | Hill to HAC |  | Open | 4
Mail No | RFI No | Rev. | Discipline | Mail No | Subject | Date | Mail No | Date
CCCEGY-RFI-000001 | REH-SW00-UIR-ME-OTC-ZZZZ-RFI-000001 | 00 | Mechanical | OTC-JV-RFI-000003 | Confirmation on water delivery point and product water pumps outlet pressure | 2026-06-15 | HillInt-RTRFI-000867 | 2026-07-28 | Response
| REH-SW00-UIR-ME-OTC-ZZZZ-RFI-000001 | 01 | Mechanical | OTC-JV-RFI-000008 | Confirmation on water delivery point and product water pumps outlet pressure | 2026-08-09 | HillInt-GNC-003847 | 2026-09-17 | Response
| REH-SW00-UIR-ME-OTC-ZZZZ-RFI-000001 | 02 | Mechanical | OTC-JV-RFI-000016 | Confirmation on water delivery point and product water pumps outlet pressure | 2026-09-25 |  |  | Open
| REH-SW00-UIR-EL-OTC-ZZZZ-RFI-000001 | 00 | Electrical | OTC-JV-RFI-000002 | Information required for designing the connection to the electrical substation | 2026-06-15 | HillInt-RTRFI-001042 | 2026-08-19 | Response
| REH-SW00-UIR-EL-OTC-ZZZZ-RFI-000001 | 01 | Electrical | OTC-JV-RFI-000014 | Information required for designing the connection to the electrical substation | 2026-09-07 | HillInt-GNC-003754 | 2026-09-15 | Response
| REH-SW00-UIR-EL-OTC-ZZZZ-RFI-000001 | 02 | Electrical | OTC-JV-RFI-000015 | Information required for designing the connection to the electrical substation | 2026-09-25 | HillInt-GNC-004300 | 2026-09-28 | Response
| REH-SW00-UIR-EL-OTC-ZZZZ-RFI-000001 | 03 | Electrical | OTC-JV-RFI-000018 | Information required for designing the connection to the electrical substation | 2026-10-11 |  |  | Open
CCCEGY-RFI-000002 | REH-SW00-UIR-ZZ-OTC-ZZZZ-RFI-000001 | 00 | All Disciplines | OTC-JV-RFI-000004 | Information required for designing the connection to the electrical substation | 2026-06-23 | HillInt-RTRFI-000877 | 2026-07-28 | Response
CCCEGY-RFI-000003 | REH-SW00-UIR-ZZ-OTC-ZZZZ-RFI-000002 | 00 | All Disciplines | OTC-JV-RFI-000005 | Clarification of Approved 4D Simulation Software | 2026-06-28 | HillInt-RTRFI-000686 | 2026-07-05 | Response
CCCEGY-RFI-000004 | REH-SW00-UIR-ZZ-OTC-ZZZZ-RFI-000003 | 00 | All Disciplines | OTC-JV-RFI-000006 | Clarification on CDE Workflow & Information Production Environment | 2026-06-28 | HillInt-RTRFI-000688 | 2026-07-05 | Response
| REH-SW00-UIR-ZZ-OTC-ZZZZ-RFI-000001 | 00 | All Disciplines | OTC-JV-RFI-000007 | 3D Modelling Platform and Deliverables for Process Scope | 2026-08-07 | HillInt-RTRFI-000884 | 2026-07-28 | Response
| REH-SW00-UIR-EL-OTC-ZZZZ-RFI-000002 | 00 | Electrical | OTC-JV-RFI-000009 | Main Control Room Location | 2026-08-12 | HillInt-RTRFI-001028 | 2026-08-17 | Response
| REH-SW00-UIR-ZZ-OTC-ZZZZ-RFI-000004 | 00 | All Disciplines | OTC-JV-RFI-000011 | Clarification on BIMDeX Workflow, Deliverables and ACC Collaboration Requirements | 2026-08-16 | HillInt-RTRFI-001070 | 2026-08-20 | Response
CCCEGY-RFI-000005 | REH-SW00-UIR-ZZ-OTC-ZZZZ-RFI-000005 | 00 | All Disciplines | HillInt-GNC-003467 | GIS-BIM Standard Applicability, Data Model & As-Built Deliverables | 2026-09-03 |  |  | Open
| REH-SW00-UIR-EL-OTC-ZZZZ-RFI-000003 | 00 | All Disciplines | OTC-JV-RFI-000013 | External Interface connection Modon with the DCS | 2026-09-05 |  | 2026-10-05 | Response
CCCEGY-RFI-000006 | REH-SW00-UIR-ST-OTC-ZZZZ-RFI-000001 | 00 | Structural | OTC-JV-RFI-000017 | Clarification of Plant Stormwater Disposal Connection and Access Road Levels | 2026-10-01 |  |  | Open
CCCEGY-RFI-000007
CCCEGY-RFI-000008
CCCEGY-RFI-000009
CCCEGY-RFI-000010
CCCEGY-RFI-000011
CCCEGY-RFI-000057
CCCEGY-RFI-000012
CCCEGY-RFI-000055
CCCEGY-RFI-000013
CCCEGY-RFI-000014
CCCEGY-RFI-000015
CCCEGY-RFI-000067
CCCEGY-RFI-000016
CCCEGY-RFI-000017
CCCEGY-RFI-000018
CCCEGY-RFI-000019
CCCEGY-RFI-000020
CCCEGY-RFI-000068
CCCEGY-RFI-000021
CCCEGY-RFI-000022
CCCEGY-RFI-000023
CCCEGY-RFI-000024
CCCEGY-RFI-000025
CCCEGY-RFI-000026
CCCEGY-RFI-000027
CCCEGY-RFI-000028
CCCEGY-RFI-000029
CCCEGY-RFI-000030
CCCEGY-RFI-000069
CCCEGY-RFI-000031
CCCEGY-RFI-000032
CCCEGY-RFI-000033
CCCEGY-RFI-000038
CCCEGY-RFI-000034
CCCEGY-RFI-000037
CCCEGY-RFI-000035
CCCEGY-RFI-000036
CCCEGY-RFI-000039
CCCEGY-RFI-000040
CCCEGY-RFI-000041
CCCEGY-RFI-000042
CCCEGY-RFI-000043
CCCEGY-RFI-000044
CCCEGY-RFI-000045
CCCEGY-RFI-000046
CCCEGY-RFI-000047
CCCEGY-RFI-000048
CCCEGY-RFI-000049
CCCEGY-RFI-000050
CCCEGY-RFI-000051
CCCEGY-RFI-000052
CCCEGY-RFI-000053
CCCEGY-RFI-000054
CCCEGY-RFI-000056
CCCEGY-RFI-000058
CCCEGY-RFI-000059
CCCEGY-RFI-000060
CCCEGY-RFI-000061
CCCEGY-RFI-000062
CCCEGY-RFI-000063
CCCEGY-RFI-000064
CCCEGY-RFI-000065
CCCEGY-RFI-000066
CCCEGY-RFI-000070
CCCEGY-RFI-000071
CCCEGY-RFI-000072
CCCEGY-RFI-000073
CCCEGY-RFI-000074
CCCEGY-RFI-000075
CCCEGY-RFI-000076
CCCEGY-RFI-000077
CCCEGY-RFI-000078
CCCEGY-RFI-000079
CCCEGY-RFI-000080
CCCEGY-RFI-000081
CCCEGY-RFI-000082
CCCEGY-RFI-000098
CCCEGY-RFI-000099
CCCEGY-RFI-000100
CCCEGY-RFI-000101
CCCEGY-RFI-000083
CCCEGY-RFI-000084
CCCEGY-RFI-000085
CCCEGY-RFI-000086
CCCEGY-RFI-000087
CCCEGY-RFI-000088
CCCEGY-RFI-000089
CCCEGY-RFI-000090
CCCEGY-RFI-000091
CCCEGY-RFI-000092
CCCEGY-RFI-000093
CCCEGY-RFI-000094
CCCEGY-RFI-000095
CCCEGY-RFI-000096
CCCEGY-RFI-000097