## STP
Request For Information Log form West Canal Project |  |  |  |  | REH08253046 Design & Build (with option to operate) Sewage Treatment Plant for REH |  |  |  | ALL | 14
[9 empty] | Response | 11
HAC TO HILL | [6 empty] | Hill to HAC |  | Open | 0
Mail No | RFI No | Rev. | Discipline | Mail No | Subject | Date | Mail No | Date
CCCEGY-RFI-000001 | P5576-K03046-HA-HI-ME-RFI-000001 | 00 | ME | HAC-RFI-000038 | Request for Utility Connection Details for Future Phases of Sewage Treatment Plant (STP 3-1) | 2026-05-19 | HillInt-RTRFI-000689 | 2026-07-05 | Response
| P5576-K03046-HA-HI-EL-RFI-000002 | 00 | EL | HAC-RFI-000039 | Request for Electrical Design Information of Sewage Treatment Plant (STP 3-1) | 2026-05-19 | HillInt-RTRFI-000538 | 2026-06-11 | Response
CCCEGY-RFI-000002 | P5576-K03046-HA-HI-RW-RFI-000003 | 00 | RW | HAC-RFI-000040 | Request for Updated Master Plan | 2026-05-19 | HillInt-RTRFI-000522 | 2026-09-06 | Response
CCCEGY-RFI-000003 | P5576-K03046-HA-HI-GE-RFI-000004 | 00 | GE | HAC-RFI-000091 | Request for Aconex Coding System (Discipline Codes & Plot Codes) for STP 3-1. | 2026-07-07 | HillInt-RTRFI-001014 | 2026-08-16 | Response
CCCEGY-RFI-000004 | P5576-K03046-HA-HI-GE-RFI-000005 | 00 | GE | HAC-RFI-000092 | Request for Bim Process Software for STP 3-1 | 2026-07-07 | HillInt-RTRFI-000943 | 2026-08-04 | Response
| P5576-K03046-HA-HI-ME-RFI-000006 | 00 | ME | HAC-RFI-000112 | Confirmation of the elevation and the design flow rate of The Treated Sewage Effluent Pump for STP3-1 | 2026-07-29 | HillInt-GNC-003201 | 2026-09-07 | Response
| P5576-K03046-HA-HI-ME-RFI-000007 | 00 | ME | HAC-RFI-000113 | Provision of Water Supply Connection for Fire, Service & Potable Water Tanks for STP3-1 | 2026-07-29 | HillInt-RTRFI-000985 | 2026-08-11 | Response
| P5576-K03046-HA-HI-ME-RFI-000008 | 00 | ME | HAC-RFI-000195 | Tie-in of STP 3-1 Sewage and Stormwater Networks | 2026-09-08 | HillInt-GNC-004112 | 2026-09-23 | Response
CCCEGY-RFI-000005 | P5576-K03046-HA-HI-AR-RFI-000009 | 00 | AR | HAC-RFI-000200 | Green Belt Location | 2026-09-09 | HillInt-GNC-003597 | 2026-09-14 | Response
| P5576-K03046-HA-HI-AR-RFI-000010 | 00 | AR | HAC-RFI-000201 | Proposed Architectural Finishing for Process Tanks | 2026-09-09 | HillInt-GNC-003601 | 2026-09-14 | Response
CCCEGY-RFI-000006 | P5576-K03046-HA-HI-GE-RFI-000011 | 00 | GE | HAC-RFI-000218 | for Design Deliverables List and Permits under Milestone 1 | 2026-09-17 | HillInt-GNC-004573 |  | Response
CCCEGY-RFI-000007
CCCEGY-RFI-000008
CCCEGY-RFI-000009
CCCEGY-RFI-000010
CCCEGY-RFI-000011
CCCEGY-RFI-000057
CCCEGY-RFI-000012
CCCEGY-RFI-000055
CCCEGY-RFI-000013
CCCEGY-RFI-000014
CCCEGY-RFI-000015
CCCEGY-RFI-000067
CCCEGY-RFI-000016
CCCEGY-RFI-000017
CCCEGY-RFI-000018
CCCEGY-RFI-000019
CCCEGY-RFI-000020
CCCEGY-RFI-000068
CCCEGY-RFI-000021
CCCEGY-RFI-000022
CCCEGY-RFI-000023
CCCEGY-RFI-000024
CCCEGY-RFI-000025
CCCEGY-RFI-000026
CCCEGY-RFI-000027
CCCEGY-RFI-000028
CCCEGY-RFI-000029
CCCEGY-RFI-000030
CCCEGY-RFI-000069
CCCEGY-RFI-000031
CCCEGY-RFI-000032
CCCEGY-RFI-000033
CCCEGY-RFI-000038
CCCEGY-RFI-000034
CCCEGY-RFI-000037
CCCEGY-RFI-000035
CCCEGY-RFI-000036
CCCEGY-RFI-000039
CCCEGY-RFI-000040
CCCEGY-RFI-000041
CCCEGY-RFI-000042
CCCEGY-RFI-000043
CCCEGY-RFI-000044
CCCEGY-RFI-000045
CCCEGY-RFI-000046
CCCEGY-RFI-000047
CCCEGY-RFI-000048
CCCEGY-RFI-000049
CCCEGY-RFI-000050
CCCEGY-RFI-000051
CCCEGY-RFI-000052
CCCEGY-RFI-000053
CCCEGY-RFI-000054
CCCEGY-RFI-000056
CCCEGY-RFI-000058
CCCEGY-RFI-000059
CCCEGY-RFI-000060
CCCEGY-RFI-000061
CCCEGY-RFI-000062
CCCEGY-RFI-000063
CCCEGY-RFI-000064
CCCEGY-RFI-000065
CCCEGY-RFI-000066
CCCEGY-RFI-000070
CCCEGY-RFI-000071
CCCEGY-RFI-000072
CCCEGY-RFI-000073
CCCEGY-RFI-000074
CCCEGY-RFI-000075
CCCEGY-RFI-000076
CCCEGY-RFI-000077
CCCEGY-RFI-000078
CCCEGY-RFI-000079
CCCEGY-RFI-000080
CCCEGY-RFI-000081
CCCEGY-RFI-000082
CCCEGY-RFI-000098
CCCEGY-RFI-000099
CCCEGY-RFI-000100
CCCEGY-RFI-000101
CCCEGY-RFI-000083
CCCEGY-RFI-000084
CCCEGY-RFI-000085
CCCEGY-RFI-000086
CCCEGY-RFI-000087
CCCEGY-RFI-000088
CCCEGY-RFI-000089
CCCEGY-RFI-000090
CCCEGY-RFI-000091
CCCEGY-RFI-000092
CCCEGY-RFI-000093
CCCEGY-RFI-000094
CCCEGY-RFI-000095
CCCEGY-RFI-000096
CCCEGY-RFI-000097