## dp03-West
Request For Information Log form DP03-West Project | [15 empty] | 2 | ALL | 144
[17 empty] | Response | 127
Consolidated Contractors Group S.A.L. (Offshore) (CCC) TO HILL | [6 empty] | Hill to ECG (DAR) |  |  | ECG to DAR | ECG (DAR) to hill |  |  | hill TO Consolidated Contractors Group S.A.L. (Offshore) (CCC) |  |  | Open | 14
Mail No | RFI No | Rev. | Mail No | Subject | Discipline | Date | Mail No | Date |  | action | Mail No | Date | Action By | Mail No | Date
CCCEGY-RFI-000001 | REH-08-26- K03271-CRJ-RFI-000001-00 | 0 | CCCEGY-RFI-000259 | Clarification for the 20 cm Replacement Soil Under Foundation | STR | 2026-06-18 | HillInt-RFI-000486 | 2026-06-21 | 3 |  | Darr-RTRFI-000004 | 2026-06-24 | Dar | HillInt-RTRFI-000607 | 2026-06-24 | 0 | Response
| REH-08-26- K03271-CRJ-RFI-000002-00 | 0 | CCCEGY-RFI-000258 | Clarification for the multi-faith area- location on general layout | STR | 2026-06-18 | HillInt-RFI-000485 | 2026-06-21 | 3 |  | Darr-RTRFI-000005 | 2026-06-24 | Dar | HillInt-RTRFI-000606 | 2026-06-24 | 0 | Response
| REH-08-26- K03271-CRJ-RFI-00003-00 | 0 | CCCEGY-RFI-000267 | Inquiry Regarding Clouded Areas and Specified "Hold" Markings | STR | 2026-06-24 | HillInt-RFI-000515 | 2026-06-24 | 34 |  | Darr-RTRFI-000060 | 2026-07-28 | Dar | HillInt-RTRFI-000888 | 2026-07-28 | 0 | Response | reminder : HillInt-GNC-001615
| REH-08-26- K03271-CRJ-RFI-00004-00 | 0 | CCCEGY-RFI-000286 | Inquiry Regarding Substructure waterproofing material | STR | 2026-06-27 | HillInt-RFI-000548 | 2026-06-28 | 1 |  | Darr-RTRFI-000009 | 2026-06-29 | Dar | HillInt-RTRFI-000640 | 2026-06-29 | 0 | Response
| REH-08-26- K03271-CRJ-RFI-00005-00 | 0 | CCCEGY-RFI-000287 | Inquiry Regarding substructure (Buried elements) concrete cover | STR | 2026-06-27 | HillInt-RFI-000549 | 2026-06-28 | 0 |  | Darr-RTRFI-000008 | 2026-06-28 | Dar | HillInt-RTRFI-000641 | 2026-06-29 | 0 | Response
| REH-08-26- K03271-CRJ-RFI-00006-00 | 0 | CCCEGY-RFI-000288 | Clarification Request related to Excavation Levels & Drawing Titles | STR | 2026-06-27 | HillInt-RFI-000550 | 2026-06-28 | 14 |  | Darr-RTRFI-000020 | 2026-07-12 | Dar | HillInt-RTRFI-000767 | 2026-07-12 | 0 | Response | reminder :HillInt-GNC-001616
| REH-08-26- K03271-CRJ-RFI-00007-00 | 0 | CCCEGY-RFI-000289 | Clarification Request related to Fence Foundation Details | STR | 2026-06-27 | HillInt-RFI-000551 | 2026-06-28 | 0 |  | Darr-RTRFI-000006 | 2026-06-28 | Dar | HillInt-RTRFI-000643 | 2026-06-29 | 0 | Response
| REH-08-26- K03271-CRJ-RFI-000008 | 0 | CCCEGY-RFI-000291 | REH-08-26-K03271-CRJ-RFI-000008 ,Technical Inquiry – Missing Unit Classification for Townhouse IFC Drawings [DD4 Package] | STR | 2026-06-29 | HillInt-RFI-000563 | 2026-06-29 | 9 |  | Darr-RTRFI-000012 | 2026-07-08 | Dar | HillInt-RTRFI-000737 | 2026-07-08 | 0 | Response | reminder :HillInt-GNC-001644
| REH-08-26- K03271-CRJ-RFI-000009 | 0 | CCCEGY-RFI-000299 | REH-08-26- K03271-CRJ-RFI-000009 - Received Corrupted Files in DD4 Package - Transmittal HILLint-GNC-1444 | STR | 2026-06-29 | HillInt-RFI-000581 | 2026-06-30 | 19 |  | Darr-RTRFI-000035 | 2026-07-19 | Dar | HillInt-RTRFI-000825 | 2026-07-19 | 0 | Response | reminder : HillInt-GNC-001645
| REH-08-26- K03271-CRJ-RFI-000010 | 0 | CCCEGY-RFI-000300 | REH-08-26- K03271-CRJ-RFI-000010 Technical inquiry – Discrepancies between Core Details Drawings vs. Columns & Axes Layout Plans | STR | 2026-06-29 | HillInt-RFI-000582 | 2026-06-30 | 9 |  | Darr-RTRFI-000017 | 2026-07-09 | Dar | HillInt-RTRFI-000747 | 2026-07-09 | 0 | Response | reminder : HillInt-GNC-001646
| REH-08-26- K03271-CRJ-RFI-000011 | 0 | CCCEGY-RFI-000301 | REH-08-26- K03271-CRJ-RFI-000011 Clarification Request: Additional Raft Footing Reinforcement (Cloud 01) | STR | 2026-06-29 | HillInt-RFI-000583 | 2026-06-30 | 9 |  | Darr-RTRFI-000016 | 2026-07-09 | Dar | HillInt-RTRFI-000746 | 2026-07-09 | 0 | Response | reminder : HillInt-GNC-001647
| REH-08-26- K03271-CRJ-RFI-000012 | 0 | CCCEGY-RFI-000302 | REH-08-26- K03271-CRJ-RFI-000012 Clarification Request: Stair Starter beam Width Dimension (4-Plex & 6-Plex) | STR | 2026-06-29 | HillInt-RFI-000584 | 2026-06-30 | 15 |  | Darr-RTRFI-000026 | 2026-07-15 | Dar | HillInt-RTRFI-000801 | 2026-07-15 | 0 | Response | reminder : HillInt-GNC-001648
| REH.08.26.3271-CRJ-RFI-STR -000013 | 0 | CCCEGY-RFI-000303 | REH.08.26.3271-CRJ-RFI-STR -000013 ,Clarification Request: Some Missing Column Setting-Out Dimensions | STR | 2026-06-30 | HillInt-RFI-000601 | 2026-06-30 | 9 |  | Darr-RTRFI-000014 | 2026-07-09 | Dar | HillInt-RTRFI-000743 | 2026-07-09 | 0 | Response | reminder :HillInt-GNC-001650
| REH.08.26.3271-CRJ-RFI-STR -000014 | 0 | CCCEGY-RFI-000322 | REH.08.26.3271-CRJ-RFI-STR -000014 ,Clarification Request: Core 2 - Discrepancies in Concentration Zone Reinforcement | STR | 2026-07-02 | HillInt-RFI-000619 | 2026-07-02 | 7 |  | Darr-RTRFI-000013 | 2026-07-09 | Dar | HillInt-RTRFI-000744 | 2026-07-09 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000015-00 | 0 | CCCEGY-RFI-000328 | REH.08.26.K03271-CRJ-RFI-AR-000015-00, Clarification Request: Drawing Levels & Mockup Building (WW-23) | Architectural | 2026-07-05 | HillInt-RFI-000638 | 2026-07-05 | 14 |  | Darr-RTRFI-000034 | 2026-07-19 | Dar | HillInt-RTRFI-000824 | 2026-07-19 | 0 | Response | reminder : HillInt-GNC-001832
| REH.08.26.3271-CRJ-RFI-ST-000016 | 0 | CCCEGY-RFI-000342 | REH.08.26.3271-CRJ-RFI-ST-000016, Discrepancies in Column Dimensions and Locations Between Architectural and Structural IFC Drawings (6-plex) | STR | 2026-07-12 | HillInt-RFI-000711 | 2026-07-12 | 3 |  | Darr-RTRFI-000029 | 2026-07-15 | Dar | HillInt-RTRFI-000805 | 2026-07-29 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000017-00 | 0 | CCCEGY-RFI-000340 | REH.08.26.3271-CRJ-RFI-ST-000017, Clarification Request: Discrepancies Between Architectural and Structural IFC Drawings for Columns (4-plex) | STR | 2026-07-11 | HillInt-RFI-000700 | 2026-07-11 | 4 |  | Darr-RTRFI-000027 | 2026-07-15 | Dar | HillInt-RTRFI-000802 | 2026-07-15 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ST-000018-00 | 0 | CCCEGY-RFI-000341 | REH.08-26.3271-CRJ-RFI-ST-000018,Clarification Request: Impervious material | STR | 2026-07-11 | HillInt-RFI-000703 | 2026-07-11 | 4 |  | Darr-RTRFI-000025 | 2026-07-15 | Dar | HillInt-RTRFI-000797 | 2026-07-15 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ST-000019-00 | 0 | CCCEGY-RFI-000349 | REH.08-26.3271-CRJ-RFI-ST-000019, Discrepancies in wet areas recessed slab and boundaries at first floor (4-plex) | STR | 2026-07-17 | HillInt-RFI-000739 | 2026-07-19 | 9 |  | Darr-RTRFI-000058 | 2026-07-28 | Dar | HillInt-RTRFI-000887 | 2026-07-28 | 0 | Response
| REH.08-26.3271-CRJ-RFI-AR-000020-00 | 0 | CCCEGY-RFI-000350 | REH.08-26.3271-CRJ-RFI-AR-000020, Clarification on Block Work Material Type for External Masonry Walls (W1) | Architectural | 2026-07-17 | HillInt-RFI-000740 | 2026-07-19 | 8 |  | Darr-RTRFI-000042 | 2026-07-27 | Dar | HillInt-RTRFI-000858 | 2026-07-27 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ME-000021-00 | 0 | CCCEGY-RFI-000351 | REH.08-26.3271-CRJ-RFI-ME-000021, Clarification Request related to Excavation Levels & Drawing Titles | MEC | 2026-07-18 | HillInt-RFI-000741 | 2026-07-19 | 14 |  | Darr-RTRFI-000074 | 2026-08-02 | Dar | HillInt-RTRFI-000907 | 2026-08-02 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ME-000021-01 | 1 | CCCEGY-RFI-000403 | Re: REH.08-26.3271-CRJ-RFI-ME-000021-01, Clarification Request related to Excavation Levels & Drawing Titles | MEC | 2026-08-05 | HillInt-RFI-000833 | 2026-08-05 | 12 |  | Darr-RTRFI-000103 | 2026-08-17 | Dar | HillInt-RTRFI-001026 | 2026-08-17 | 0 | Response
| REH.08.26.3271-CRJ-RFI-000022-00 | 0 | CCCEGY-RFI-000352 | REH.08.26.3271-CRJ-RFI-000022, Clarification on Missing Specification Section 016000 (Product Requirements) | All Disciplines | 2026-07-18 | HillInt-RFI-000742 | 2026-07-19 | 9 |  | Darr-RTRFI-000062 | 2026-07-28 | Dar | HillInt-RTRFI-000906 | 2026-08-02 | 0 | Response | closed by ENG . Asmaa Abdellahy
| REH.08.26.3271-CRJ-RFI-EL-000023-00 | 0 | CCCEGY-RFI-000353 | REH.08.26.3271-CRJ-RFI-EL-000023, Discrepancy Between IFC Drawings and BOQ regarding Light Current Routing Method | ELEC | 2026-07-18 | HillInt-RFI-000743 | 2026-07-19 | 9 |  | Darr-RTRFI-000044 | 2026-07-28 | Dar | HillInt-RTRFI-000874 | 2026-07-28 | 0 | Response | reminder : HillInt-GNC-002125
| REH.08.26.3271-CRJ-RFI-ST-000024-00 | 0 | CCCEGY-RFI-000334 | REH.08.26.3271-CRJ-RFI-ST-000024, Clarification Request: Underground masonry works | STR | 2026-07-07 | HillInt-RFI-000667 | 2026-07-07 | 8 |  | Darr-RTRFI-000021 | 2026-07-15 | Dar | HillInt-RTRFI-000800 | 2026-07-15 | 0 | Response | reminder : HillInt-GNC-001831
| REH.08.26.3271-CRJ-RFI-ST-000025 | 0 | CCCEGY-RFI-000375 | REH.08.26.3271-CRJ-RFI-ST-000025, Clarification of Fence vs. Retaining Wall Foundations and Request for Master Plan | STR | 2026-07-21 | HillInt-RFI-000769 | 2026-07-21 | 8 |  | Darr-RTRFI-000072 | 2026-07-29 | Dar | HillInt-RTRFI-000899 | 2026-07-29 | 0 | Response | reminder : HillInt-GNC-002126
| REH.08.26.3271-CRJ-RFI-ST-000025 | 1 | CCCEGY-RFI-000404 | Re: REH.08.26.3271-CRJ-RFI-ST-000025-01, Clarification of Fence vs. Retaining Wall Foundations and Request for Master Plan | STR | 2026-08-05 | HillInt-RFI-000834 | 2026-08-05 | 5 |  | Darr-RTRFI-000084 | 2026-08-10 | Dar | HillInt-RTRFI-000973 | 2026-08-10 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000025 | 2 | CCCEGY-RFI-000464 | Re: REH.08.26.3271-CRJ-RFI-ST-000025-02, Clarification Required (Fence / Retaining Wall Foundation) | STR | 2026-08-17 | HillInt-RFI-000957 | 2026-08-17 | 16 |  | Darr-RTRFI-000168 | 2026-09-02 | Dar | HillInt-RTRFI-001229 | 2026-09-02 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000026 | 0 | CCCEGY-RFI-000377 | REH.08.26.3271-CRJ-RFI-ST-000026,Discrepancy in Slab on Grade (SOG) Thickness and Proposed Revised Section | STR | 2026-07-23 | HillInt-RTRFI-000851 | 2026-07-23 | 5 |  | Darr-RTRFI-000052 | 2026-07-28 | Dar | HillInt-RTRFI-000876 | 2026-07-28 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000027 | 0 | CCCEGY-RFI-000385 | REH.08.26.3271-CRJ-RFI-ST-000027,Revit Models Queries | STR | 2026-07-25 | HillInt-RFI-000780 | 2026-07-26 | 2 |  | Darr-RTRFI-000051 | 2026-07-28 | Dar | HillInt-RTRFI-000875 | 2026-07-28 | 0 | Response
| REH.08.26.3271-CRJ-RFI-EL-000028 | 0 | CCCEGY-RFI-000386 | REH.08.26.3271-CRJ-RFI-EL-000028,Discrepancy between ID drawing and Electrical lighting layouts | ELEC | 2026-07-25 | HillInt-RFI-000781 | 2026-07-26 | 2 |  | Darr-RTRFI-000057 | 2026-07-28 | Dar | HillInt-RTRFI-000886 | 2026-07-28 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000029 | 0 | CCCEGY-RFI-000387 | REH.08.26.3271-CRJ-RFI-ME-000029, HVAC Duct Clearance & Ceiling Void Coordination Conflict | MEC | 2026-07-25 | HillInt-RFI-000782 | 2026-07-26 | 3 |  | Darr-RTRFI-000070 | 2026-07-29 | Dar | HillInt-RTRFI-000901 | 2026-07-30 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000030 | 0 | CCCEGY-RFI-000389 | REH.08.26.3271-CRJ-RFI-ME-000030, Contradiction in the type of water closet | MEC | 2026-07-27 | HillInt-RFI-000798 | 2026-07-27 | 2 |  | Darr-RTRFI-000069 | 2026-07-29 | Dar | HillInt-RTRFI-000896 | 2026-07-29 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000030-01 | 1 | CCCEGY-RFI-000405 | Re: REH.08.26.3271-CRJ-RFI-ME-000030-01, Contradiction in the type of water closet | MEC | 2026-08-05 | HillInt-RFI-000835 | 2026-08-05 | 4 |  | Darr-RTRFI-000082 | 2026-08-09 | Dar | HillInt-RTRFI-000971 | 2026-08-09 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000031 | 0 | CCCEGY-RFI-000390 | REH.08.26.3271-CRJ-RFI-ME-000031, Type of Floor drain inside wet areas | MEC | 2026-07-28 | HillInt-RFI-000801 | 2026-07-28 | 0 |  | Darr-RTRFI-000061 | 2026-07-28 | Dar | HillInt-RTRFI-000889 | 2026-07-28 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000032 | 0 | CCCEGY-RFI-000394 | REH.08.26.3271-CRJ-RFI-ME-000032, Insufficient space to run the drainage pipes at the First floor | MEC | 2026-07-29 | HillInt-RFI-000806 | 2026-07-29 | 0 |  | Darr-RTRFI-000071 | 2026-07-29 | Dar | HillInt-RTRFI-000898 | 2026-07-29 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000033 | 0 | CCCEGY-RFI-000402 | REH.08.26.3271-CRJ-RFI-AR-000033, 4 Plex – Flat – First Floor – Shafts discrepancy between Architecture & Structure | Architectural | 2026-08-03 | HillInt-RFI-000826 | 2026-08-03 | 3 |  | Darr-RTRFI-000080 | 2026-08-06 | Dar | HillInt-RTRFI-000955 | 2026-08-06 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000033 | 1 | CCCEGY-RFI-000435 | Re: REH.08.26.3271-CRJ-RFI-AR-000033-01, 4 Plex – Flat – First Floor – Shafts discrepancy between Architecture & Structure | Architectural | 2026-08-09 | HillInt-RFI-000875 | 2026-08-09 | 8 |  | Darr-RTRFI-000106 | 2026-08-17 | Dar | HillInt-RTRFI-001030 | 2026-08-17 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000034 | 0 | CCCEGY-RFI-000406 | REH.08.26.3271-CRJ-RFI-ME-000034,HVAC Duct Clearance & Ceiling Void Coordination Conflict (4 Plex-4 Bedroom type) | MEC | 2026-08-05 | HillInt-RFI-000836 | 2026-08-05 | 1 |  | Darr-RTRFI-000081 | 2026-08-06 | Dar | HillInt-RTRFI-000966 | 2026-08-06 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000035 | 0 | CCCEGY-RFI-000407 | REH.08.26.3271-CRJ-RFI-AR-000035,Clarification of Exterior Insulation and Finish System (EIFS) Specification & Scope | Architectural | 2026-08-04 | HillInt-RFI-000837 | 2026-08-05 | 5 |  | Darr-RTRFI-000086 | 2026-08-10 | Dar | HillInt-RTRFI-000983 | 2026-08-10 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000036 | 0 | CCCEGY-RFI-000416 | REH.08.26.3271-CRJ-RFI-ST-000036,General – Slab on Grade Details | STR | 2026-08-05 | HillInt-RFI-000838 | 2026-08-05 | 5 |  | Darr-RTRFI-000085 | 2026-08-10 | Dar | HillInt-RTRFI-000974 | 2026-08-10 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000036 | 1 | CCCEGY-RFI-000465 | REH.08.26.3271-CRJ-RFI-ST-000036-01,General – Slab on Grade Details | STR | 2026-08-17 | HillInt-RFI-000959 | 2026-08-17 | 6 |  | Darr-RTRFI-000127 | 2026-08-23 | Dar | HillInt-RTRFI-001095 | 2026-08-24 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000037 | 0 | CCCEGY-RFI-000437 | REH.08.26.3271-CRJ-RFI-AR-000037, 3 Bedroom townhouse – Beam clash with ceiling and missing downstand from STR IFC | Architectural | 2026-08-13 | HillInt-RFI-000914 | 2026-08-13 | 5 |  | Darr-RTRFI-000109 | 2026-08-18 | Dar | HillInt-RTRFI-001037 | 2026-08-18 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000038 | 0 | CCCEGY-RFI-000462 | REH.08.26.3271-CRJ-RFI-ST-000038, Difference between townhouses’ finish levels and natural ground levels | STR | 2026-08-17 | HillInt-RFI-000955 | 2026-08-17 | 3 |  | Darr-RTRFI-000118 | 2026-08-20 | Dar | HillInt-RTRFI-001064 | 2026-08-20 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000039 | 0 | CCCEGY-RFI-000463 | REH.08.26.3271-CRJ-RFI-ST-000039, 4 Plex – 1 Stepped – First Floor Slab | STR | 2026-08-17 | HillInt-RFI-000956 | 2026-08-17 | 7 |  | Darr-RTRFI-000126 | 2026-08-24 | Dar | HillInt-RTRFI-001094 | 2026-08-24 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000040 | 0 | CCCEGY-RFI-000466 | REH.08.26.3271-CRJ-RFI-ST-000040, WW-23 (Mockup Building) - Fence Foundation vs Building Foundation | STR | 2026-08-17 | HillInt-RFI-000960 | 2026-08-17 | 7 |  | Darr-RTRFI-000128 | 2026-08-24 | Dar | HillInt-RTRFI-001096 | 2026-08-24 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000041 | 0 | CCCEGY-RFI-000516 | REH.08.26.3271-CRJ-RFI-AR-000041, Arch Openings Clearance | Architectural | 2026-08-23 | HillInt-RFI-001059 | 2026-08-23 | 7 |  | Darr-RTRFI-000135 | 2026-08-30 | Dar | HillInt-RTRFI-001169 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000041 | 1 | CCCEGY-RFI-000694 | Re: REH.08.26.3271-CRJ-RFI-AR-000041-01, Arch Openings Clearance | Architectural | 2026-09-28 | HillInt-GNC-004421 | 2026-09-29 | 7 | ECG | SHKECGCR-RTRFI-000143 | 2026-10-06 |  | HillInt-GNC-004809 | 2026-10-06 | 0 | Response | HillInt-GNC-004760 : reminder
| REH.08-26.3271-CRJ-RFI-ME-000042 | 0 | CCCEGY-RFI-000517 | REH.08-26.3271-CRJ-RFI-ME-000042, Reply to Consultant reply to RFI(RFI-ME-000032) | MEC | 2026-08-23 | HillInt-RFI-001060 | 2026-08-23 | 8 |  | Darr-RTRFI-000156 | 2026-08-31 | Dar | HillInt-RTRFI-001184 | 2026-08-31 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ME-000043 | 0 | CCCEGY-RFI-000521 | REH.08.26.3271-CRJ-RFI-AR-000043, 3 Bedroom And 4 Bedroom Town-House– Openings Discrepancies | Architectural | 2026-08-25 | HillInt-RFI-001079 | 2026-08-26 | 4 |  | CCCEGY-RFI-000521 | 2026-08-30 | Dar | HillInt-RTRFI-001177 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000044 | 0 | CCCEGY-RFI-000518 | REH.08.26.3271-CRJ-RFI-AR-000044, 4-Plex Connection Between Townhouses | Architectural | 2026-08-23 | HillInt-RFI-001061 | 2026-08-23 | 7 |  | Darr-RTRFI-000136 | 2026-08-30 | Dar | HillInt-RTRFI-001170 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000045 | 0 | CCCEGY-RFI-000535 | REH.08.26.3271-CRJ-RFI-AR-000045, 3 Bedroom TH – Stair Discrepancy | Architectural | 2026-08-30 | HillInt-RFI-001110 | 2026-08-31 | 3 |  | SHKECGCR-RTRFI-000023 | 2026-09-03 | ECG | HillInt-GNC-004323 | 2026-09-03 | 0 | Response | send by outlook
| REH.08.26.3271-CRJ-RFI-AR-000045 | 1 | CCCEGY-RFI-000693 | Re: REH.08.26.3271-CRJ-RFI-AR-000045-01, 3 Bedroom TH – Stair Discrepancy | Architectural | 2026-09-28 | HillInt-GNC-004420 | 2026-09-29 | 5 |  | SHKECGCR-RTRFI-000135 | 2026-10-04 | ECG | HillInt-GNC-004665 | 2026-10-04 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000045 | 2 | CCCEGY-RFI-000754 | Re: REH.08.26.3271-CRJ-RFI-AR-000045-02, 3 Bedroom TH – Stair Discrepancy | Architectural | 2026-10-06 | [6 empty] | ECG |  |  |  | Open
| REH.08-26.3271-CRJ-RFI-ME-000046 | 0 | CCCEGY-RFI-000523 | REH.08-26.3271-CRJ-RFI-ME-000046, Rainwater for trash room | Mechanical | 2026-08-25 | HillInt-RFI-001080 | 2026-08-26 | 5 |  | Darr-RTRFI-000163 | 2026-08-31 | Dar | HillInt-RTRFI-001205 | 2026-09-01 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000047 | 0 | CCCEGY-RFI-000519 | REH.08.26.3271-CRJ-RFI-AR-000047, General – Roof Shafts | Architectural | 2026-08-24 | HillInt-RFI-001063 | 2026-08-24 | 8 |  | Darr-RTRFI-000162 | 2026-09-01 | Dar | HillInt-RTRFI-001204 | 2026-09-01 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000047 | 1 | CCCEGY-RFI-000594 | REH.08.26.3271-CRJ-RFI-AR-000047-01, General – Roof Shafts | Architectural | 2026-09-08 | HillInt-GNC-003286 | 2026-09-08 | 19 |  | SHKECGCR-RTRFI-000089 | 2026-09-27 | ECG | HillInt-GNC-004276 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000047 | 2 | CCCEGY-RFI-000755 | Re: REH.08.26.3271-CRJ-RFI-AR-000047-02, General – Roof Shafts | Architectural | 2026-10-07 |  |  | 0 |  |  |  | ECG |  |  | 0 | Open
| REH.08.26.3271-CRJ-RFI-ST-000048 | 0 | CCCEGY-RFI-000520 | REH.08.26.3271-CRJ-RFI-ST-000048, Received revised design for ground beams | Structural | 2026-08-24 | HillInt-RFI-001064 | 2026-08-24 | 7 |  | Darr-RTRFI-000152 | 2026-08-31 | Dar | HillInt-RTRFI-001185 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000048 | 1 | CCCEGY-RFI-000520 | REH.08.26.3271-CRJ-RFI-ST-000048-01, Received revised design for ground beams | Structural | 2026-09-03 | HillInt-GNC-003248 | 2026-09-08 | 13 |  | SHKECGCR-RTRFI-000074 | 2026-09-21 | ECG | HillInt-RTRFI-001277 | 2026-09-21 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000049 | 0 | CCCEGY-RFI-000522 | REH.08.26.3271-CRJ-RFI-ME-000049, Type of the louver on the exhaust air duct | Mechanical | 2026-08-25 | HillInt-RFI-001081 | 2026-08-26 | 5 |  | Darr-RTRFI-000158 | 2026-08-31 | Dar | HillInt-RTRFI-001186 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000050 | 0 | CCCEGY-RFI-000536 | REH.08.26.3271-CRJ-RFI-AR-000050, 4 Bedroom Town-House – Opening Sill Discrepancy | Architectural | 2026-08-30 | HillInt-RFI-001112 | 2026-08-31 | 6 |  | SHKECGCR-RTRFI-000028 | 2026-09-06 | ECG | send by outlook |  | 33 | Response
| REH.08.26.3271-CRJ-RFI-ST-000051 | 0 | CCCEGY-RFI-000524 | REH.08.26.3271-CRJ-RFI-ST-000051, Received Retaining Walls Design | Structural | 2026-08-26 | HillInt-RFI-001082 | 2026-08-26 | 6 |  | Darr-RTRFI-000164 | 2026-09-01 | Dar | HillInt-RTRFI-001224 | 2026-09-02 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000052 | 0 | CCCEGY-RFI-000525 | REH.08.26.3271-CRJ-RFI-AR-000052, Received Retaining Walls Design | Architectural | 2026-08-25 | HillInt-RFI-001083 | 2026-08-26 | 7 |  | Darr-RTRFI-000167 | 2026-09-02 | Dar | HillInt-RTRFI-001228 | 2026-09-02 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000053 | 0 | CCCEGY-RFI-000526 | REH.08.26.3271-CRJ-RFI-ST-000053, Multi-Faith Buildings (Excavation Levels & Coordinates) | Structural | 2026-08-26 | HillInt-RFI-001094 | 2026-08-31 | 16 |  | SHKECGCR-RTRFI-000067 | 2026-09-16 | ECG | HillInt-RTRFI-001270 | 2026-09-17 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000051 | 1 | CCCEGY-RFI-000582 | Re: REH.08.26.3271-CRJ-RFI-ST-000051-01, Received Retaining Walls Design | Structural | 2026-09-06 | HillInt-GNC-003249 | 2026-09-08 | #VALUE! |  | Darr-RTRFI-000189 | 3 October 2026 | Dar | HillInt-GNC-004655 | 2026-10-04 | 0 | Response | Please note that RFI No. REH.08.26.3271-CRJ-RFI-ST-000051-01 does not include the RFI response or the required signature. Kindly ensure that the response to the RFI is properly attached and duly signed before resubmission. Please review and take the necessary action accordingly.
| REH.08.26.3271-CRJ-RFI-AR-000054 | 0 | CCCEGY-RFI-000527 | REH.08.26.3271-CRJ-RFI-AR-000054, Multi-Faith Buildings (Outstanding Designs) | Architectural | 2026-08-26 | HillInt-RFI-001095 | 2026-08-31 | 23 |  | Darr-GNC-001182 | 2026-09-23 | ECG | HillInt-GNC-004707 | 2026-10-05 | 0 | Response | reminder : HillInt-GNC-004177
| REH.08.26.3271-CRJ-RFI-ST-000055 | 0 | CCCEGY-RFI-000528 | REH.08.26.3271-CRJ-RFI-ST-000055, Verification of Historical Filling and Assessment of Its Impact on Foundation Design | Structural | 2026-08-26 | HillInt-RFI-001096 | 2026-08-31 | 22 |  | SHKECGCR-RTRFI-000076 | 2026-09-22 | ECG | REH.08.26.3271-CRJ-RFI-ST-000055 | 2026-09-23 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000056 | 0 | CCCEGY-RFI-000537 | REH.08.26.3271-CRJ-RFI-ST-000056, 6 Plex – 1 & 2 Stepped – First Floor Slab | Structural | 2026-08-30 | HillInt-RFI-001115 | 2026-08-31 | 23 |  | Darr-GNC-001159 | 2026-09-23 | dar | HillInt-GNC-004115 | 2026-09-23 | 0 | Response | Transfer to dar
| REH.08.26.3271-CRJ-RFI-ST-000057 | 0 | CCCEGY-RFI-000538 | REH.08.26.3271-CRJ-RFI-ST-000057, Slab on grade – difference levels Contradiction | Structural | 2026-08-30 | HillInt-RFI-001117 | 2026-08-31 | 23 |  | Darr-GNC-001160 | 2026-09-23 | dar | HillInt-GNC-004116 | 2026-09-23 | 0 | Response | Transfer to dar
| REH.08.26.3271-CRJ-RFI-ST-000058 | 0 | CCCEGY-RFI-000529 | REH.08.26.3271-CRJ-RFI-ST-000058, Proposed Ground Beams under External Walls for Townhouses (4-Plex and 6-Plex) | Structural | 2026-08-27 | done |  | 46261 |  | SHKECGCR-RTRFI-000015 | 2026-08-27 | ECG | HillInt-RTRFI-001164 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000059 | 0 | CCCEGY-RFI-000530 | REH.08.26.3271-CRJ-RFI-ST-000059, Plate Load Test Application | Structural | 2026-08-27 | done |  | 46262 |  | SHKECGCR-RTRFI-000016 | 2026-08-28 | ECG | HillInt-RTRFI-001167 | 2026-08-31 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000060 | 0 | CCCEGY-GNC-000049 | REH.08.26.3271-CRJ-RFI-AR-000060, Underground Blockwork Quires | Architectural | 2026-09-05 | HillInt-RFI-001183 | 2026-09-08 | 1 |  | SHKECGCR-RTRFI-000031 | 2026-09-09 | ECG | HillInt-RTRFI-001238 | 2026-09-09 | 0 | Response | The submission could not be completed due to an issue with Aconex.
| REH.08.26.3271-CRJ-RFI-ME-000061 | 0 | CCCEGY-RFI-000539 | REH.08.26.3271-CRJ-RFI-ME-000061, HVAC clashes with Structural elements at Roof | Mechanical | 2026-08-30 | HillInt-RFI-001118 | 2026-08-31 | 4 |  | SHKECGCR-RTRFI-000024 | 2026-09-04 | ECG | HillInt-RTRFI-001261 | 2026-09-15 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000062 | 0 | CCCEGY-RFI-000540 | REH.08.26.3271-CRJ-RFI-ME-000062, Concrete wall behind the Lavatory at Bathroom 2 | Mechanical | 2026-08-30 | HillInt-RFI-001120 | 2026-08-31 | 15 |  | SHKECGCR-GNC-000275 | 2026-09-15 | ECG | HillInt-RTRFI-001260 | 2026-09-15 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000063 | 0 | CCCEGY-RFI-000550 | REH.08.26.3271-CRJ-RFI-ME-000063, Contradiction in the type of lavatory at the Master Bathroom | Mechanical | 2026-08-31 | HillInt-RFI-001158 | 2026-09-01 | 12 |  | SHKECGCR-RTRFI-000037 | 2026-09-13 | ECG | HillInt-GNC-003585 | 2026-09-13 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000063 | 1 | CCCEGY-RFI-000662 | Re: REH.08.26.3271-CRJ-RFI-ME-000063-01, Contradiction in the type of lavatory at the Master Bathroom | Mechanical | 2026-09-21 | HillInt-GNC-003966 | 2026-09-21 | 4 |  | SHKECGCR-RTRFI-000085 | 2026-09-25 | ECG | HillInt-GNC-004265 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000064 | 0 | CCCEGY-RFI-000547 | REH.08.26.3271-CRJ-RFI-AR-000064, General – Wall Queries – Ground Floor | Architectural | 2026-08-31 | HillInt-RFI-001150 | 2026-09-01 | 20 |  | SHKECGCR-RTRFI-000075 | 2026-09-21 | ECG | HillInt-RTRFI-001276 | 2026-09-21 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000065 | 0 | CCCEGY-RFI-000553 | REH.08.26.3271-CRJ-RFI-AR-000065, General – Acoustics Queries | Architectural | 2026-09-01 | HillInt-RFI-001153 | 2026-09-01 | 15 |  | Darr-GNC-001136 | 2026-09-16 | ECG | HillInt-RTRFI-001268 | 2026-09-17 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000066 | 0 | CCCEGY-RFI-000548 | REH.08.26.3271-CRJ-RFI-AR-000066, General – Missing Doors tags | Architectural | 2026-08-31 | HillInt-RFI-001154 | 2026-09-01 | 22 |  | SHKECGCR-RTRFI-000077 | 2026-09-23 | ECG | HillInt-GNC-004114 | 2026-09-23 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000067 | 0 | CCCEGY-RFI-000561 | REH.08.26.3271-CRJ-RFI-AR-000067, General – Entrances’ Queries | Architectural | 2026-09-02 | HillInt-RFI-001172 | 2026-09-02 | 22 |  | Darr-GNC-001193 | 2026-09-24 | Dar | HillInt-GNC-004243 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000068 | 0 | CCCEGY-RFI-000549 | REH.08.26.3271-CRJ-RFI-AR-000068, General – 4 Bedroom TH Stairs Handrail | Architectural | 2026-08-31 | HillInt-RFI-001157 | 2026-09-01 | 21 |  | Darr-GNC-001155 | 2026-09-22 | ECG | HillInt-GNC-004077 | 2026-09-22 | 0 | Response | Transfer to dar
| REH.08.26.3271-CRJ-RFI-AR-000068-01 | 1 | CCCEGY-RFI-000676 | General – 4 Bedroom TH Stairs Handrail | Architectural | 2026-09-22 | HillInt-GNC-004079 | 2026-09-22 | 4 |  | SHKECGCR-RTRFI-000091 | 2026-09-26 | ECG | HillInt-GNC-004278 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000069 | 0 | CCCEGY-RFI-000563 | REH.08.26.3271-CRJ-RFI-AR-000069, General – Kitchen Joinery Details’ Queries | Architectural | 2026-09-06 | HillInt-GNC-003250 | 2026-09-08 | 4 |  | SHKECGCR-RTRFI-000058 | 2026-09-12 | ECG | HillInt-RTRFI-001259 | 2026-09-15 | 0 | Response | The submission could not be completed due to an issue with Aconex.
| REH.08.26.3271-CRJ-RFI-AR-000070 | 0 | CCCEGY-RFI-000562 | REH.08.26.3271-CRJ-RFI-AR-000070, General – Discrepancy in wall types. | Architectural | 2026-09-02 | HillInt-RFI-001173 | 2026-09-02 | 4 |  | Darr-RTRFI-000173 | 2026-09-06 | ECG | HillInt-GNC-003982 | 2026-09-21 | 0 | Response | send by outlook
| REH.08.26.3271-CRJ-RFI-ME-000071 | 0 | CCCEGY-RFI-000564 | REH.08.26.3271-CRJ-RFI-ME-000071, Reply to Consultant reply to RFI(RFI-ME-000042) | Mechanical | 2026-09-03 | HillInt-GNC-003251 | 2026-09-08 | 3 |  | SHKECGCR-RTRFI-000036 | 2026-09-11 | ECG | HillInt-GNC-003584 | 2026-09-13 | 0 | Response | The submission could not be completed due to an issue with Aconex.
| REH.08.26.3271-CRJ-RFI-ST-000072 | 0 | CCCEGY-RFI-000583 | REH.08.26.3271-CRJ-RFI-ST-000072, Multi-Faith Buildings (Superstructure Design) | Structural | 2026-09-06 | HillInt-GNC-003252 | 2026-09-08 | 7 |  | Darr-GNC-001128 | 2026-09-15 | ECG | HillInt-RTRFI-001258 | 2026-09-15 | 0 | Response | The submission could not be completed due to an issue with Aconex.
| REH.08.26.3271-CRJ-RFI-ST-000072 | 1 | CCCEGY-RFI-000696 | Re: REH.08.26.3271-CRJ-RFI-ST-000072-01, Multi-Faith Buildings (Superstructure Design) | Structural | 2026-09-28 | HillInt-GNC-004423 | 2026-09-29 | 8 | ECG | SHKECGCR-RTRFI-000171 | 2026-10-07 | ECG | HillInt-GNC-004915 | 2026-10-07 | 0 | Response | HillInt-GNC-004748 : reminder
| REH.08.26.3271-CRJ-RFI-ME-000073 | 0 | CCCEGY-RFI-000584 | REH.08.26.3271-CRJ-RFI-ME-000073, Contradiction in the Capacity of Ventilation fans | Mechanical | 2026-09-06 | HillInt-GNC-003253 | 2026-09-08 | 6 |  | Darr-GNC-001110 | 2026-09-14 | ECG | HillInt-RTRFI-001257 | 2026-09-15 | 0 | Response | The submission could not be completed due to an issue with Aconex.
| REH.08.26.3271-CRJ-RFI-ME-000073 | 1 | CCCEGY-RFI-000663 | Re: REH.08.26.3271-CRJ-RFI-ME-000073-01, Contradiction in the Capacity of Ventilation fans | Mechanical | 2026-09-21 | HillInt-GNC-003984 | 2026-09-21 | 3 |  | Darr-GNC-001187 | 2026-09-24 | DAR | HillInt-GNC-004236 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000074 | 0 | CCCEGY-RFI-000638 | REH.08.26.3271-CRJ-RFI-AR-000074, Skirting discrepancies | Architectural | 2026-09-17 | HillInt-GNC-003830 | 2026-09-17 | 3 |  | SHKECGCR-RTRFI-000071 | 2026-09-20 | ECG | HillInt-GNC-003877 | 2026-09-20 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ST-000075 | 0 | CCCEGY-RFI-000602 | REH.08-26.3271-CRJ-RFI-ST-000075, WW-71 & WW-69 – Common fence foundation | Structural | 2026-09-09 | HillInt-GNC-003397 | 2026-09-09 | 1 |  | SHKECGCR-RTRFI-000034 | 2026-09-10 | ECG | HillInt-RTRFI-001262 | 2026-09-16 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ST-000075 | 1 | CCCEGY-RFI-000656 | REH.08-26.3271-CRJ-RFI-ST-000075-01, WW-71 & WW-69 – Common fence foundation | Structural | 2026-09-20 | HillInt-GNC-003996 | 2026-09-21 | 2 |  | Darr-GNC-001171 | 2026-09-23 | ECG | HillInt-GNC-004159 | 2026-09-24 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ST-000075 | 2 | CCCEGY-RFI-000703 | Re: REH.08-26.3271-CRJ-RFI-ST-000075-02, WW-71 & WW-69 – Common fence foundation | Structural | 2026-09-29 | HillInt-GNC-004435 | 2026-09-29 | 1 |  | Darr-GNC-001243 | 2026-09-30 | DAR | HillInt-GNC-004511 | 2026-09-30 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000076 | 0 | CCCEGY-RFI-000603 | REH.08.26.3271-CRJ-RFI-ST-000076, Fence wall between houses at the same plex | Structural | 2026-09-09 | HillInt-GNC-003398 | 2026-09-09 | 7 |  | Darr-GNC-001134 | 2026-09-16 | ECG | HillInt-RTRFI-001267 | 2026-09-17 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000077 | 0 | CCCEGY-RFI-000613 | REH.08.26.3271-CRJ-RFI-ST-000077, FENCE LOCATION – SITE PLAN vs MASTER PALN | Structural | 2026-09-12 | HillInt-GNC-003576 | 2026-09-13 | 4 |  | Darr-GNC-001138 | 2026-09-17 | ECG | HillInt-RTRFI-001271 | 2026-09-17 | 0 | Response
| REH.08-26.3271-CRJ-RFI-ST-000078 | 0 | CCCEGY-RFI-000614 | REH.08-26.3271-CRJ-RFI-ST-000078, Contradiction between fence wall in connection with the Str. element of the building | Structural | 2026-09-12 | HillInt-GNC-003574 | 2026-09-13 | -46278 | DAR | [5 empty] | 20 | Open | reminder HillInt-GNC-003873
| REH.08.26.3271-CRJ-RFI-AR-000079 | 0 | CCCEGY-RFI-000640 | REH.08.26.3271-CRJ-RFI-AR-000079, Discrepancies Between Arch ID Drawings and MEP Drawings | Architectural | 2026-09-18 | HillInt-GNC-003882 | 2026-09-20 | 4 |  | Darr-GNC-001191 | 2026-09-24 | Dar | HillInt-GNC-004242 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000080 | 0 | CCCEGY-RFI-000619 | REH.08.26.3271-CRJ-RFI-ST-000080, Discrepancy Regarding the Exact Location of the External Boundary Wall | CIVIL | 2026-09-15 | HillInt-GNC-003675 | 2026-09-15 | 12 |  | Darr-GNC-001211 | 2026-09-27 | ECG | HillInt-GNC-004283 | 2026-09-27 | 0 | Response | trasfer to DAR
| REH.08.26.3271-CRJ-RFI-ST-000081 | 0 | CCCEGY-RFI-000620 | REH.08.26.3271-CRJ-RFI-ST-000081, WW-87 Contradiction at fence foundation Vs Plex Footings | CIVIL | 2026-09-15 | HillInt-GNC-003676 | 2026-09-15 | 7 |  | Darr-GNC-001157 | 2026-09-22 | ECG | HillInt-GNC-004344 | 2026-09-28 | 0 | Response | trasfer to DAR
| REH.08.26.3271-CRJ-RFI-ST-000082 | 0 | CCCEGY-RFI-000621 | REH.08.26.3271-CRJ-RFI-ST-000082, Contradiction between IFC general fence foundation detail & superimposed plan for plex & fence foundation | CIVIL | 2026-09-15 | HillInt-GNC-003677 | 2026-09-15 | 9 |  | Darr-GNC-001172 | 2026-09-24 | ECG | HillInt-GNC-004176 | 2026-09-24 | 0 | Response | Trasfer to DAR
| REH.08.26.3271-CRJ-RFI-ST-000083 | 0 | CCCEGY-RFI-000622 | REH.08.26.3271-CRJ-RFI-ST-000083, WW-17 Contradiction at fence foundation Vs Plex Footings | CIVIL | 2026-09-15 | HillInt-GNC-003678 | 2026-09-15 | #REF! |  | Darr-RTRFI-000183 | 2026-09-22 | Dar | HillInt-GNC-004078 | 2026-09-22 | 0 | Response | Trasfer to DAR
| REH.08.26.3271-CRJ-RFI-ST-000084 | 0 | CCCEGY-RFI-000623 | REH.08.26.3271-CRJ-RFI-ST-000084, Fence Foundation & walls – Expansion joint | CIVIL | 2026-09-15 | HillInt-GNC-003679 | 2026-09-15 | 7 |  | Darr-GNC-001168 | 2026-09-23 | Dar | HillInt-GNC-004136 | 2026-09-23 | 0 | Response | Trasfer to DAR
| REH.08.26.3271-CRJ-RFI-ST-000085 | 0 | CCCEGY-RFI-000639 | REH.08.26.3271-CRJ-RFI-EL-000085, Electric Conduits Colors | ELEC | 2026-09-17 | HillInt-GNC-003828 | 2026-09-17 | 6 |  | Darr-GNC-001151 | 2026-09-20 | ECG | HillInt-RTRFI-001275 | 2026-09-21 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000086 | 0 | CCCEGY-RFI-000652 | REH.08.26.3271-CRJ-RFI-AR-000086, Ceiling Clashes. | Architectural | 2026-09-20 | HillInt-GNC-003908 | 2026-09-20 | 7 |  | SHKECGCR-RTRFI-000082 | 2026-09-27 | ECG | HillInt-GNC-004263 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000087 | 0 | CCCEGY-RFI-000657 | REH.08.26.3271-CRJ-RFI-ST-000087, WW-54 - Fence Foundation & walls | Structural | 2026-09-21 | HillInt-GNC-003997 | 2026-09-21 | 2 |  | Darr-GNC-001183 | 2026-09-23 | ECG | HillInt-GNC-004178 | 2026-09-24 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000087 | 1 | CCCEGY-RFI-000702 | Re: REH.08.26.3271-CRJ-RFI-ST-000087-01, WW-54 - Fence Foundation & walls | Structural | 2026-09-29 | HillInt-GNC-004434 | 2026-09-29 | 1 |  | Darr-GNC-001244 | 2026-09-30 | Dar | HillInt-GNC-004512 | 2026-09-30 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000088 | 0 | CCCEGY-RFI-000699 | REH.08.26.3271-CRJ-RFI-ST-000088, Master Plan | Structural | 2026-09-28 | HillInt-GNC-004426 | 2026-09-29 | -46294 | DAR | [5 empty] | 4 | Open | HillInt-GNC-004734 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000089 | 0 | CCCEGY-RFI-000653 | REH.08.26.3271-CRJ-RFI-CV-00089, Inquiry about Roads Profiles. | CIVIL | 2026-09-20 | HillInt-GNC-003955 | 2026-09-21 | 16 | DAR | SHKECGCR-RTRFI-000165 | 2026-10-07 |  | HillInt-GNC-004911 | 2026-10-07 | 0 | Response | HillInt-GNC-004749 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000090 | 0 | CCCEGY-RFI-000654 | REH.08.26.3271-CRJ-RFI-CV-00090, Inquiry about Road Profile (Number 35) | CIVIL | 2026-09-20 | HillInt-GNC-003953 | 2026-09-21 | 16 | DAR | SHKECGCR-RTRFI-000166 | 2026-10-07 |  | HillInt-GNC-004912 | 2026-10-07 | 0 | Response | HillInt-RFI-001210
| REH.08.26.3271-CRJ-RFI-ST-000091 | 0 | CCCEGY-RFI-000655 | REH.08.26.3271-CRJ-RFI-CV-00091, Inquiry about Roads Design Package | CIVIL | 2026-09-20 | HillInt-GNC-003954 | 2026-09-21 | 16 | DAR | SHKECGCR-RTRFI-000186 | 2026-10-07 |  | HillInt-GNC-004942 | 2026-10-07 | 0 | Response | HillInt-GNC-004759 : reminder
| REH.08.26.3271-CRJ-RFI-AR-000092 | 0 | CCCEGY-RFI-000698 | REH.08.26.3271-CRJ-RFI-AR-000092, 3&4 Bedroom - Skirting Behind Wardrobe | Architectural | 2026-09-28 | HillInt-GNC-004425 | 2026-09-29 | 5 |  | SHKECGCR-RTRFI-000136 | 2026-10-04 | ECG | HillInt-GNC-004666 | 2026-10-04 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000093 | 0 | CCCEGY-RFI-000664 | REH.08.26.3271-CRJ-RFI-ME-000093, Coordination between fence and Plumbing work | Mechanical | 2026-09-21 | HillInt-GNC-003983 | 2026-09-21 | -46286 | DAR | [5 empty] | 11 | Open | HillInt-GNC-004743 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000094 | 0 | CCCEGY-RFI-000683 | REH.08.26.3271-CRJ-RFI-ME-000094, Inquiry about Potable water and Firefighting Networks | Mechanical | 2026-09-24 | HillInt-GNC-004244 | 2026-09-27 | 10 | DAR | SHKECGCR-RTRFI-000184 | 2026-10-07 |  | HillInt-GNC-004937 | 2026-10-07 | 0 | Response | HillInt-GNC-004750 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000095 | 0 | CCCEGY-RFI-000684 | REH.08.26.3271-CRJ-RFI-ME-000095, Inquiry about Potable water and Firefighting Networks | Mechanical | 2026-09-27 | HillInt-GNC-004248 | 2026-09-27 | -46292 | DAR | [5 empty] | 5 | Open | HillInt-GNC-004751 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000096 | 0 | CCCEGY-RFI-000673 | REH.08.26.3271-CRJ-RFI-ME-000096, Inquiry about Mechanical Infrastructure Package | Mechanical | 2026-09-21 | HillInt-GNC-004026 | 2026-09-21 | 16 | DAR | SHKECGCR-RTRFI-000164 | 2026-10-07 | ECG | HillInt-GNC-004909 | 2026-10-07 | 0 | Response | HillInt-GNC-004752 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000097 | 0 | CCCEGY-RFI-000661 | REH.08.26.3271-CRJ-RFI-AR-000097, Plaster Thickness discrepancies. | Architectural | 2026-09-21 | HillInt-GNC-003957 | 2026-09-21 | 4 |  | SHKECGCR-RTRFI-000083 | 2026-09-25 | ECG | HillInt-GNC-004264 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000098 | 0 | CCCEGY-RFI-000669 | REH.08.26.3271-CRJ-RFI-ST-000098, Multifaith – Buildings names & Coordinates | Structural | 2026-09-21 | HillInt-GNC-004022 | 2026-09-21 | 6 |  | Darr-RTRFI-000187 | 2026-09-27 | dar | HillInt-GNC-004253 | 2026-09-27 | 0 | Response | HillInt-GNC-004241 Please note that the RFI reply has not been attached to the email, although the email refers to an attached reply. Kindly ensure that the complete RFI reply is properly attached and resend the email accordingly. Please make sure to verify all attachments before sending any correspondence to avoid delays and unnecessary rework. Your immediate action is required.
| REH.08.26.3271-CRJ-RFI-ST-000099 | 0 | CCCEGY-RFI-000670 | Fwd: REH.08.26.3271-CRJ-RFI-ST-000099, Pergolas Anchors Details | Structural | 2026-09-21 | HillInt-GNC-004023 | 2026-09-21 | -46286 | DAR | [5 empty] | 11 | Open | HillInt-GNC-004753 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000100 | 0 | CCCEGY-RFI-000671 | Fwd: REH.08.26.3271-CRJ-RFI-ST-000100, Contradiction between landscape & structure drawings | Structural | 2026-09-21 | HillInt-GNC-004024 | 2026-09-21 | 6 |  | Darr-GNC-001189 | 2026-09-27 | dar | HillInt-GNC-004238 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000100 | 1 | CCCEGY-RFI-000751 | Re: REH.08.26.3271-CRJ-RFI-ST-000100-01, Contradiction between landscape & structure drawings | Structural | 2026-10-05 | HillInt-GNC-004733 | 2026-10-05 | -46300 | ECG | [5 empty] | 0 | Open
| REH.08.26.3271-CRJ-RFI-ST-000101 | 0 | CCCEGY-RFI-000672 | Fwd: REH.08.26.3271-CRJ-RFI-ST-000101, WW71-Contradiction for pergolas pedestals | Structural | 2026-09-21 | HillInt-GNC-004025 | 2026-09-21 | 6 |  | Darr-GNC-001188 | 2026-09-27 | ECG | HillInt-GNC-004237 | 2026-09-27 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ST-000102 | 0 | CCCEGY-RFI-000674 | REH.08.26.3271-CRJ-RFI-GN-000102, Inquiry about BOQ | All Disciplines | 2026-09-21 | HillInt-GNC-004027 | 2026-09-21 | 16 | DAR | SHKECGCR-RTRFI-000185 | 2026-10-07 |  | HillInt-GNC-004940 | 2026-10-07 | 0 | Response | HillInt-GNC-004742 : reminder
| REH.08.26.3271-CRJ-RFI-GN-000103 | 0 | CCCEGY-RFI-000685 | Fwd: REH.08.26.3271-CRJ-RFI-GN-000103, Inquiry about Infrastructure package (Multi faith) | All Disciplines | 2026-09-24 | HillInt-GNC-004254 | 2026-09-27 | 3 |  | Darr-GNC-001237 | 2026-09-30 | ECG | HillInt-GNC-004510 | 2026-09-30 | 0 | Response
| REH.08.26.3271-CRJ-RFI-GN-000104 | 0 | CCCEGY-RFI-000686 | REH.08.26.3271-CRJ-RFI-GN-000104, Inquiry about Infrastructure package (Lagoons) | All Disciplines | 2026-09-24 | HillInt-GNC-004255 | 2026-09-27 | 9 | DAR | SHKECGCR-RTRFI-000152 | 2026-10-06 | ECG | HillInt-GNC-004857 | 2026-10-06 | 0 | Response | HillInt-GNC-004682 : reminder
| REH.08.26.3271-CRJ-RFI-EL-000105 | 0 | CCCEGY-RFI-000687 | REH.08.26.3271-CRJ-RFI-EL-000105, Inquiry about Infrastructure package (Electric) | Electrical | 2026-09-24 | HillInt-GNC-004256 | 2026-09-27 | 10 | ECG | SHKECGCR-RTRFI-000181 | 2026-10-07 |  | HillInt-GNC-004933 | 2026-10-07 | 0 | Response | HillInt-GNC-004754 : reminder
| REH.08.26.3271-CRJ-RFI-GN-000106 | 0 | CCCEGY-RFI-000689 | REH.08.26.3271-CRJ-RFI-GN-000106, Inquiry about Infrastructure package (General) | All Disciplines | 2026-09-25 | HillInt-GNC-004258 | 2026-09-27 | 10 | DAR | SHKECGCR-RTRFI-000167 | 2026-10-07 |  | HillInt-GNC-004913 | 2026-10-07 | 0 | Response | HillInt-GNC-004683 : reminder
| REH.08.26.3271-CRJ-RFI-EL-000107 | 0 | CCCEGY-RFI-000688 | REH.08.26.3271-CRJ-RFI-EL-000107, Clarification on Earthing System Descoping vs. IFC Scope | Electrical | 2026-09-25 | HillInt-GNC-004257 | 2026-09-27 | 4 | ECG | SHKECGCR-RTRFI-000114 | 2026-10-01 | ECG | HillInt-GNC-004755 | 2026-10-05 | 0 | Response
| REH.08.26.3271-CRJ-RFI-EL-000108 | 0 | CCCEGY-RFI-000690 | REH.08.26.3271-CRJ-RFI-EL-000108, Clarification & Revision Request: Descoping of provisional sum Items | Electrical | 2026-09-25 | HillInt-GNC-004259 | 2026-09-27 | 4 |  | SHKECGCR-RTRFI-000116 | 2026-10-01 | ECG | HillInt-GNC-004724 | 2026-10-05 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000109 | 0 | CCCEGY-RFI-000697 | REH.08.26.3271-CRJ-RFI-AR-000109, 3 Bedroom First Floor - Ceiling Queries | Architectural | 2026-09-28 | HillInt-GNC-004424 | 2026-09-29 | 7 | ECG | SHKECGCR-RTRFI-000150 | 2026-10-06 | ECG | HillInt-GNC-004856 | 2026-10-06 | 0 | Response | HillInt-GNC-004756 : reminder
| REH.08.26.3271-CRJ-RFI-AR-000110 | 0 | CCCEGY-RFI-000695 | REH.08.26.3271-CRJ-RFI-AR-000110, 4 Plex – Landscape Discrepancy | Architectural | 2026-09-28 | HillInt-GNC-004422 | 2026-09-29 | -46294 | ECG | [5 empty] | 4 | Open | HillInt-GNC-004757 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000111 | 0 | CCCEGY-RFI-000700 | REH.08.26.3271-CRJ-RFI-ST-000111, Fence Foundation & Concrete walls Model | Structural | 2026-09-28 | HillInt-GNC-004428 | 2026-09-29 | 8 | DAR | SHKECGCR-RTRFI-000178 | 2026-10-07 |  | HillInt-GNC-004925 | 2026-10-07 | 0 | Response | HillInt-GNC-004735 : reminder
| REH.08.26.3271-CRJ-RFI-ST-000112 | 0 | CCCEGY-RFI-000701 | REH.08.26.3271-CRJ-RFI-ST-000112, Request for Structural Calculations & Geotechnical Data – Townhouse Fences | Structural | 2026-09-29 | HillInt-GNC-004429 | 2026-09-29 | -46294 | DAR | [5 empty] | 3 | Open | HillInt-GNC-004758 : reminder
| REH.08.26.3271-CRJ-RFI-ME-000113 | 0 | CCCEGY-RFI-000735 | REH.08.26.3271-CRJ-RFI-ME-000113, Coordination between fence and Plumbing work (WW 23) | Mechanical | 2026-10-01 | HillInt-GNC-004609 | 2026-10-04 | -46299 | [6 empty] | 1 | Open
| REH.08.26.3271-CRJ-RFI-AR-000114 | 0 | CCCEGY-RFI-000746 | REH.08.26.3271-CRJ-RFI-AR-000114, 3&4 Bedroom – Discrepancy Between Architectural ID and HVAC Drawings | Architectural | 2026-10-04 | HillInt-GNC-004610 | 2026-10-04 | -46299 | [6 empty] | 0 | Open
| REH.08.26.3271-CRJ-RFI-AR-000115 | 0 | CCCEGY-RFI-000747 | REH.08.26.3271-CRJ-RFI-AR-000115, 3&4 Bedroom – Discrepancy between Arch & Mep in dishwasher location | Architectural | 2026-10-04 | HillInt-GNC-004611 | 2026-10-04 | -46299 | [6 empty] | 0 | Open
| REH.08.26.3271-CRJ-RFI-AR-000116 | 0 | CCCEGY-RFI-000752 | REH.08.26.3271-CRJ-RFI-AR-000116, discrepancy between Access panel location in MECH & ARCH | Architectural | 2026-10-05 | HillInt-GNC-004770 | 2026-10-05 | 1 | ecg | SHKECGCR-GNC-000530 | 2026-10-06 | ecg | HillInt-GNC-004869 | 2026-10-07 | 0 | Response
| REH.08.26.3271-CRJ-RFI-ME-000117 | 0 | CCCEGY-RFI-000748 | REH.08.26.3271-CRJ-RFI-ME-000117, Requesting additional water hammer arrestor | Mechanical | 2026-10-04 | HillInt-GNC-004671 | 2026-10-04 | -46299 | [6 empty] | 0 | Open
| REH.08.26.3271-CRJ-RFI-AR-000118 | 0 | CCCEGY-RFI-000749 | REH.08.26.3271-CRJ-RFI-AR-000118, 3&4 Bedroom – Discrepancy between ID & Material Approval | Architectural | 2026-10-05 | HillInt-GNC-004730 | 2026-10-05 | 2 |  | SHKECGCR-RTRFI-000170 | 2026-10-07 |  | HillInt-GNC-004914 | 2026-10-07 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000119 | 0 | CCCEGY-RFI-000750 | REH.08.26.3271-CRJ-RFI-AR-000119, 3&4 Bedroom – Discrepancy between ID & Material Approved | Architectural | 2026-10-05 | HillInt-GNC-004732 | 2026-10-05 | 2 |  | SHKECGCR-RTRFI-000174 | 2026-10-07 |  | HillInt-GNC-004920 | 2026-10-07 | 0 | Response
| REH.08.26.3271-CRJ-RFI-AR-000120 | 0 | CCCEGY-RFI-000753 | REH.08.26.3271-CRJ-RFI-AR-000120, 3&4 Bedroom – Ironmongery Manual Is Missing | Architectural | 2026-10-05 | HillInt-GNC-004771 | 2026-10-05 | 2 |  | SHKECGCR-RTRFI-000176 | 2026-10-07 |  | HillInt-GNC-004921 | 2026-10-07 | 0 | Response