## Dashboard
RFI LOG DASHBOARD DP05
TOTAL ITEMS |  |  | PENDING |  |  | RESPONDED
36 |  |  | 12 |  |  | 24
Arch |  |  | ST |  |  | ME
Total |  | 3 | Total |  | 32 | Total | 1
Pending |  | 3 | Pending |  | 9 | Pending | 0
Responded |  | 0 | Responded |  | 23 | Responded | 1
| Sheet Name | Total | Pending | Responded | Response Rate
| Arch | 3 | 3 | 0 | 0%
| ST | 32 | 9 | 23 | 71.88%
| ME | 1 | 0 | 1 | 100%
| GRAND TOTAL | 36 | 12 | 24 | 66.67%

## Arch
Request For Information Log For Design Pakage DP05 | [15 empty] | ALL | 3
[16 empty] | Response | 0
ACC TO HILL |  | Orascom to Hill |  |  |  | Hill To OBMI |  | OBMI To Hill |  | Hill To Orascom |  | Dewan to hill |  | hill TO CCC |  | open | 3
Mail No | Mail No2 | REV | RFI No | Subject | Date | Mail No3 | Date4 | Mail No5 | Date6 | Mail No7 | Date8 | Mail No9 | Date10 | Mail No11 | Date12 | Status | Notes
CCCEGY-RFI-000003 | REH-MD1-DP5-AR-OC-HIL-RFI-0001 | 0 | REH-MD1-DP5-AR-OC-HIL-RFI-0001 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Architectural - 0001 - Clusters ground finish floor level | 2026-09-01 | HillInt-RFI-001163 | 2026-09-02 | [8 empty] | open | Sent To Ihab Ghaly HillInt-RFI-000484 21/6/2026
CCCEGY-RFI-000002 | REH-MD1-DP5-AR-OC-HIL-RFI-0002 | 0 | REH-MD1-DP5-AR-OC-HIL-RFI-0002 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Architectural - 0002 - elevators, Dump waiter, & trolly lift dimensions & pits | 2026-09-14 | HillInt-GNC-003619 | 2026-09-12 | [8 empty] | open
CCCEGY-RFI-000001 | REH-MD1-DP5-AR-OC-HIL-RFI-0003 | 0 | REH-MD1-DP5-AR-OC-HIL-RFI-0003 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Architectural - 0003 - Contradiction between architectural 100% schematic package & Structural IFC package | 2026-09-14 | HillInt-GNC-003616 | 2026-09-14 | [8 empty] | open

## ST
Request For Information Log For Design Pakage DP05 | [15 empty] | ALL | 32
[16 empty] | Response | 23
ACC TO HILL |  | Orascom to Hill |  |  |  | Hill To OBMI |  | HILL To SHKER |  | Hill To Orascom |  | Dewan to hill |  | hill TO CCC |  | open | 9
Mail No | Mail No2 | REV | RFI No | Subject | Date | Mail No3 | Date4 | Mail No5 | Date6 | Mail No7 | Date8 | Mail No9 | Date10 | Mail No11 | Date12 | Status | Notes
CCCEGY-RFI-000003 | REH-MD1-DP5-ST-OC-HIL-RFI-0001 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0001 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0001 - BRV-OVERALL EXCAVATION PLAN FOUNDATION SECTION | 16/07/2026 | HillInt-RTRFI-000819 | 17/07/2026 | OBMI-RTRFI-000024 | 30/07/2026 | HillInt-RTRFI-000921 | 3 August 2026 |  |  |  |  | Response
CCCEGY-RFI-000002 | REH-MD1-DP5-ST-OC-HIL-RFI-0002 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0002 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0002 - Applicable specification for DP05 works | 19/07/2026 | HillInt-RFI-000965 | 2026-08-18 |  | Hill To OBMI | HillInt-RTRFI-001052 | 2026-08-19 |  |  |  |  | Response
CCCEGY-RFI-000001 | REH-MD1-DP5-ST-OC-HIL-RFI-0003 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0003 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0003 - Retaining system design near Cluster A -Village (V04) | 19/07/2026 |  |  |  |  | HillInt-RTRFI-001041 | 2026-08-18 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0004 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0004 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0004 - Retaining system design near Cluster A -Village (V04) | 22/07/2026 | HillInt-RFI-000779 | 23/07/2026 | OBMI-RTRFI-000025 | 2026-08-02 | HillInt-RTRFI-000920 | 2026-08-03 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0005 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0005 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0005 - Review Comments on DP05 Village GDR – Appendices and Calculations | 2026-09-08 | HillInt-RFI-000966 | 2026-08-18 |  |  | HillInt-RTRFI-001193 | 2026-09-01 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0006 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0006 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0006 - Basement Excavation For DP05 | 2026-08-10 | HillInt-RFI-000967 | 2026-08-18 |  |  | HillInt-RTRFI-001072 | 2026-08-20 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0007 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0007 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0007 - Clarification on Structural Filling/Backfilling Material Requirements | 2026-08-15 | HillInt-RFI-000968 | 2026-08-18 |  |  | HillInt-RTRFI-001194 | 2026-09-01 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0008 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0008 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0008 - Clarification of Design Service Life Requirements for DP05 Structures | 2026-08-16 | HillInt-RFI-000969 | 2026-08-18 |  |  | HillInt-RFI-000990 | 2026-08-19 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0009 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0009 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0009 - Clarification of Waterproofing and Damp Proofing Typical Details | 2026-08-16 | HillInt-RFI-000970 | 2026-08-18 |  |  | HillInt-RFI-000991 | 2026-08-19 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0010 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0010 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0010 - Cluster A - Elevator pit and Sump-Pit dimensions and Location | 2026-08-21 |  |  |  |  | HillInt-RTRFI-001173 | 2026-08-31 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-10-1 | 1 | REH-MD1-DP5-ST-OC-HIL-RFI-10-1 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0010 R1- Cluster A - Elevator pit and Sump-Pit dimensions and Location | 2026-09-01 |  |  | HillInt-GNC-003167 | 2026-09-06 | [6 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0011 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0011 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0011 - Cove wall retaining system and the excavation for the branded resident village (area 1.3) | 2026-08-20 | HillInt-RFI-001075 | 2026-08-25 |  |  | HillInt-RTRFI-001234 | 2026-09-08 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0012 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0012 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0012 - proposed of Stirrups Punching Shear Reinforcement in Raft Foundation at cluster A -DP05 | 2026-08-24 | HillInt-RFI-001073 | 2026-08-25 |  |  | HillInt-RTRFI-001168 | 2026-08-31 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0013 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0013 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0013 - Review Comments and Clarifications Required on DP05 Affiniti Draft GDR | 2026-08-24 | HillInt-RFI-001077 | 2026-08-25 |  |  | HillInt-RTRFI-001192 | 2026-09-01 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0013 | 1 | REH-MD1-DP5-ST-OC-HIL-RFI-0013 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0013 - Review Comments and Clarifications Required on DP05 Affiniti Draft GDR | 2026-09-07 |  |  |  |  | HillInt-GNC-004152 | 2026-09-24 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0014 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0014 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0014 - Clarification on Retaining System details at Afiniti – Cove Side | 2026-08-31 | HillInt-RFI-001116 | 2026-08-31 | [8 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0015 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0015 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0015 - Cluster B – Miss Coordination Between Arch & STR | 2026-09-06 | HillInt-RFI-001178 | 2026-09-06 |  |  | HillInt-GNC-004388 | 2026-09-29 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0016 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0016 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0016 - Cluster-A01& Cluster-A02 Coordinates and Structure Foundation Clarification | 2026-09-08 | HillInt-GNC-003646 | 2026-09-14 |  |  | HillInt-GNC-004014 | 2026-09-21 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0017 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0017 | FL To HILL: REH.08.26.3205-00-OCC-ZZ-FL-000017 – Response to Outstanding Submission of Soil Investigation and Borehole Test Results | 2026-09-09 |  |  |  |  | HillInt-RTRFI-001282 | 2026-09-24 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0018 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0018 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0018 - AFINITI Excavation For DP05 | 2026-09-16 |  |  |  |  | HillInt-RTRFI-001279 | 2026-09-21 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0019 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0019 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0019 - Clarification on Soil Replacement Requirements for the Remaining Part at F.F.L. +22.00 | 2026-09-16 |  |  |  |  | HillInt-RTRFI-001280 | 2026-09-21 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0020 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0020 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0020 - Review and Confirmation of Soil Replacement – Basement at Level +17.00 m - Part 3 | 2026-09-17 |  |  |  |  | HillInt-RTRFI-001278 | 2026-09-21 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0021 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0021 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0021 - Village Basement (Area 1.2) – Clashes Between STR & ARCH | 2026-09-23 | HillInt-GNC-004171 | 2026-09-24 |  |  | HillInt-GNC-004443 | 2026-09-30 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0022 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0022 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0022 - Village Basement (Area 1.2) – Sump Pit Location | 2026-09-24 | HillInt-GNC-004173 | 2026-09-24 |  |  | HillInt-GNC-004568 | 2026-10-01 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0023 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0023 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0023 - Review Comments and Clarifications Required on Structural Design of Columns and Foundations for Clusters A01, A02, and A04 - Village Area | 2026-09-29 | HillInt-GNC-004446 | 2026-09-24 |  |  | HillInt-GNC-004729 | 2026-10-05 |  |  |  |  | Response
| REH-MD1-DP5-ST-OC-HIL-RFI-0024 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0024 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0024 - Review Comments and Clarifications Required on Final GDR for DP05-DP01 and DP05-DP04 Interface Walls | 2026-10-03 | HillInt-GNC-004600 | 2026-10-04 | [8 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0025 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0025 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0025 - Review Comments and Clarifications Required on DP05 Affiniti GDR – Addendum | 2026-10-03 | HillInt-GNC-004596 | 2026-10-04 | [8 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0026 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0026 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0026 - Required geotechnical recommendations for the front part of Afiniti – near step (1) | 2026-10-03 | HillInt-GNC-004597 | 2026-10-04 | [8 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0027 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0027 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0027 - Expansion Joint Location and Dimension Conflicts at Village Basement Level | 2026-10-04 | HillInt-GNC-004687 | 2026-10-05 | [8 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0028 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0028 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0028 - Comments on DP05 Afiniti Diaphragm Cliff Wall 3 - Reinforcement Details | 2026-10-05 | HillInt-GNC-004790 | 2026-10-06 | [8 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0029 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0029 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0029 - Request for Foundation Design Package - Afiniti Hotel | 2026-10-11 | [10 empty] | open
| REH-MD1-DP5-ST-OC-HIL-RFI-0030 | 0 | REH-MD1-DP5-ST-OC-HIL-RFI-0030 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Structure - 0030 - Conflicts Between Carnelia’s G.I.R. & Carnelia’s Excavation IFC Package | 2026-10-11 | [10 empty] | open

## ME
Request For Information Log For Design Pakage DP05 | [15 empty] | ALL | 1
[16 empty] | Response | 1
ACC TO HILL |  | Orascom to Hill |  |  |  | Hill To OBMI |  | OBMI To Hill |  | Hill To Orascom |  | Dewan to hill |  | hill TO CCC |  | OPEN | 0
Mail No | Mail No | REV | RFI No | Subject | Date | Mail No | Date | Mail No | Date | Mail No | Date | Mail No | Date | Mail No | Date | Status | Notes
CCCEGY-RFI-000003 | REH-MD1-DP5-ME-OC-HIL-RFI-0001 | 0 | REH-MD1-DP5-ME-OC-HIL-RFI-0001 | P1000-K03205 – DP05 – REH-Wadi Yemm – Request for Information – Mechanical - 0001 - Clarification for drainage system for clusters | 2026-09-03 |  |  |  |  | HillInt-RTRFI-001281 | 2026-09-22 |  |  |  |  | Response |  | Sent To Ihab Ghaly HillInt-RFI-000484 21/6/2026 | Sent To Al Ain HillInt-RFI-000516 24/6/2026
CCCEGY-RFI-000001