## GRAND CANAL
Request For Information Log For Grand Canal Project | [11 empty] | ALL | 8
[12 empty] | Response | 7
Hassan Allam TO HILL | [5 empty] | Hill to Hassan Allam |  | Dewan to hill |  | hill TO CCC |  | open | 1
Mail No | Mail No | REV | RFI No | Subject | Date | Mail No | Date | Mail No | Date | Mail No | Date
CCCEGY-RFI-000003 | P0801-K03200-HA-HI-SU-RFI-000001 | 0 | HAC-RFI-000008 | P0801-K03200-HA-HI-SU-RFI-000001 - Clarification of the Grand Canal Excavation Limits | 2026-04-03 | HillInt-RTRFI-000224 | 21 April 2026 |  |  |  |  | Response
CCCEGY-RFI-000002 | P0801-K03200-HA-HI-ST-RFI-000002 | 0 | HAC-RFI-000010 | P0801-K03200-HA-HI-ST-RFI-000002 for Submission of Alternative Route Proposal with DWG & KMZ Drawings for Dry Bulk Excavation. | 2026-04-12 | HillInt-RTRFI-000130 | 2026-04-13 |  |  |  |  | Response
CCCEGY-RFI-000001 | P0801-K03200-HA-HI-GE-RFI-000003 | 0 | HAC-RFI-000013 | P0801-K03200-HA-HI-GE-RFI-000003 for Hoarding purposed location Sign Board Locations at entrance of Dry Bulk Project. | 2026-04-15 | HillInt-RTRFI-000230 | 2026-04-22 |  |  |  |  | Response
| P0801-K03200-HA-HI-GE-RFI-000004 | 0 | HAC-RFI-000021 | P0801-K03200-HA-HI-GE-RFI-000004 For Dry Bulk Project Signage Layout & Formatting At Entrance of Dry bulk Project. | 2026-04-30 | HillInt-RTRFI-000351 | 2026-05-05 |  |  |  |  | Response
| P0801-K03200-HA-HI-GE-RFI-000005 | 0 | HAC-RFI-000023 | P0801-K03200-HA-HI-GE-RFI-000005 for Dry Bulk Project Excavation Levels at Proposed Bridges Areas | 2026-05-04 | HillInt-RTRFI-000360 | 2026-05-06 |  |  |  |  | Response
| P0801-K03200-HA-HI-GE-RFI-000005 | 1 | HAC-RFI-000031 | P0801-K03200-HA-HI-GE-RFI-000005-1 for Submission of Existing Average Levels for Bridge Locations (Right, Left & Middle Directions) Rev 01 | 2026-05-14 | HillInt-RTRFI-000534 | 2026-06-11 |  |  |  |  | Response
| P0801-K03200-HA-HI-GE-RFI-000006 | 0 | HAC-RFI-000095 | Clarification Regarding Rock Classification (Rippable / Non-Rippable). | 2026-07-09 | HillInt-RTRFI-000838 | 2026-07-21 |  |  |  |  | Response
| P0801-K03200-HA-HI-ST-RFI-000007 | 0 | HAC-RFI-000163 | Clarification of Rough Grading Level and Access Road Requirements VVIP PLOT (OD01 EAST BEACH). | 2026-08-17 | [6 empty] | open