## INFRA
Request For Information Log form INFRA Project | [11 empty] | ALL | 154
[12 empty] | Response | 147
Hassan Allam TO HILL | [5 empty] | Hill to Hassan Allam |  | Dewan to hill |  | hill TO CCC |  | open | 7
Mail No | RFI NO | REV | Mail No | Subject | Date | Mail No | Date | Mail No | Date | Mail No | Date
CCCEGY-RFI-000001 | P000-K03048-HA-HI-RW-RFI-000001 | 00 | HAC-RFI-000001 | P000-K03048-HA-HI-RW-RFI-000001-Clarification on Super-elevation for Horizontal Curve at Station 29+400 | 2026-02-19 | HillInt-RTRFI-000024 | 2026-03-02 |  |  |  |  | Response
CCCEGY-RFI-000002 | P000-K03048-HA-HI-RW-RFI-000002 | 00 | HAC-RFI-000002 | Clarification on Earthworks Limits and Final Grading Levels for Sidewalk & Utility Corridor | 2026-02-19 | HillInt-RTRFI-000004 | 2026-02-25 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000002 | 01 | HAC-RFI-000006 | Clarification on Earthworks Limits and Final Grading Levels for Sidewalk & Utility Corridor | 2026-03-01 | HillInt-RTRFI-000005 | 2026-02-25 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000002 | 02 | HAC-RFI-000111 | Clarification on Earthworks Limits and Final Grading Levels for Sidewalk & Utility Corridor rev (02) | 2026-07-29 | HillInt-RTRFI-000923 | 2026-08-03 |  |  |  |  | Response
CCCEGY-RFI-000003 | P000-K03048-HA-HI-RW-RFI-000003 | 0 | HAC-RFI-000003 | P000-K03048-HA-HI-RW-RFI-000003 -Clarification regarding the pavement layers Extension detail beneath the curbstone | 2026-02-19 | HillInt-RTRFI-000007 | 2026-02-25 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000004 | 0 | HAC-RFI-000004 | P000-K03048-HA-HI-RW-RFI-000004 - Comparison Analysis: Sub-base Design vs. As-Built (Heat Map) | 2026-02-19 | HillInt-RTRFI-000006 | 2026-02-25 |  |  |  |  | Response
|  |  | HAC-RFI-000007 | Re: P000-K03048-HA-HI-RW-RFI-000004 - Comparison Analysis: Sub-base Design vs. As-Built (Heat Map) | 2026-01-03 | HillInt-RTRFI-000278 | 2026-04-26 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000005-00 |  | HAC-RFI-000005 | P000-K03048-HA-HI-GE-RFI-000005-00 - Quantities in B.O.Q for Electrical works | 2026-02-23 | HillInt-RTRFI-000019 | 2026-03-01 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000006-00 |  | P000-K03048-HA-HI-RW-RFI-00006 | P000-K03048-HA-HI-RW-RFI-000006-00 for MS03 Scope Conflict & Land Access Constraints (J7 to J12). | 2026-03-30 | HillInt-RTRFI-000097 | 2026-04-06 |  |  |  |  | Response
|  |  | HAC-GNC-000019 |  | 2026-04-06 | DRAFT-002163 | 2026-04-23 |  |  |  |  | Response
|  |  | P000-K03048-HA-HI-RW-RFI-0006. |  | 2026-04-08 | HillInt-RTRFI-000243 | 2026-04-23
|  |  | HAC-RFI-000016 |  | 2026-04-25 |  | 2026-04-29 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000007-00 |  | P000-K03048-HA-HI-ME-RFI-00007 | P000-K03048-HA-HI-ME-RFI-000007-00 for Missing Finish Floor Levels. | 2026-04-01 | HillInt-RTRFI-000299 | 2026-04-27 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000008-00 |  | P000-K03048-HA-HI-ME-RFI-00008 | P000-K03048-HA-HI-ME-RFI-000008-00 for Missing Connection Level and Detail for the Connection between STP-1/STP-3-1/T-1-1/T-2-5 and Irrigation Line. | 2026-04-02 | HillInt-RTRFI-000200 | 2026-04-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000009-00 |  | P000-K03048-HA-HI-ME-RFI-00009 | P000-K03048-HA-HI-ME-RFI-000009-00 for Missing Connection Level and Detail for the Connection between RO Water tank (RO-1) and Potable Water Line | 2026-04-02 | HillInt-RTRFI-000201 | 2026-04-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000010-00 | 00 | P000-K03048-HA-HI-ME-RFI-00010 | P000-K03048-HA-HI-ME-RFI-000010-00 for Missing Sediment Trap Item in BOQ and Missing Detail and Geometry. | 2026-04-02 | HillInt-RTRFI-000202 | 2026-04-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000011-00 |  | P000-K03048-HA-HI-ME-RFI-00011 | P000-K03048-HA-HI-ME-RFI-000011-00 for Missing Manhole with Flooding Sensor typical Detail and Missing item in BOQ for the Manhole with Flooding Sensor. | 2026-04-02 | HillInt-RTRFI-000240 | 2026-04-23 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000012-00 |  | P000-K03048-HA-HI-ST-RFI-00012 | P000-K03048-HA-HI-ST-RFI-000012-00 for Missing structure detail for box culvert with full Concrete Dimensions and Sections. | 2026-04-02 | HillInt-RTRFI-000588 | 2026-06-22 |  |  |  |  | Response | send to shaker | Reminder to shaker 27 April 2026 | Reminder to shaker 27 April 2026
| P000-K03048-HA-HI-ME-RFI-000013-00 |  | P000-K03048-HA-HI-ME-RFI-00013 | P000-K03048-HA-HI-ME-RFI-000013-00 for Missing Connection Point Level and location between storm main line and box culvert. | 2026-04-02 | HillInt-RTRFI-000203 | 2026-04-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000014-00 |  | P000-K03048-HA-HI-ST-RFI-00014 | P000-K03048-HA-HI-ST-RFI-000014-00 for Missing Structure Design Details for all valve chambers (PW and IRR and Forced Main). | 2026-04-02 | HillInt-RTRFI-000386 | 2026-05-13 |  |  |  |  | Response | send to shaker | Reminder to shaker 21 April 2026 | Reminder to shaker 27 April 2026
| P000-K03048-HA-HI-GE-RFI-000015-00 |  | HAC-RFI-000009 | P000-K03048-HA-HI-GE-RFI-000015-00 for Gravity Networks Ductile Iron Covers Logo Design | 2026-04-04 | HillInt-RTRFI-000219 | 2026-04-21 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000015-00 |  | P000-K03048-HA-HI-GE-RFI-0015 |  | 2026-04-04
| P000-K03048-HA-HI-ME-RFI-000016-00 |  | P000-K03048-HA-HI-ME-RFI-00016 | P000-K03048-HA-HI-ME-RFI-000016-00 For Catch Basins are Located in the High Points of Road. | 2026-04-06 | HillInt-RTRFI-000204 | 2026-04-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000017-00 |  | P000-K03048-HA-HI-ME-RFI-00017 | P000-K03048-HA-HI-ME-RFI-000017-00 For Irrigation Network 12m difference between the Main Line and the Connection with the Tank. | 2026-04-06 | HillInt-RTRFI-000291 | 2026-04-27 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000018-00 |  | P000-K03048-HA-HI-ME-RFI-00018 | P000-K03048-HA-HI-ME-RFI-000018-00 For Sewage network distance between manholes Ring Road – Overall Layout. | 2026-04-09 | HillInt-RTRFI-000293 | 2026-04-27 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000019-00 |  | P000-K03048-HA-HI-ME-RFI-00019 | P000-K03048-HA-HI-ME-RFI-000019-00 For Sewage network pipe cover Ring Road – Overall Layout. | 2026-04-09 | HillInt-RTRFI-000292 | 2026-04-27 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000020-00 |  | HAC-RFI-000011 | P000-K03048-HA-HI-ST-RFI-000020 for Fence Relocation with 1m Offset from ROW (Station 22+800 to 12+900) For Ring Road Overall Layout. | 2026-04-13 | HillInt-RTRFI-000269 | 2026-04-26 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000021-00 |  | HAC-RFI-000012 | P000-K03048-HA-HI-GE-RFI-000021 for Hoarding purposed location for Sign Board Locations at entrance of Infra Project. | 2026-04-15 | HillInt-RTRFI-000229 | 2026-04-22 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000022-00 |  | HAC-RFI-000014 | P000-K03048-HA-HI-ME-RFI-000022 For Change in Valves & Special Fitting PN From 16 to 20 (PW and IRR and Forced Main). | 2026-04-20 | HillInt-RTRFI-000296 | 2026-04-27 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000023-00 |  | HAC-RFI-000015 | P000-K03048-HA-HI-GE-RFI-000023 For Request to Review and Approval for the Structural Design three Project signboard (Main, Directional & Site Safety). | 2026-04-23 | HillInt-RTRFI-000281 | 2026-04-26 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000023-01 |  | HAC-RFI-000017 | Re: Kindly find attached outgoing RFI from HAC to HILL Ref. P000-K03048-HA-HI-GE-RFI-000023 For Request to Review and Approval for the Structural Design three Project signboard (Main, Directional & Site Safety). Rev01 | 2026-04-28 | HillInt-RTRFI-000344 | 2026-05-04 |  |  |  |  | Response | Mr Tamer Elsayed
| P000-K03048-HA-HI-ME-RFI-000024 |  | HAC-RFI-000018 | P000-K03048-HA-HI-ME-RFI-000024 for Discrepancy in Centerline Levels for the Outside Area (Reference to RFI No. 7). | 2026-04-28 | HillInt-RTRFI-000407 | 2026-05-18 |  |  |  |  | Response | send to shaker
| P000-K03048-HA-HI-ME-RFI-000025 |  | HAC-RFI-000019 | P000-K03048-HA-HI-ME-RFI-000025 for Conflict Between Storm Water IFC Drawings and Existing Culverts on Site. | 2026-04-30 | HillInt-RTRFI-000378 | 2026-05-11 |  |  |  |  | Response | send to Shaker HillInt-RFI-000216 | send reminder
| P000-K03048-HA-HI-GE-RFI-000026 |  | HAC-RFI-000020 | P000-K03048-HA-HI-GE-RFI-000026 for Infra Project Signage Layout & Formatting At Entrance of Infra Project. | 2026-04-30 | [6 empty] | Response | send to hill eng-Ayman El Ghannam to signature 04/05/2026
| P000-K03048-HA-HI-ME-RFI-000027 |  | HAC-RFI-000024 | P000-K03048-HA-HI-ME-RFI-000027 for Clash Between Existing Culverts and Irrigation Main Line. | 2026-05-05 | HillInt-RTRFI-000350 | 2026-05-05 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000028 |  | HAC-RFI-000025 | P000-K03048-HA-HI-ME-RFI-000028 for Clash Between Existing Culverts and Potable Water Main Line. | 2026-05-05 | HillInt-RTRFI-000349 | 2026-05-05 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000029 |  | HAC-RFI-000026 | P000-K03048-HA-HI-BR-RFI-000029 for Hoarding purposed location Infra at Bridge J09. | 2026-05-06 | [6 empty] | Response
| P000-K03048-HA-HI-BR-RFI-000030 |  | HAC-RFI-000027 | P000-K03048-HA-HI-BR-RFI-000030 For Requesting date about the non-Working Pile At Bridge J09. | 2026-05-11 | HillInt-RTRFI-000384 | 2026-05-13 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000031 |  | HillInt-RFI-000275 | P000-K03048-HA-HI-BR-RFI-000031 For Steel Reinforcement Grade Clarification At Bridge J09. | 2026-05-11 | [6 empty] | Response
| P000-K03048-HA-HI-BR-RFI-000032 |  | HAC-RFI-000029 | P000-K03048-HA-HI-BR-RFI-000032 For Cement Type of Piles Mix Design. | 2026-05-12 | HillInt-RTRFI-000434 | 2026-05-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000033 |  | HAC-RFI-000032 | P000-K03048-HA-HI-ME-RFI-000033 For Concrete Encasement Around Pipes Not Included in BOQ. | 2026-05-14 | HillInt-RTRFI-000398 | 2026-05-17 |  |  |  |  | Response | MOATAZ TAMER
| P000-K03048-HA-HI-ME-RFI-000034 |  | HAC-RFI-000033 | P000-K03048-HA-HI-ME-RFI-000034 For The thrust block for bends Not Included in BOQ. | 2026-05-17 | HillInt-RTRFI-000394 | 2026-05-17 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000035 |  | HAC-RFI-000034 | P000-K03048-HA-HI-ME-RFI-000035 For Catch Basin Section Modification. | 2026-05-17 | HillInt-RTRFI-000435 | 2026-05-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000036 | 00 | HAC-RFI-000035 | P000-K03048-HA-HI-ST-RFI-000036 For Missing Structure Details for Chambers and Culver Box. | 2026-05-18 | HillInt-RTRFI-000608 | 2026-06-24 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ST-RFI-000036 | 01 | HAC-RFI-000066 | Missing Structure Details for Chambers and Culver Box. | 2026-06-25 | HillInt-RTRFI-000612 | 2026-06-25 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000036 | 02 | HAC-RFI-000082 | Missing Structure Details for Chambers and Culver Box. | 2026-07-04 | HillInt-RFI-000629 | 2026-07-05 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000037 |  | HAC-RFI-000043 | P000-K03048-HA-HI-GE-RFI-000037 for Modification of Sign Board location for Infra Project at Entrance of Infra Project. | 2026-05-21 | HillInt-RTRFI-000448 | 2026-05-23 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-ME-RFI-000038 |  | HAC-RFI-000044 | P000-K03048-HA-HI-ME-RFI-000038 for Confirmation of Proposed FGL Levels for Road to STP-01 and RO Water Tank. | 2026-05-23 | HillInt-RTRFI-000466 | 2026-06-01 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000039 |  | HAC-RFI-000045 | P000-K03048-HA-HI-ME-RFI-000039 for Warning Tape clarification for Wet Utilities (overall). | 2026-05-23 | HillInt-RTRFI-000465 | 2026-06-01 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000040 |  | HAC-RFI-000046 | P000-K03048-HA-HI-ME-RFI-000040 for Proposed Box Culverts Clashes (Box Over All Layout). | 2026-05-23 | HillInt-RTRFI-000464 | 2026-06-01 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-EL-RFI-000041 |  | HAC-RFI-000047 | Lighting poles more specifications . | 2026-06-04 | HillInt-RTRFI-000559 | 2026-06-15 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000042 |  | HAC-RFI-000048 | Bridge J09 - Proposal for new cut-off levels for pile caps at axis MB P01, MB P02 and MB P03. | 2026-06-07 | HillInt-RTRFI-000560 | 2026-06-15 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000043 |  | HAC-RFI-000049 | Proposal for Cold - applied bitumen emulsion for waterproofing for Beneath of Pile Cap for All Bridges. | 2026-06-08 | HillInt-RTRFI-000558 | 2026-06-15 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000044 |  | HAC-RFI-000050 | Clarification Required Regarding Utility Design Levels and Existing Ground Levels – STP-1 Access Road. | 2026-06-11 | HillInt-RTRFI-000544 | 2026-06-14 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000045 |  | HAC-RFI-000051 | Clarification on Conflicting Concrete Specifications between Specification [STANDARD CONSTRUCTION SPECIFICATIONS PART 2 ROAD STRUCTURE] and Specification [Primary Infrastructure Package for the Ring Road Volume (2) | 2026-06-12 | HillInt-RTRFI-000567 | 2026-06-17 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-BR-RFI-000046 |  | HAC-RFI-000052 | Request for Clarification & Adjustment of Pile Cut-Off Level for axis MB P04 and MB P05 at bridge J09. | 2026-06-13 | HillInt-RTRFI-000557 | 2026-06-15 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000047 |  | HAC-RFI-000053 | Proposed Box Culverts Modification Ras Elhekma Ring Road station 28+500 & station 19+300. | 2026-06-14 | HillInt-RTRFI-000564 | 2026-06-16 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000048 | 00 | HAC-RFI-000054 | Clarification on Road Crossing Sleeves (Ras Elhekma Ring Road station 28+500 & station 19+300). | 2026-06-16 | HillInt-RTRFI-000589 | 2026-06-22 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000048 | 01 | HAC-RFI-000064 | Clarification on Road Crossing Sleeves (Ras Elhekma Ring Road station 28+500 & station 19+300). | 2026-06-23 | HillInt-RTRFI-000622 | 2026-06-28 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000049 | 00 | HAC-RFI-000055 | Valve Chambers Structure Details Queries(Over All Layout). | 2026-06-17 | HillInt-RTRFI-000654 | 2026-06-29 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-BR-RFI-000050 | 00 | HAC-RFI-000056 | Proposal for Piles to be tested for the Cross Hole Sonic Logging Test (CSL) at bridge J09 main bridge from MB-P01 to MB-P05. | 2026-06-17 | HillInt-RTRFI-000579 | 2026-06-21 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000051 | 00 | HAC-RFI-000062 | Request for confirmation of using mass concrete at pile caps only (All Bridges). | 2026-06-22 | HillInt-RTRFI-000626 | 2026-06-28 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000051 | 01 | HAC-RFI-000103 | Request for Confirmation of Execution Mass Concrete for Pile Cap only for all Junctions. (Rev.01) | 2026-07-20 | HillInt-RTRFI-000861 | 2026-07-27 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-BR-RFI-000051 | 02 | HAC-RFI-000142 | Request for Confirmation of using Mass Concrete for Pile Caps only(All Bridges/Junctions) (Rev.02) | 2026-08-05 | HillInt-RTRFI-000969 | 2026-08-09 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000052 | 00 | HAC-RFI-000063 | Review and Approval of the Alignment, Profile, and Proposed Typical Section for Utility Route Backfilling Corridor to STP1(Ring Road -East Zone – General) | 2026-06-22 | HillInt-RTRFI-000676 | 2026-07-01 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-RW-RFI-000052 | 01 | HillInt-RFI-000658 | Review and Approval of the Alignment, Profile, and Proposed Typical Section for Utility Route Backfilling Corridor to STP1(Ring Road -East Zone – General) | 2026-07-06 | HillInt-RTRFI-000919 | 2026-08-03 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000053 | 00 | HAC-RFI-000065 | Clarification of Operating Pressure and Request for Design Report (Over All ). | 2026-06-23 | HillInt-RTRFI-000656 | 2026-06-30 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000053 | 01 | HAC-RFI-000079 | Clarification of Operating Pressure and Request for Design Report (Over All ). | 2026-07-01 | HillInt-RTRFI-000790 | 2026-07-14 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000054 | 00 | HAC-RFI-000067 | Clarification of HDPE Conduit Specification for Road Crossings Sleeves. | 2026-06-25 | HillInt-RTRFI-000703 | 2026-07-06 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-EL-RFI-000054 | 01 | HAC-RFI-000094 | Clarification of HDPE Conduit Specification for Road Crossings Sleeves. | 2026-07-09 | HillInt-RTRFI-000813 | 2026-07-16 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000055 | 00 | HAC-RFI-000068 | Landscape Design Required for Recessed Manhole Covers. | 2026-06-25 | HillInt-RTRFI-000811 | 2026-07-16 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-EL-RFI-000056 | 00 | HAC-RFI-000070 | Discrepancy in LV Feeder Cable Size Between IFC Drawings and BOQ (Over All). | 2026-06-25 | HillInt-RTRFI-000627 | 2026-06-28 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000057 | 00 | HAC-RFI-000071 | Requesting the Use of CEM III in Pile Concrete Mix Design for JN 09 (Bridges J09). | 2026-06-25 | HillInt-RTRFI-000679 | 2026-07-01 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-BR-RFI-000058 | 00 | HAC-RFI-000072 | Requested evidence for GGBS material & CEM III proposed mix design. | 2026-06-25 | HillInt-RTRFI-000678 | 2026-07-01 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-EL-RFI-000059 | 00 | HAC-RFI-000074 | Scope Clarification – MV Feeder Connection Over All Infra. | 2026-06-29 | HillInt-RTRFI-000814 | 2026-07-16 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000060 | 00 | HAC-RFI-000075 | Clarification of Ductile Iron Cover Load Rating for Valve Chambers (Over All). | 2026-06-30 | HillInt-RTRFI-000667 | 2026-06-30 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000060 | 01 | HAC-RFI-000078 | Clarification of Ductile Iron Cover Load Rating for Valve Chambers (Over All). | 2026-07-01 | HillInt-RTRFI-000691 | 2026-07-05 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000061 | 00 | HAC-RFI-000076 | Confirmation list of Piles for Cross Hole Sonic Logging Testing (CSL) at bridge J09 main bridge At MB-A01 and MB-A02. | 2026-06-30 | HillInt-RTRFI-000828 | 2026-07-19 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000062 | 00 | HAC-RFI-000077 | Proposed Location of Civil Defense Station. | 2026-06-30 | HillInt-RTRFI-000680 | 2026-07-01 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000062 | 01 | HillInt-RFI-000662 | Proposed Location of Civil Defense Station. | 2026-07-07 | HillInt-RTRFI-000770 | 2026-07-13 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000063 | 00 | HAC-RFI-000083 | Request for Box Culvert Extension Design (Over All). | 2026-07-04 | HillInt-RTRFI-000796 | 2026-07-15 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000063 | 01 | HAC-RFI-000104 | Request for Box Culvert Extension Design (Over All). | 2026-07-20 | HillInt-RTRFI-000856 | 2026-07-26 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-ST-RFI-000063 | 01 | HAC-RFI-000108 | Request for Box Culvert Extension Design (Over All). | 2026-07-28 | HillInt-RTRFI-000925 | 2026-08-03 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000064 | 00 | HAC-RFI-000084 | Discrepancy Between Geotechnical Report by EGEC and Project Final Specifications for Pile Settlement Limits (Particular Specs. ) (Bridge 09). | 2026-07-05 | HillInt-RTRFI-000748 | 2026-07-09 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000065 | 00 | HAC-RFI-000085 | Requesting Clarification of Bridge Deck Slab Waterproofing Membrane Thickness . | 2026-07-05 | HillInt-RTRFI-000786 | 2026-07-13 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000066 | 00 | HAC-RFI-000086 | Clarification of Washout Valve Chamber Drainage Arrangement and Discharge Method (Over All). | 2026-07-06 | HillInt-RTRFI-000742 | 2026-07-09 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000067 | 00 | HAC-RFI-000087 | Approval of DWC HDPE Pipe Installation Arrangement Between Gravity Manholes. | 2026-07-06 | HillInt-RTRFI-000741 | 2026-07-09 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000068 | 00 | HAC-RFI-000090 | Clarification Regarding Sewer Pipeline Levels at Box Culvert Crossing (Over All). | 2026-07-07 | HillInt-RTRFI-000724 | 2026-07-07 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000069 | 00 | HAC-RFI-000093 | Confirmation of Final Spherical Bearing Design Load of Bridge J09. | 2026-07-08 | HillInt-RTRFI-000785 | 2026-07-13 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000070 | 00 | HAC-RFI-000096 | Clarification on Load Test Criteria for Non-Working Pile of Bridge J10. | 2026-07-13 | HillInt-RTRFI-000829 | 2026-07-19 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000071 | 00 | HAC-RFI-000098 | Clarification of the Required Number of static load test (non-working piles and working piles) for Bridge J09. | 2026-07-14 | HillInt-RTRFI-000857 | 2026-07-26 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-BR-RFI-000072 | 00 | HAC-RFI-000099 | Subject: Conformation of pile cut off levels and pile caps top level for Axis from MB P01 to MB P05 at Junction 09. | 2026-07-14 | HillInt-RTRFI-000795 | 2026-07-15 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000073 | 00 | HAC-RFI-000100 | Concrete Encasement Requirement for Double Wall Corrugated HDPE Pipes (Over All). | 2026-07-16 | HillInt-RTRFI-000862 | 2026-07-27 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-BR-RFI-000074 | 00 | HAC-RFI-000101 | Request for Approval of Alternative 2.5 mm Thickness for Cross hole sonic test Access Tubes – for piles work. | 2026-07-18 | HillInt-RTRFI-000833 | 2026-07-20 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-BR-RFI-000075 | 00 | HAC-RFI-000102 | Confirmation that the Concrete of Superstructure Elements is considered “Low” permeability level with a maximum limit of RCPT of 2000 coulombs All BRIDGES. | 2026-07-18 | HillInt-RTRFI-000836 | 2026-07-20 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-ST-RFI-000076 | 00 | HAC-RFI-000107 | Clarification of Plain Concrete Grade for Catch Basin and Manholes Over All . | 2026-07-27 | HillInt-RTRFI-000892 | 2026-07-29 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000077 | 00 | HAC-RFI-000109 | Proposed Culvert at St.13+500 Level Modification to Resolve Conflict with Proposed 1200mm Potable Water Pipeline (Ring Road) | 2026-07-29 | HillInt-RTRFI-001002 | 2026-08-12 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-El-RFI-000078 | 00 | HAC-RFI-000110 | Clarification of Installation Method for CCTV Panel Outgoing Feeder Cables to Smart Poles and Emergency Points (Ring Road) | 2026-07-29 | HillInt-RTRFI-000962 | 2026-08-06 |  |  |  |  | Response | send to hill eng-Ayman El Ghannam
| P000-K03048-HA-HI-ME-RFI-000079 | 00 | HAC-RFI-000114 | Clarification of Installation Method for 110 mm UPVC Duct Line with 4 × 32 mm HDPE Sub-Ducts. | 2026-07-30 | HillInt-RTRFI-000970 | 2026-08-09 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000080 | 00 | HAC-RFI-000115 | Proposed Foundation Design for 20 m Lighting Poles (Over All). | 2026-07-30 | HillInt-RTRFI-001187 | 2026-08-31 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000081 | 00 | HAC-RFI-000116 | Discrepancy between the Right & Left Side for New Jersey Barrier in terms of the Architectural Design of Barrier & Barrier Details for Main Bridge of Junction 09. | 2026-07-30 | HillInt-RTRFI-000945 | 2026-08-05 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000082 | 00 | HAC-RFI-000128 | Proposed Modification of Sewage Pipeline Alignment at Existing Box Culverts. | 2026-08-03 | HillInt-RTRFI-000968 | 2026-08-09 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000082 | 01 | HAC-RFI-000170 | Proposed Modification of Sewage Pipeline Alignment at Existing Box Culverts. | 2026-08-19 | HillInt-RTRFI-001226 | 2026-09-02 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-EL-RFI-000083 | 00 | HAC-RFI-000129 | Clarification of DALI Cable Size and Quantity for Street Lighting Control System. | 2026-08-03 | HillInt-RTRFI-001043 | 2026-08-19 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000084 | 00 | HAC-RFI-000138 | Proposed Precast Design for Sewage and Stormwater Manholes. | 2026-08-03 | HillInt-RTRFI-001022 | 2026-08-17 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000084 | 01 | HAC-RFI-000169 | Proposed Precast Design for Sewage and Stormwater Manholes. | 2026-08-20 | HillInt-RTRFI-001201 | 2026-09-01 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000085 | 00 | HAC-RFI-000140 | Requesting for using Cement Type CEMIII/A (OPC+ 50% GGBS) instead of Cement Type CEMIII/B (OPC+ 65% GGBS) for all Reinforced Concrete Elements. | 2026-08-04 | HillInt-RTRFI-000949 | 2026-08-06 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000086 | 00 | HAC-RFI-000141 | Proposed Change of DWC HDPE Pipe Diameter from 1100 mm to 1200 mm (Over All) | 2026-08-04 | HillInt-RTRFI-000967 | 2026-08-09 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000087 | 00 | HAC-RFI-000143 | Overlap Between Executed Non-Working Test Pile and Pile Cap at Axis MB-P03 at Junction 10. | 2026-08-05 | HillInt-RTRFI-001004 | 2026-08-12 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-ME-RFI-000088 | 00 | HAC-RFI-000145 | Insufficient Pipe Cover at Potable Water Crossings above Existing Box Culverts. | 2026-08-05 | HillInt-RTRFI-001003 | 2026-08-12 |  |  |  |  | Response | send to Shaker
| P000-K03048-HA-HI-BR-RFI-000089 | 00 | HAC-RFI-000147 | Proposed Piles for Cross Hole Sonic Logging (CSL) Testing – Bridge J09 U Turn 2 from Axis (U2-A1) to Axis (U2-A2) | 2026-08-10 | HillInt-RTRFI-001016 | 2026-08-16 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000090 | 00 | HAC-RFI-000148 | Proposed Piles for Cross Hole Sonic Logging (CSL) Testing – Bridge J09 U Turn 1 From Axis (U1-A1) to Axis (U1-A2) | 2026-08-10 | HillInt-RTRFI-001017 | 2026-08-16 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000091 | 00 | HAC-RFI-000149 | Proposed Piles for Cross Hole Sonic Logging (CSL) Testing – Bridge J10 Main Bridge from Axis (MB-A1) to Axis (MB-A2). | 2026-08-10 | HillInt-RTRFI-001020 | 2026-08-16 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000092 | 00 | HAC-RFI-000150 | Proposed Piles for Cross Hole Sonic Logging (CSL) Testing – Bridge J05 Main Bridge from Axis (MB-A1) to Axis (MB-A2). | 2026-08-10 | HillInt-RTRFI-001056 | 2026-08-20 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000093 | 00 | HAC-RFI-000151 | Proposed Piles for Cross Hole Sonic Logging (CSL) Testing – Bridge J03 Main Bridge from Axis (MB-A1) to Axis (MB-A2). | 2026-08-11 | HillInt-RTRFI-001019 | 2026-08-16 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000094 | 00 | HAC-RFI-000152 | Clarification on Installation Method of Telecom Micro-Ducts – Direct Buried vs. Inside 110 mm UPVC Conduit. | 2026-08-11 | HillInt-RTRFI-001018 | 2026-08-16 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000095 | 00 | HAC-RFI-000153 | Request for Updated Vendor List. | 2026-08-11 | HillInt-RTRFI-001007 | 2026-08-13 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000096 | 00 | HAC-RFI-000154 | Confirmation of Backfilling and Testing Sequence for Gravity Pipelines (Over All). | 2026-08-12 | HillInt-RTRFI-001015 | 2026-08-16 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000097 | 00 | HAC-RFI-000162 | Clarifications and Confirmations Required for IFC Road Drawings (Interchanges Package) - New Jersey Barriers, Curb stone Details, and Site Boundaries. | 2026-08-16 | HillInt-RTRFI-001191 | 2026-08-31 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-RW-RFI-000097 | 01 | HAC-RFI-000222 | Clarifications and Confirmations Required for IFC Road Drawings (Interchanges Package) - New Jersey Barriers, Curb stone Details, and Site Boundaries. | 2026-09-21 | [6 empty] | open
| P000-K03048-HA-HI-EL-RFI-000098 | 00 | HAC-RFI-000164 | Clarification on Installation Method of Telecom Micro-Ducts – Direct Buried vs. Inside 110 mm UPVC Conduit – Response. | 2026-08-18 | HillInt-RTRFI-001161 | 2026-08-31 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000099 | 00 | HAC-RFI-000165 | Clarification on Design Layout Overlapping Outside Project Right-of-Way (R.O.W.) Limits for Junctions J03 & J05. | 2026-08-18 | HillInt-GNC-003236 | 2026-09-08 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-ME-RFI-000100 | 00 | HAC-RFI-000167 | Proposed Colors and Markings for Underground Warning Tapes for Wet &Dry Utilities | 2026-08-19 | HillInt-RTRFI-001065 | 2026-08-20 |  |  |  |  | Response
| P000-K03048-HA-HI-ME-RFI-000101 | 00 | HAC-RFI-000173 | Proposed Modification of Stormwater Catch basin cover Design. | 2026-08-24 | HillInt-RTRFI-001203 | 2026-09-01 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000102 | 00 | HAC-RFI-000174 | Discrepancy in Bearing Centerlines Spacing at Abutment Axis MB-A1&MB-A2 at Junction 09 | 2026-08-30 | HillInt-RTRFI-001227 | 2026-09-02 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000103 | 00 | HAC-RFI-000175 | Site Obstacles for Execution of Non-working Piles Nos. 2, 3, & 4 of Junction J09 | 2026-08-30 | HillInt-GNC-003192 | 2026-09-07 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000103 | 01 | HAC-RFI-000204 | Site Obstacles for Execution of Non-working Piles Nos. 2, 3, & 4 of Junction J09 | 2026-09-10 | HillInt-GNC-004002 | 2026-09-21 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000104 | 00 | HAC-RFI-000176 | Discrepancy in the number of Pier Reinforcement bars between Pier Elevation Reinforcement Details and Section of the mentioned Drawings for the same Element at Junctions J03, J09 & J10 | 2026-08-30 | HillInt-RTRFI-001233 | 2026-09-03 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-RW-RFI-000105 | 00 | HAC-RFI-000177 | Follow-up Queries for Same Road Design (Interchange package). | 2026-08-30 | HillInt-GNC-003415 | 2026-09-09 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000106 | 00 | HAC-RFI-000180 | Request for Structural Reinforcement Details for Median Barrier (Newjersy) under Junctions Applies protection to Piers – All Junctions. | 2026-09-01 | [6 empty] | open | Send to Shaker
| P000-K03048-HA-HI-EL-RFI-000107 | 00 | HAC-RFI-000181 | Confirmation of Proposed Cable Trench Detail for LV & MV Cables in The Same 1m Utility Corridor (Ring Road). | 2026-09-01 | HillInt-GNC-003432 | 2026-09-10 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000108 | 00 | HAC-RFI-000182 | Request for MSE WALL DETAILS AT MAIN BRIDGES ABUTMENTS Drawing for Junction 05 | 2026-09-02 | [6 empty] | open | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000109 | 00 | HAC-RFI-000183 | Constructability Concerns & Proposed Realignment of Front MSE Wall at Abutment for all Junctions. | 2026-09-02 | HillInt-GNC-004459 | 2026-09-30 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-RW-RFI-000110 | 00 | HAC-RFI-000184 | Confirmation of Proposed Fence Relocation Following Approved Grading Revision. | 2026-09-02 | HillInt-GNC-003193 | 2026-09-07 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000110 | 01 | HAC-RFI-000216 | Confirmation of Proposed Fence Relocation Following Approved Grading Revision. | 2026-09-13 | HillInt-GNC-004314 | 2026-09-28 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000110 | 02 | HAC-RFI-000258 | Confirmation of Proposed Fence Relocation Following Approved Grading Revision. | 2026-10-05 | HillInt-GNC-005009 | 2026-10-11 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000111 | 00 | HAC-RFI-000185 | Request for Approval of Alternative Kerbstone Dimensions. | 2026-09-02 | HillInt-GNC-003430 | 2026-09-10 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000112 | 00 | HAC-RFI-000202 | Clarification & Relaxation Request for Maximum Concrete Core Temperature Limit (ACI 301M-20- 8.1.3) for Mass Concrete Element for all Junctions. | 2026-09-09 | HillInt-GNC-003606 | 2026-09-14 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000113 | 00 | HAC-RFI-000215 | Clarification of Pull Box Size and Dimensions Security System (Ring Road). | 2026-09-14 | HillInt-GNC-004399 | 2026-09-29 |  |  |  |  | Response | Send to Shaker
| P000-K03048-HA-HI-RW-RFI-000114 | 00 | HAC-RFI-000217 | Approval Request for Asphalt Job Mix Formulas (Binder & Wearing Courses) and Optimum Bitumen Content Clarification. | 2026-09-15 | HillInt-GNC-004209 | 2026-09-27 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000115 | 00 | HAC-RFI-000219 | Clarifications and Confirmations Required for IFC Road Drawings (Interchanges Package) - Request for Clarification Regarding Fill Limits and MSE Wall Scope at Junction Areas & Ring Road Typical X-Sec. note. | 2026-09-17 | HillInt-GNC-004091 | 2026-09-23 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000116 | 00 | HAC-RFI-000220 | Clarification of Bedding, Soil Replacement and Geotextile Requirements for DI and DWC HDPE Pipelines (Ring Road). | 2026-09-17 | HillInt-GNC-004305 | 2026-09-28 |  |  |  |  | Response
| P000-K03048-HA-HI-ST-RFI-000117 | 00 | HAC-RFI-000221 | Confirmation of Concrete Grades for Pre-Cast Fence Wall and Foundation (REH South Fence) | 2026-09-21 | HillInt-GNC-004166 | 2026-09-24 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000118 | 00 | HAC-RFI-000228 | Request for Clarification Regarding the Relocation of the Existing Fence. | 2026-09-23 | HillInt-GNC-004460 | 2026-09-30 |  |  |  |  | Response
| P000-K03048-HA-HI-El-RFI-000119 | 00 | HAC-RFI-000229 | SCADA System Coordination with Wet Utilities IFC and Shop Drawings – Zone 2. | 2026-09-24 | HillInt-GNC-004605 | 2026-10-04 |  |  |  |  | Response
| P000-K03048-HA-HI-GE-RFI-000120 | 00 | HAC-RFI-000244 | Missing Information and Technical Clarifications for Infrastructure Design Review | 2026-09-28 | [6 empty] | open
| P000-K03048-HA-HI-RW-RFI-000121 | 00 | HAC-RFI-000245 | Request for Preliminary Approval for Removal of Existing Concrete Side Slopes Along the Existing Road | 2026-09-28 | HillInt-GNC-004601 | 2026-10-04 |  |  |  |  | Response
| P000-K03048-HA-HI-EL-RFI-000122 | 00 | HAC-RFI-000246 | Road Crossing Protection / Concrete Encasement for Telecom & Security Networks. | 2026-09-29 | HillInt-GNC-004599 | 2026-10-04 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000123 | 00 | HAC-RFI-000248 | Request for Flowable Concrete Mix Specifications for Congested Reinforcement in Pile Caps and Piers for all Junctions. | 2026-10-04 | HillInt-GNC-005023 | 2026-10-11 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000124 | 00 | HAC-RFI-000250 | Request for Details of Lifting Jacks at Pier Head (JUNCTION 09) | 2026-10-04 | [6 empty] | open | Send to Shaker
| P000-K03048-HA-HI-RW-RFI-000125 | 00 | HAC-RFI-000254 | Comprehensive Design Review Summary for Junctions. | 2026-10-05 | HillInt-GNC-005021 | 2026-10-11 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000126 | 00 | HAC-RFI-000255 | Discrepancy Between Finished Grade Levels and IFC Road Design Levels at the Intersections. | 2026-10-05 | HillInt-GNC-005019 | 2026-10-11 |  |  |  |  | Response
| P000-K03048-HA-HI-RW-RFI-000127 | 00 | HAC-RFI-000256 | Clarification Regarding Demarcation Plan Issuance and Shop Drawing Preparation. | 2026-10-05 | HillInt-GNC-005017 | 2026-10-11 |  |  |  |  | Response
| P000-K03048-HA-HI-BR-RFI-000128 | 00 | HAC-RFI-000259 | A discrepancy between Grading Finish Levels and Pile Cap Top Levels at MB2 of Junction 03. | 2026-10-06 | [6 empty] | open
| P000-K03048-HA-HI-BR-RFI-000129 | 00 | HAC-RFI-000260 | Approval of the change of Access Doors (Opening) Dimensions & Clarification and approval of the quantity of Openings for each Box-Section Panel for all Junctions | 2026-10-06 | [6 empty] | open | Send to Shaker
| P000-K03048-HA-HI-BR-RFI-000130 | 00 | HAC-RFI-000261 | Clarification on Shear Link Distribution Extent Across Pile Cap (Discrepancy in Section Details) for Pile Cap of Axis (U1-P3) Junction 09 | 2026-10-06 | HillInt-GNC-005011 | 2026-10-11 |  |  |  |  | Response