## MSS
Request For Information Log form West Canal Project |  |  |  |  | REH08253044 Design & Build Main Power Supply Infrastructure for REH Development – Egypt | [7 empty] | ALL | 18
[13 empty] | Response | 15
Seweedy TO HILL | [6 empty] | Hill to Shaker |  | Shaker to Hill |  | Hill to Seweedy |  | Open | 0
Mail No | RFI No | Rev. | Discipline | Mail No | Subject | Date | Mail No | Date | Mail No | Date | Mail No | Date
CCCEGY-RFI-000001 | 1212- K03044-CN-SEW.RME-RFI-0001 | 00 | Civil | EERM-RFI-000001 | Clarification of MSS1 Exact Coordinates and Orientation | 2026-06-04 | HillInt-RFI-000410 | 2026-06-11 | N/A |  | HillInt-RTRFI-000527 | 2026-06-10 | Response
| 1212- K03044-CN-SEW.RME-RFI-0002 | 00 | All | EERM-RFI-000002 | OHTL scope & MSS3 Clarification | 2026-06-04 | HillInt-RFI-000411 | 2026-06-11 | N/A |  | HillInt-RTRFI-000536 | 2026-06-11 | Response
CCCEGY-RFI-000002 | 1212- K03044-CN-SEW.RME-RFI-0003 | 00 | All | EERM-RFI-000003 | TELECOM Scope | 2026-06-04 | HillInt-RFI-000412 | 2026-06-11 | N/A |  | HillInt-RTRFI-000528 | 2026-06-10 | Response
CCCEGY-RFI-000003 | 1212- K03044-CN-SEW.RME-RFI-0004 | 00 | ARCH | EERM-RFI-000004 | Architectural Zero Level for Buildings at MSS1 & MSS2 & MSS3 | 2026-06-04 | HillInt-RFI-000413 | 2026-06-11 | N/A |  | HillInt-RTRFI-000529 | 2026-06-10 | Response
CCCEGY-RFI-000004 | 1212- K03044-CN-SEW.RME-RFI-0005 | 00 | Survey | EERM-RFI-000005 | HV & MV Cable Routing Design Requirement | 2026-06-04 | HillInt-RFI-000414 | 2026-06-11 | N/A |  | HillInt-RTRFI-000537 | 2026-06-11 | Response
| REH08253044-CN-SEW.RME-RFI-0006 | 00 | ARCH | REH08253044-CN-SEW.RME-RFI-006 | Architectural Zero Level for Buildings at MSS1 & MSS2 & MSS3 | 2026-06-14 |  |  |  |  | HillInt-RTRFI-000894 | 2026-07-29 | Response
| REH08253044-CN-SEW.RME-RFI-0007 | 00 | Survey | EERM-RFI-000006 | HV & MV Cable Routing Design Requirement | 2026-06-17 |  |  | HillInt-RFI-000473 | 2026-06-17 | HillInt-RTRFI-000726 | 2026-08-07 | Response
| 1212- K03044-CN-SEW.RME-RFI-0008 | 00 | Electrical | EERM-RFI-000007 | OHTL scope & MSS3 Clarification | 2026-06-17 |  |  | HillInt-RFI-000472 | 2026-06-17 | HillInt-RTRFI-000577 | 2026-06-21 | Response
| REH08253044-CN-SEW.RME-RFI-0009 | 00 | ARCH | EERM-RFI-000008 | Guidelines and Perspective for Fence of MSS1, MSS2, & MSS3 | 2026-07-08 |  |  |  |  | HillInt-RTRFI-000752 | 2026-07-09 | Response
CCCEGY-RFI-000005 | REH08253044-CN-SEW.RME-RFI-0010 | 00 | ARCH | EERM-RFI-000009 | Proposed Zero Level for MSS1 | 2026-07-12 |  |  |  |  | HillInt-RTRFI-000895 | 2026-07-29 | Response
| REH08253044-CN-SEW.RME-RFI-0011 | 00 | Mech | EERM-RFI-000010 | Tie-in and Tie-out points for all Electrical and MEP networks for MSS1 | 2026-07-19 |  |  |  |  | HillInt-RTRFI-001031 | 2026-08-17 | Response
CCCEGY-RFI-000006 | REH08253044-CN-SEW.RME-RFI-0012 | 00 | Mech | EERM-RFI-000011 | Tie-in and Tie-out points for all Electrical and MEP networks for MSS2 | 2026-07-19 |  |  |  |  | HillInt-RTRFI-001032 | 2026-08-17 | Response
CCCEGY-RFI-000007 | REH08253044-CN-SEW.RME-RFI-0013 | 00 | Mech | EERM-RFI-000012 | Tie-in and Tie-out points for all Electrical and MEP networks for MSS3 | 2026-07-19 |  |  |  |  | HillInt-RTRFI-001033 | 2026-08-17 | Response
CCCEGY-RFI-000008 | REH08253044-CN-SEW.RME-RFI-0014 | 00 | Civil | EERM-RFI-000013 | Request for location of the Approved Public Disposal Site for Excavation | 2026-08-02 |  |  |  |  | HillInt-RTRFI-000954 | 2026-08-06 | Response
CCCEGY-RFI-000009 | REH08253044-CN-SEW.RME-RFI-0015 | 00 | All | EERM-RFI-000014 | High Voltage (HV) and Medium Voltage (MV) cable rou | 2026-09-24 |  |  |  |  | HillInt-GNC-004893 | 2026-10-07 | Response
CCCEGY-RFI-000010
CCCEGY-RFI-000011
CCCEGY-RFI-000057
CCCEGY-RFI-000012
CCCEGY-RFI-000055
CCCEGY-RFI-000013
CCCEGY-RFI-000014
CCCEGY-RFI-000015
CCCEGY-RFI-000067
CCCEGY-RFI-000016
CCCEGY-RFI-000017
CCCEGY-RFI-000018
CCCEGY-RFI-000019
CCCEGY-RFI-000020
CCCEGY-RFI-000068
CCCEGY-RFI-000021
CCCEGY-RFI-000022
CCCEGY-RFI-000023
CCCEGY-RFI-000024
CCCEGY-RFI-000025
CCCEGY-RFI-000026
CCCEGY-RFI-000027
CCCEGY-RFI-000028
CCCEGY-RFI-000029
CCCEGY-RFI-000030
CCCEGY-RFI-000069
CCCEGY-RFI-000031
CCCEGY-RFI-000032
CCCEGY-RFI-000033
CCCEGY-RFI-000038
CCCEGY-RFI-000034
CCCEGY-RFI-000037
CCCEGY-RFI-000035
CCCEGY-RFI-000036
CCCEGY-RFI-000039
CCCEGY-RFI-000040
CCCEGY-RFI-000041
CCCEGY-RFI-000042
CCCEGY-RFI-000043
CCCEGY-RFI-000044
CCCEGY-RFI-000045
CCCEGY-RFI-000046
CCCEGY-RFI-000047
CCCEGY-RFI-000048
CCCEGY-RFI-000049
CCCEGY-RFI-000050
CCCEGY-RFI-000051
CCCEGY-RFI-000052
CCCEGY-RFI-000053
CCCEGY-RFI-000054
CCCEGY-RFI-000056
CCCEGY-RFI-000058
CCCEGY-RFI-000059
CCCEGY-RFI-000060
CCCEGY-RFI-000061
CCCEGY-RFI-000062
CCCEGY-RFI-000063
CCCEGY-RFI-000064
CCCEGY-RFI-000065
CCCEGY-RFI-000066
CCCEGY-RFI-000070
CCCEGY-RFI-000071
CCCEGY-RFI-000072
CCCEGY-RFI-000073
CCCEGY-RFI-000074
CCCEGY-RFI-000075
CCCEGY-RFI-000076
CCCEGY-RFI-000077
CCCEGY-RFI-000078
CCCEGY-RFI-000079
CCCEGY-RFI-000080
CCCEGY-RFI-000081
CCCEGY-RFI-000082
CCCEGY-RFI-000098
CCCEGY-RFI-000099
CCCEGY-RFI-000100
CCCEGY-RFI-000101
CCCEGY-RFI-000083
CCCEGY-RFI-000084
CCCEGY-RFI-000085
CCCEGY-RFI-000086
CCCEGY-RFI-000087
CCCEGY-RFI-000088
CCCEGY-RFI-000089
CCCEGY-RFI-000090
CCCEGY-RFI-000091
CCCEGY-RFI-000092
CCCEGY-RFI-000093
CCCEGY-RFI-000094
CCCEGY-RFI-000095
CCCEGY-RFI-000096
CCCEGY-RFI-000097