## Dashboard
SITE CLARIFICATION LOG DASHBOARD DP01
Automatic summary of Pending and Responded items for every sheet
TOTAL ITEMS |  |  | PENDING |  | RESPONDED
1709 |  |  | 95 |  | 1614
Sheet Name | Total | Pending | Responded | Response Rate
GN | 14 | 3 | 11 | 78.57%
ST | 963 | 36 | 927 | 96.26%
AR | 56 | 6 | 50 | 89.29%
EL | 352 | 22 | 330 | 93.75%
ME | 303 | 25 | 278 | 91.75%
Telecom | 21 | 3 | 18 | 85.71%
GRAND TOTAL | 1709 | 95 | 1614 | 94.44%
GN |  |  | ST |  | AR
Total | 14 |  | Total | 963 | Total | 56
Pending | 3 |  | Pending | 36 | Pending | 6
Responded | 11 |  | Responded | 927 | Responded | 50
EL |  |  | ME |  | Telecom
Total | 352 |  | Total | 303 | Total | 21
Pending | 22 |  | Pending | 25 | Pending | 3
Responded | 330 |  | Responded | 278 | Responded | 18

## GN
Site Clarification Request ( General )
Ref. | Mail No | Rev. | Subject | Sub-Building | Issue Date | Received Date | Action
REH-MD01-MDU-ZZ-OC-Hil-1025-SCR-000001 | REH-MD01-ZZ-OC-Hil-1025-SCR-01 | 0 | REH-MDU - Wadi Yemm - Missing data for Apartments Arch & MEP 50% DD Package at plot 1025 | 1025 | 2026-05-03 | 2026-05-06 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1025-SCR-000002 | OC-SCR-000589 | 0 | REH-MDU - Wadi Yemm - Changing the location of panel board in apartment (Q2-3) - Plot 1025 | 1025 | 2026-07-28 | 2026-08-03 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1044-SCR-000001 | OC-SCR-000659 | 0 | REH-MDU - Wadi Yemm - Dropping slap in spa areas & clash beam with door | 1044 | 2026-08-03 | 2026-08-12 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1031-SCR-000001 | OC-SCR-000690 | 0 | REH-MDU - Wadi Yemm - SCR – Clarification Regarding Electrical and LC Outlets and Devices Mounting Heights in the (Shaker Package) | 1031 | 2026-08-06 | 2026-08-10 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1031-SCR-000002 | OC-SCR-000691 | 0 | REH-MDU - Wadi Yemm - SCR – Clarification Regarding the Mounting Heights of Electrical and ELV Devices Inside the Elevator Shaft (Shaker Package | 1031 | 2026-08-06 | 2026-08-11 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1044-SCR-000002 | OC-SCR-000713 | 0 | REH-MDU - Wadi Yemm - beam with wall arch & clash wall arch & str | 1044 | 2026-08-09 | 2026-08-17 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1021-SCR-000001 | OC-SCR-000731 | 0 | REH-MDU - Wadi Yemm - Changing the location of panel board in apartment (Q3-3BHK) - Plot 1021 | 1021 | 2026-08-09 | 2026-08-22 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1024-SCR-000001 | OC-SCR-000791 | 0 | REH-MDU - Wadi Yemm - Clarification Regarding the Mounting Heights of Electrical and ELV Devices Inside the Elevator Shaft (ECG Package) | 1024 | 2026-08-13 | 2026-08-19 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1044-SCR-000003 | OC-SCR-000954 | 0 | REH-MDU - Wadi Yemm - Staircase Coordination Clarification | 1044 | 2026-08-26 | 2026-09-09 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1025-SCR-000003 | OC-SCR-001170 | 0 | REH-MDU - Wadi Yemm - Plot 1025- MEP Openings in beams | 1025 | 2026-09-15 | 2026-09-16 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1044-SCR-000004 | OC-SCR-001321 | 0 | REH-MDU - Wadi Yemm - Column Alignment at the Slab Edge and Omission of Beam CA3 | 1044 | 2026-09-24 | 2026-09-27 | Responded
REH-MD01-MDU-ZZ-OC-Hil-1021-SCR-000002 | OC-SCR-001366 | 0 | REH-MDU - Wadi Yemm - Plot 1021 -Ground level -Attic Slab-part 04 | 1021 | 2026-09-30 |  | Pending
REH-MD01-MDU-SS-OC-Hil-1018-SCR-000029 | OC-SCR-001419 | 0 | REH-MD01-MDU-SS-OC-Hil-1018-SCR-000029 - Corridor CCTV Coverage Not Complete - PLOT#1018 - FIRST FLOOR | 1081 | 2026-10-05 |  | Pending
REH-MD01-MDU-ZZ-OC-Hil-1031-SCR-000003 | OC-SCR-001434 | 0 | REH-MD01-MDU-ZZ-OC-Hil-1031-SCR-000003-SP02-Plot 1031,1032,1033 FOR all typical stair RFT detail. (Missing Reinforcement Details) | 1031 | 2026-10-06 |  | Pending
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Ras Al Hekma Cape, Egypt.
Employer:- MoDon.
Lead Consultant:- SHAKER & ECG

## ST
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Northern coast near Ras Al Hekma Cape, Egypt. |  |  |  | Site Clarification Request ( Structural )
Employer:- Modon.
Lead Consultant:- SHAKER & ECG | Ref. | Mail No | Rev. | Subject | Sub-Building | Issue Date | Received Date | Action
| P0155-RA06-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and discrepancy at plot 1024 | RA06 | 2025-12-21 | 2025-12-22 | Responded
| P0155-RA06-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and discrepancy (2) at plot 1024 | RA06 | 2025-12-22 | 2025-12-26 | Responded
| P0155-RA04-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and discrepancy at plot 1025 | RA04 | 2025-12-23 | 2025-12-24 | Responded
| P0155-RA00-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Cement Type for Concrete Materials (Wadi Yemm Project) | RA00 | 2025-12-23 |  | Pending
| P0155-RA06-SCR-ST-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Discrepancy Between StructuraL and Architectural Drawings plot 1024 | RA06 | 2025-12-25 | 2025-12-27 | Responded
| P0155-RA04-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and discrepancy (2) at plot 1025 | RA04 | 2025-12-27 | 2025-12-29 | Responded
| P0155-RA06-SCR-ST-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center -Missing data and conflicts in columns (1) in plot 1024 | RA06 | 2025-12-28 | 2025-12-30 | Responded
| P0155-RA06-SCR-ST-OC-DAR-000005 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and conflicts in columns (2) in plot 1024 | RA06 | 2025-12-28 | 2025-12-30 | Responded
| P0155-RA03-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing and Conflict data at plot 1047 | RA03 | 2026-01-05 | 2026-01-11 | Responded
| P0155-RA03-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing and Conflict data at plot 1047 | RA03 | 2026-01-10 | 2026-01-11 | Responded
| P0155-RA06-SCR-ST-OC-DAR-000006 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and conflicts in columns in plot 1024 | RA06 | 2026-01-12 | 2026-06-23 | Responded
| P0155-RA04-SCR-ST-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and discrepancy (3) at plot 1025 COL&SLABS | RA04 | 2026-01-12 | 2026-01-14 | Responded
| P0155-RA05-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing and Conflict data at plot 1026 | RA05 | 2026-01-14 |  | Pending
| P0155-RA06-SCR-ST-OC-DAR-000007 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data and conflicts in plot 1024 | RA06 | 2026-01-21 |  | Pending
| P0155-RA05-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing and Conflict data at plot 1026 | RA05 | 2026-01-28 | 2026-03-25 | Responded
| P0155-RA03-SCR-ST-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data at plot 1047 | RA03 | 2026-02-03 | 2026-02-15 | Responded
| P0155-RA03-SCR-ST-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing data at plot 1047 | RA03 | 2026-02-05 | 2026-02-15 | Responded
| P0155-RA01-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Excavation Level required for area infront of Plot 1036 | RA01 | 2026-02-03 | 2026-03-08 | Responded
| P0155-RA03-SCR-ST-OC-DAR-000005 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Data Conflict in plot 1047 | RA03 | 2026-02-07 | 2026-02-15 | Responded
| P0155-RA07-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Discrepancy and missing data at Drawings supper plot 01 | RA07 | 2026-02-07 | 2026-02-19 | Responded
| P0155-RA07-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Horizontal protection layer and missing axis at supper plot 01 | RA07 | 2026-02-10 | 2026-03-04 | Responded
| P0155-RA04-SCR-ST-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Structure and Archecture details for stairs at plot 1025 | RA04 | 2026-01-12 | 2026-03-05 | Responded
| P0155-RA00-SCR-BM-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Approval to use Revit 2026 | RA00 | 2026-02-14 | 2026-02-27 | Responded
| P0155-RA10-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Levls PC &RC at plot 1021 | RA10 | 2026-02-17 | 2026-02-22 | Responded
| P0155-RA07-SCR-ST-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Super Plot 01 – Discrepancies and Missing Data | RA07 | 2026-02-17 | 2026-03-17 | Responded
| P0155-RA09-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Conflict Data in Plot 1044 | RA09 | 2026-02-17 | 2026-03-10 | Responded
| P0155-RA10-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing and Conflict data at plot 1021 | RA10 | 2026-02-18 | 2026-03-04 | Responded
| P0155-RA02-SCR-ST-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Discrepancy and missing data at Drawings plot 1028 | RA02 | 2026-02-18 | 2026-02-26 | Responded
| P0155-RA02-SCR-ST-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Conflicts at Basement 01 Slab – Plot 1028 | RA02 | 2026-02-18 | 2026-02-26 | Responded
| P0155-RA03-SCR-ST-OC-DAR-000006 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Conflict Data in Plot 1047 | RA03 | 2026-02-19 | 2026-03-04 | Responded
| P0155-RA10-SCR-ST-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Data in Plot 1021 | RA10 | 2026-02-19 | 2026-03-04 | Responded
| P0155-RA04-SCR-ST-OC-DAR-000005 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Column at plot 1036 part 04 | 1036 | 2026-01-12 | 2026-03-02 | Responded
| P0155-RA02-SCR-ST-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Retaining Walls details & cores conflicts – Plot 1028 | RA02 | 2026-02-21 | 2026-02-26 | Responded
| P0155-RA10-SCR-ST-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Data in Plot 1021 | RA10 | 2026-02-22 | 2026-03-04 | Responded
| P0155-RA04-SCR-ST-OC-DAR-000006 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Discrepency in additional reinforcement diameter of Retaining wall at plot 1036 part 02 | 1036 | 2026-02-22 | 2026-03-05 | Responded
| P0155-RA06-SCR-ST-OC-DAR-000008 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - IFC Clarification at plot 1025 | 1025 | 2026-02-24 | 2026-03-04 | Responded
| P0155-RA07-SCR-ST-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Cente Super Plot 01 – Discrepancies and Missing Data | RA07 | 2026-02-25 | 2026-03-06 | Responded
| P0155-RA07-SCR-ST-OC-DAR-000005 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Cente conflict at B1 slab plot 1025 | 1025 | 2026-02-25 | 2026-03-03 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000001 |  | 0 | REH-MD01 - Wadi Yemm - Sea Town Discrepancies in beams & toilet FFL for Plot 1047 | 1047 | 2026-02-26 | 2026-03-04 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-02-28 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Missing Columnns on axis (10) in the design drawing details at plot 1036 | 1036 | 2026-03-02 | 2026-03-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1021-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Missing Section Details For W3)) & Contradiction between (plan &section for Service Pit. | 1021 | 2026-03-02 | 2026-03-04 | Responded
| REH-MD01-MDU-ST-OC-DAR-1022-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Missing setting out plan for super plot 06 | 1022 | 2026-03-03 | 2026-03-11 | Responded
| REH-MD01-MDU-ST-OC-DAR-1021-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Contradiction between (plan &section for Service Pit ) | 1021 | 2026-03-06 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- BEAMS AT STAIRS AREA at plot 1025 | 1025 | 2026-03-06 | 2026-03-15 | Responded
| REH-MD01-MDU-ST-OC-DAR-1028-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- CONFLICT BETWEEN ARCH & STRUCTURE DRAWINGS | 1028 | 2026-03-06 | 2026-03-15 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Discrepancies and Missing Data Regarding columns | 1029 | 2026-03-06 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- conflict between the structural and architectural column &There is a shift between the structural and architectural Axis & The stairs are shown in the architectural drawings but not shown in the structural drawings | 1036 | 2026-03-06 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Discrepancies in Ground Plan for Plot 1047 | 1047 | 2026-03-06 | 2026-03-15 | Responded
| REH-MD01-MDU-ST-OC-DAR-1021-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Tower Crane's Footing in Plot 1021 | 1021 | 2026-03-07 | 2026-03-10 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Levls PC &RC at plot 1044 | 1044 | 2026-03-07 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Conflict in RW plot (1047) | 1047 | 2026-03-08 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Core opennings, stairs, Ramps & Axes descrepancies | 1026 | 2026-03-09 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-XXXX-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Clarification regarding the Internal Waterproofing for Water Tanks | XXXX | 2026-03-09 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1028-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Rienforcment clarification | 1028 | 2026-03-10 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Conflict data at plot 1026 | 1026 | 2026-03-10 | 2026-03-19 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- some missing data regarding the walls&There are missing columns, and some of them conflict with the architectural drawings. | 1036 | 2026-03-11 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- More Clarifications About Additional Reinforcement | 1044 | 2026-03-11 | 2026-03-19 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- STAIR STARTER PLACES at plot 1025 | 1025 | 2026-03-12 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1022-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Missing some RFT details for retaining walls at SP06 | 1022 | 2026-03-12 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Slab-basment01 - beam @10.9 supporting conditions -part1c plot 1025 | 1025 | 2026-03-15 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1028-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Stairs and shear wall at plot 1028 | 1028 | 2026-03-15 | 2026-03-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Discrepancies between Site Excution and Design D4 | 1029 | 2026-03-15 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Shafts, missing RFT & Beams in Plot 1047 | 1047 | 2026-03-15 | 2026-03-26 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Stairs Starter Relocation As Per SCR Reply in Plot 1047 | 1047 | 2026-03-15 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- updated columns double height levels- plot 1025 | 1025 | 2026-03-15 | 2026-03-16 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Conflicts in vertical elements in plot 1024 | 1024 | 2026-03-16 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-1022-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Clarification for Punching detail at SP06 | 1022 | 2026-03-16 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- There is a conflict between the 2D drawings and the 3D drawings, | 1036 | 2026-03-16 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- The wall detail is missing | 1036 | 2026-03-16 | 2026-03-19 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Typical Detail for Retaining Wall - Water Stop | 1029 | 2026-03-16 | 2026-03-17 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Plot area and its coordinates | 1036 | 2026-03-17 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- SHAFTS, DOOR OPENINGS CONFLICT - PLOT 1026 | 1026 | 2026-03-17 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000007 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Missing range for this add RFT | 1036 | 2026-03-17 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- updated columns double height levels- plot 1025 | 1025 | 2026-03-17 | 2026-03-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Clarification on Wall W4 Modification | 1044 | 2026-03-18 | 2026-03-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-XXXX-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Clarification on Waterproofing System Conflict | XXXX | 2026-03-18 | 2026-04-01 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Retaining wall types and raft thickening face. | 1029 | 2026-03-18 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1060-SCR-000001 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- The limits of plot 1060 excavation overlaps with construction road for area 2 & 3 | 1060 | 2026-03-24 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Conflict column location at plot 1026 | 1026 | 2026-03-24 | 2026-04-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Staircase Proposal Including Beams, Openings, and Stair Riser Redistribution – Plot 1025 | 1025 | 2026-03-25 | 2026-03-29 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000008 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Clarify Openings | 1036 | 2026-03-25 | 2026-03-25 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Retaining wall types and raft thickening face. | 1029 | 2026-03-26 | 2026-04-01 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000007 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-03-26 | 2026-04-01 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Stairs Flight width - Plot 1026. | 1026 | 2026-03-26 | 2026-03-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Missing data in basement slab at plot 1026 | 1026 | 2026-03-26 | 2026-04-08 | Responded
| REH-MD01-MDU-ST-OC-DAR-1021-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Missing wall type & required data in Plot 1021 | 1021 | 2026-03-26 | 2026-04-01 | Responded
| REH-MD01-MDU-ST-OC-DAR-XXXX-SCR-000003 | OC-SCR-000013 | 00 | REH-MD01 - Wadi Yemm - Sea Town - Issues for Raft Foundation SP-06 (1045-1018) | XXXX | 2026-03-29 | 2026-04-01 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Conflict in Beam Depth between old and new Design in Plot 1047 | 1047 | 2026-03-30 | 2026-03-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000007 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Removed Column at Plot 1047 Ground Floor | 1047 | 2026-03-31 | 2026-04-02 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000008 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-03-31 | 2026-04-07 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000007 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Conflict data in Stairs at plot 1026 | 1026 | 2026-04-01 | 2026-04-02 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000008 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Missing TYPE Planted Columns at plot 1026 | 1026 | 2026-04-01 | 2026-04-05 | Responded
| REH-MD01-MDU-ST-OC-DAR-XXXX-SCR-00004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - General Details | XXXX | 2026-04-01 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1022-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Carifications at super plot 06 | 1022 | 2026-04-02 | 2026-04-07 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000009 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Missing Parts of the Basement 01 Floor Slab | 1036 | 2026-04-02 | 2026-04-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000009 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town- Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-04 | 2026-04-07 | Responded
| REH-MD01-RLA-ST-OC-DAR-1022-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Missing RWs type at super plot 06 | 1022 | 2026-04-05 | 2026-04-16 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000009 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Shifting Column at plot 1026 | 1026 | 2026-04-06 | 2026-04-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000002 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Stair starters, shafts contradictions & toilet finishes - Plot 1024 - part 02 | 1024 | 2026-04-06 | 2026-04-11 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000010 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Resizing of Sump Pit 04- Part 03 | 1036 | 2026-04-06 | 2026-04-07 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000011 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Updated Column Layout Drawing of Plot 1036 | 1036 | 2026-04-06 | 2026-04-07 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000010 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Conflict Column at plot 1026 | 1026 | 2026-04-06 | 2026-04-11 | Responded
| REH-MD01-RLA-ST-OC-DAR-1022-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Carifications at super plot 06 | 1022 | 2026-04-07 | 2026-04-14 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000003 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Stair starters, shafts & Axis contradictions- Plot 1024 - part 06 | 1024 | 2026-04-07 | 2026-04-11 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue -Zone 10 - 1024 | 1024 | 2026-04-08 | 2026-04-11 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000008 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Models Inquiries in Plot 1047 | 1047 | 2026-04-08 | 2026-04-14 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000011 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Conflict planted Column at plot 1026 | 1026 | 2026-04-08 | 2026-04-11 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000012 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Conflict Expansion joint at plot 1026 | 1026 | 2026-04-08 | 2026-04-12 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000009 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Additional bar position Inquiries in Plot 1047 | 1047 | 2026-04-08 | 2026-04-14 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Stair general details- Plot 1024 | 1024 | 2026-04-09 | 2026-04-14 | Responded
| REH-MD01-MDU-ST-OC-DAR-1021-SCR-000005 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - (Missing columns data & Conflict in plans - in Plot 1021) | 1021 | 2026-04-09 | 2026-04-14 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000006 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Beams Levels contradictions with Slab Levels - Plot 1024 | 1024 | 2026-04-15 | 2026-04-18 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000010 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-15 | 2026-04-20 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000011 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Super Plot 01 – Thickening line confirmation | 1029 | 2026-04-15 | 2026-04-20 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000012 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Missing starter bars for ramps - Plot 1036 | 1036 | 2026-04-15 | 2026-04-16 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000013 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Missing shear wall type - Plot 1036 | 1036 | 2026-04-15 | 2026-04-15 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000004 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Missing Revit Model for Basement Detailed Design Package | 1044 | 2026-04-15 | 2026-04-29 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000010 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Check of Tower crane mast opening through ground slab in Plot 1047. | 1047 | 2026-04-15 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000012 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-15 | 2026-04-20 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000007 |  | 00 | REH-MD01 - Wadi Yemm - Sea Town - Casted columns issue - Shafts contradictions- Plot 1024 | 1024 | 2026-04-15 | 2026-04-20 | Responded
| REH-MD01-RLA-ST-OC-DAR-1022-SCR-000007 |  | 00 | REH-RLA- Wadi Yemm - Sea Town - Casted columns issue - Clarification on RW-2 & RW-3 Thickness and Section Details- SP-06 | 1022 | 2026-04-15 | 2026-04-20 | Responded
| REH-MD01-MDU-ST-OC-DAR-1021-SCR-000006 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Casted columns issue - Shafts discrepancies - Basement 01 - Plot 21 | 1021 | 2026-04-15 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000014 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Casted columns issue - Missing door openings exist in the RFT Details of all cores | 1036 | 2026-04-15 | 2026-04-19 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000005 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Casted columns issue - Discrepancies between the detailed design and the Revit model. | 1044 | 2026-04-16 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000015 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Casted columns issue - Difference in beam model. | 1036 | 2026-04-16 | 2026-04-19 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000016 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Columns shape code | 1036 | 2026-04-19 | 2026-04-19 | Responded
| REH-MD01-RLA-ST-OC-DAR-1022-SCR-000008 | OC-SCR-000016 | 00 | REH-RLA- Wadi Yemm - Sea Town - discrepancies between AXIS in the IFC and sketch 2 in scr 01 | 1022 | 2026-04-19 | 2026-04-20 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000017 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Shear walls RFT Details | 1036 | 2026-04-20 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000018 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - level discrepancy between Beams & Slab | 1036 | 2026-04-20 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000011 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Plot 1047-Part 02- Modification depth of beams (GB09, GCA03& GB15)at Ground floor: | 1047 | 2026-04-20 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1025-SCR-000007 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Clarification at ground floor plan – Plot 1025 | 1025 | 2026-04-20 | 2026-04-21 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000008 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Missing Drawing and Conflicts in Ground Design - Plot 1024 | 1024 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000013 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Conflict Beams of Ramp at plot 1026 | 1026 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000014 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Missing TYPE Planted Columns at plot 1026 | 1026 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000015 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Conflict in ramp location - plot 1026 | 1026 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000019 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Retaining Walls RFT Details | 1036 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000020 |  | 00 | REH-MDU- Wadi Yemm - Sea Town - Difference in beam model. | 1036 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000012 |  | 00 | REH-MDU- Wadi Yemm - Plot 1047-Part 02- zone on grid (CZ, 200: 206) at Ground floor | 1047 | 2026-04-21 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-XXXX-SCR-000005 |  | 00 | REH-MDU- Wadi Yemm - Clarification on Bitumen Protection Course Conflict | XXXX | 2026-04-21 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1036-SCR-000021 |  | 00 | REH-MDU- Wadi Yemm - SHEAR WALLS MISSING DETAILS | 1036 | 2026-04-22 | 2026-04-23 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000009 |  | 00 | REH-MDU- Wadi Yemm - Missing Drawing and Conflicts in Ground Design - Plot 1024 | 1024 | 2026-04-23 | 2026-04-27 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000013 |  | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-23 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1031-SCR-000001 |  | 00 | REH-MDU- Wadi Yemm - Missing & Conflict data at SP02 | 1031 | 2026-04-23 | 2026-05-03 | Responded
| REH-MD01-MDU-ST-OC-DAR-1031-SCR-000002 |  | 00 | REH-MDU- Wadi Yemm - SP02 & Sports Club Boundaries | 1031 | 2026-04-23 | 2026-05-03 | Responded
| REH-MD01-MDU-ST-OC-DAR-1060-SCR-000002 |  | 00 | REH-MDU- Wadi Yemm - Discrepancy between the wall in foundation model &basement model model | 1060 | 2026-04-23 | 2026-04-29 | Responded
| REH-MD01-MDU-ST-OC-DAR-1060-SCR-000003 |  | 00 | REH-MDU- Wadi Yemm - DISCREPANCY BETWEEN MODEL & IFC | 1060 | 2026-04-23 | 2026-04-29 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000014 |  | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Discrepancy in Column Dimensions Between Structural Plan and Column Schedule – Plot 1029 | 1029 | 2026-04-25 | 2026-04-29 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000010 |  | 00 | REH-MDU- Wadi Yemm - Levels contradictions-Ground floor- Plot 1024 | 1024 | 2026-04-26 | 2026-05-03 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000016 |  | 00 | REH-MDU- Wadi Yemm - Shafts contradictions- Plot 1026- basement 01 | 1026 | 2026-04-26 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1060-SCR-000004 |  | 00 | REH-MDU- Wadi Yemm - missing data in IFC package sent 19/04/2026 at plot 1060 | 1060 | 2026-04-27 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-DAR-1060-SCR-000005 |  | 00 | REH-MDU- Wadi Yemm - conflicts in design package at plot 1060 between excavation plan and foundation plan | 1060 | 2026-04-27 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-DAR-1024-SCR-000011 |  | 00 | REH-MDU- Wadi Yemm - Beam Levels contradictions-Ground floor- Plot 1024 | 1024 | 2026-04-27 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000006 | REH-MD01-ST-OC-DAR-1044-SCR-06 | 00 | REH-MDU- Wadi Yemm - Clarification For Beams Level and Elevation | 1044 | 2026-04-27 | 2026-05-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1047-SCR-000013 | REH-MD01-ST-OC-DAR-1047-SCR-13 | 00 | REH-MDU- Wadi Yemm - Plot 1047-Ground floor Construction Joint in slab: | 1047 | 2026-04-27 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1043-SCR-000001 | REH-MD01-ST-OC-DAR-1043-SCR-01 | 00 | REH-MDU- Wadi Yemm - Light house - discrepancy beteen concrete Dimensions and RFT section | 1043 | 2026-04-28 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1043-SCR-000002 | REH-MD01-ST-OC-DAR-1043-SCR-02 | 00 | REH-MDU- Wadi Yemm - Light house - foundation Missing Levels | 1043 | 2026-04-28 | 2026-04-30 | Responded
| REH-MD01-MDU-ST-OC-DAR-1043-SCR-000003 | REH-MD01-ST-OC-DAR-1043-SCR-03 | 00 | REH-MDU- Wadi Yemm - Light house -Column Location Conflict with Raft | 1043 | 2026-04-28 | 2026-05-03 | Responded
| REH-MD01-MDU-ST-OC-DAR-1043-SCR-000004 | REH-MD01-ST-OC-DAR-1043-SCR-04 | 00 | REH-MDU- Wadi Yemm - Light house - Missing Walls in Foundation & Reinforcement Drawings | 1043 | 2026-04-28 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-DAR-1026-SCR-000017 | REH-MD01-ST-OC-DAR-1026-SCR-17 | 00 | REH-MDU- Wadi Yemm - Stair 05 & Ramp combined beams - Basement 01 & Ground floor - Plot 1026 | 1026 | 2026-04-28 | 2026-05-03 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000015 | REH-MD01-ST-OC-DAR-1029-SCR-15 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-28 | 2026-05-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1029-SCR-000016 | REH-MDU-ST-OC-DAR-1029-SCR-16 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Super Plot 01 – Sump inside Elevator Pit | 1029 | 2026-04-28 | 2026-05-05 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000007 | REH-MD01-ST-OC-DAR-1044-SCR-07 | 00 | REH-MDU- Wadi Yemm - Clarification For Attic Slab & slab level | 1044 | 2026-04-28 | 2026-05-06 | Responded
| REH-MD01-MDU-ST-OC-DAR-1044-SCR-000008 | REH-MD01-ST-OC-DAR-1044-SCR-08 | 00 | REH-MDU- Wadi Yemm - Clarification For Missing Top of wall level and Missing Beams Type | 1044 | 2026-04-28 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000001 | REH-MD01-ST-OC-Hil-1021-SCR-01 | 00 | REH-MDU- Wadi Yemm - Slab discrepancies - Basement 01 - Plot 1021 | 1021 | 2026-04-30 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000001 | REH-MD01-ST-OC-Hil-1024-SCR-01 | 00 | REH-MDU- Wadi Yemm - Missing Thickness -Ground floor- Plot 1024 | 1024 | 2026-04-30 | 2026-05-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000001 |  | 00 | REH-MDU- Wadi Yemm - Beam Positioning Clarification | 1026 | 2026-04-30 | 2026-05-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000002 | REH-MD01-ST-OC-Hil-1026-SCR-02 | 00 | REH-MDU- Wadi Yemm - Beam Positioning Clarification | 1026 | 2026-04-30 | 2026-05-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000001 | REH-MD01-ST-OC-Hil-1028-SCR-01 | 00 | REH-MDU- Wadi Yemm - Missing Columns type – Plot 1028- Part 2 | 1028 | 2026-04-30 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000002 |  | 00 | REH-MDU- Wadi Yemm - Stair 5 Upstand Height Clarification– Plot 1028- Part 3 | 1028 | 2026-04-30 | 2026-05-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000003 | REH-MD01-ST-OC-Hil-1028-SCR-03 | 00 | REH-MDU- Wadi Yemm - CLARIFICATION FOR CORRUPTED REVIT FILE | 1028 | 2026-04-30 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000001 | REH-MD01-ST-OC-Hil-1029-SCR-01 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-30 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000002 | REH-MD01-ST-OC-Hil-1029-SCR-02 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Discrepancies and Missing Data | 1029 | 2026-04-30 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000001 | REH-MD01-ST-OC-Hil-1044-SCR-01 | 00 | REH-MDU- Wadi Yemm - Clarification For Punching Details and additional Reinforcement | 1044 | 2026-04-30 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000002 | REH-MD01-ST-OC-Hil-1044-SCR-02 | 00 | REH-MDU- Wadi Yemm - Discrepancy in Wall Thickness (W2) | 1044 | 2026-04-30 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000001 | REH-MD01-ST-OC-Hil-1060-SCR-01 | 00 | REH-MDU- Wadi Yemm - CLARIFICATION FOR EXPANTION LOCATION IN RETAINNG WALL | 1060 | 2026-04-30 | 2026-05-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000002 | OC-SCR-000017 | 00 | REH-MDU- Wadi Yemm - CLARIFICATION FOR FOUNDATION THK. UNDER PITS | 1060 | 2026-04-30 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000001 | REH-MD01-ST-OC-Hil-1025-SCR-01 | 00 | REH-MDU- Wadi Yemm - Clarification at ground floor plan (2) – Plot 1025 | 1025 | 2026-05-02 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000003 | REH-MD01-ST-OC-Hil-1029-SCR-03 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Discrepancy in Column Dimensions Between Structural Plan and Column Schedule – Plot 1029 | 1029 | 2026-05-02 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000001 | REH-MD01-ST-OC-Hil-1047-SCR-01 | 00 | REH-MDU- Wadi Yemm - Plot 1047- Inquiry of TOC levels of the retaining wall behind axis (222), and bet. (CG, and CZ). | 1047 | 2026-05-03 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000003 | REH-MD01-ST-OC-Hil-1060-SCR-03 | 00 | REH-MDU- Wadi Yemm - Missing data in the IFC. Package | 1060 | 2026-05-03 | 2026-05-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000004 | REH-MD01-ST-OC-Hil-1060-SCR-04 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN MODELS | 1060 | 2026-05-03 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000003 | OC-SCR-000018 | 00 | REH-MDU- Wadi Yemm - Plot 1026 - Discrepancies in Ground Floor | 1026 | 2026-05-04 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000002 | REH-MD01-ST-OC-Hil-1024-SCR-02 | 00 | REH-MDU- Wadi Yemm - Clarification For Stair case support | 1024 | 2026-05-05 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000004 | REH-MD01-ST-OC-Hil-1028-SCR-04 | 00 | REH-MDU- Wadi Yemm - [P_1028] Shaft Size & Location Clashes Between Mechanical, Architectural, and Structural Drawings | 1028 | 2026-05-05 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000001 | REH-MD01-ST-OC-Hil-1036-SCR-01 | 00 | REH-MDU- Wadi Yemm - Missing Parts of the Ground Floor Slab. | 1036 | 2026-05-05 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000002 | REH-MD01-ST-OC-Hil-1036-SCR-02 | 00 | REH-MDU- Wadi Yemm - Missing Parts of the Ground Floor Slab. | 1036 | 2026-05-05 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000003 | REH-MD01-ST-OC-Hil-1036-SCR-03 | 00 | REH-MDU- Wadi Yemm - Missing Parts of the Ground Floor Sla | 1036 | 2026-05-05 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000002 | REH-MD01-ST-OC-Hil-1021-SCR-02 | 00 | REH-MDU- Wadi Yemm - Basement 01 levels. | 1021 | 2026-05-06 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000003 | REH-MD01-ST-OC-Hil-1021-SCR-03 | 00 | REH-MDU- Wadi Yemm - discrepancies in RW & Slab - Basement 01 - Plot 1021 | 1021 | 2026-05-06 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000004 | REH-MD01-ST-OC-Hil-1026-SCR-04 | 00 | REH-MDU- Wadi Yemm - Plot 1026 - Combined beams of Ramp from Basement 01 to Ground floor. | 1026 | 2026-05-06 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000005 | REH-MD01-ST-OC-Hil-1026-SCR-05 | 00 | REH-MDU- Wadi Yemm - Openning and missing columns | 1026 | 2026-05-06 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000006 | OC-SCR-000098 | 00 | REH-MDU- Wadi Yemm - Shafts contradictions- Plot 1026- at Ground floor | 1026 | 2026-05-24 | 2026-06-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000004 | REH-MD01-ST-OC-Hil-1029-SCR-04 | 00 | REH-MDU- Wadi Yemm - Missing Column Details | 1029 | 2026-05-06 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000001 | REH-MD01-ST-OC-Hil-1031-SCR-01 | 00 | REH-MDU- Wadi Yemm - Discrepancies in columns,cores,stairs starters and axis -1032&1033 B2 plan- SP02 | 1031 | 2026-05-06 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000004 | REH-MD01-ST-OC-Hil-1036-SCR-04 | 00 | REH-MDU- Wadi Yemm - Conflict between special conditions and general notes on IFC for concrete compressive strength for different elements. | 1036 | 2026-05-06 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000001 | REH-MD01-ST-OC-Hil-1043-SCR-01 | 00 | REH-MDU- Wadi Yemm - Light house - Missing Stair Starter Location | 1043 | 2026-05-06 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000002 | REH-MD01-ST-OC-Hil-1043-SCR-02 | 00 | REH-MDU- Wadi Yemm - Light house - core concrete dimensions discrepancy | 1043 | 2026-05-06 | 2026-05-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000003 | REH-MD01-ST-OC-Hil-1044-SCR-03 | 00 | REH-MDU- Wadi Yemm - Ramp Type, Support Condition & Slope Discrepancy | 1044 | 2026-05-06 | 2026-06-02 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000001 | REH-MD01-ST-OC-Hil-XXXX-SCR-01 | 00 | REH-MDU- Wadi Yemm - Proposal For Links in Punshing Details Ground floor- Plot 1024,1026 | XXXX | 2026-05-06 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000005 | REH-MD01-ST-OC-Hil-1036-SCR-05 | 00 | REH-MDU- Wadi Yemm - Clarification Request Regarding Missing TOC Elevation for the footing marked with a revision cloud | 1036 | 2026-05-09 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000002 | REH-MD01-ST-OC-Hil-1047-SCR-02 | 00 | REH-MDU- Wadi Yemm - Plot 1047- Inquiry of unify of the Bottom levels of part of slabs in 1st, and 2nd Floors. | 1047 | 2026-05-09 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000001 | REH-MD01-ST-OC-Hil-1027-SCR-01 | 00 | REH-MDU- Wadi Yemm - Fortaleza - Discrepancy at Foundation | 1027 | 2026-05-09 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000006 | REH-MD01-ST-OC-Hil-1036-SCR-06 | 00 | REH-MDU- Wadi Yemm - Fortaleza - Clarification Request Regarding Conflict for Ramp Slab Thickness in Drawings as marked with arevision cloud. | 1036 | 2026-05-10 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000003 | REH-MD01-ST-OC-Hil-1043-SCR-03 | 00 | REH-MDU- Wadi Yemm - Light house - Columns and Axes conflicts | 1043 | 2026-05-10 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000001 | REH-MD01-ST-OC-Hil-1022-SCR-01 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-10 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000003 | REH-MD01-ST-OC-Hil-1024-SCR-03 | 00 | REH-MDU- Wadi Yemm - Slab discrepancies - Ground Floor - Plot 1024 | 1024 | 2026-05-10 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000007 | REH-MD01-ST-OC-Hil-1036-SCR-07 | 00 | REH-MDU- Wadi Yemm - Clarification Request Regarding Missing Planted Column Type in Drawings as marked with arevision cloud. | 1036 | 2026-05-10 | 2026-05-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000008 | REH-MD01-ST-OC-Hil-1036-SCR-08 | 00 | REH-MDU- Wadi Yemm - STR-MEP coordination | 1036 | 2026-05-10 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000004 | REH-MD01-ST-OC-Hil-1043-SCR-04 | 00 | REH-MDU- Wadi Yemm - Light house - architectural and structural drawing conflict | 1043 | 2026-05-10 | 2026-05-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000005 | REH-MD01-ST-OC-Hil-1060-SCR-05 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN MODEL & IFC DRAWINGS | 1060 | 2026-05-10 | 2026-05-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000004 | OC-SCR-000020 | 00 | REH-MDU- Wadi Yemm - Clarification For Stairs missing data | 1024 | 2026-05-11 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000005 | REH-MD01-ST-OC-Hil-1029-SCR-05 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Clarification Request Regarding Missing T.O.C. for Columns in Drawings as marked with a revision cloud. | 1029 | 2026-05-11 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000009 | REH-MD01-ST-OC-Hil-1036-SCR-09 | 00 | REH-MDU- Wadi Yemm - STR-MEP coordination | 1036 | 2026-05-11 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000010 | REH-MD01-ST-OC-Hil-1036-SCR-10 | 00 | REH-MDU- Wadi Yemm - Clarification Request Regarding Your Reply S.C.R. (REH-MD01-MDU-ST-OC-Hil-1036-SCR-000002-00) | 1036 | 2026-05-11 | 2026-05-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000011 | REH-MD01-ST-OC-Hil-1036-SCR-11 | 00 | REH-MDU- Wadi Yemm -Change of Beam (GB 07) on Ground Floor at Zone 05 - Plot 1036 | 1036 | 2026-05-11 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000005 | REH-MD01-ST-OC-Hil-1024-SCR-05 | 00 | REH-MDU- Wadi Yemm - Columns shifting as per site condition - Ground floor- Plot 1024 | 1024 | 2026-05-11 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000007 | REH-MD01-ST-OC-Hil-1029-SCR-07 | 00 | REH-MDU- Wadi Yemm - Super Plot 01 – Missing Raft Level | 1029 | 2026-05-11 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000006 | REH-MD01-ST-OC-Hil-1029-SCR-06 | 00 | REH-MDU- Wadi Yemm - slab boundaries are not coordinated with the columns or beams. please check and confirm | 1029 | 2026-05-11 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000008 | REH-MD01-ST-OC-Hil-1029-SCR-08 | 00 | REH-MDU- Wadi Yemm -Super Plot 01 – plot 1029 – Clarification Request Regarding Double Height Columns in Drawings as marked with a revision cloud. | 1029 | 2026-05-11 | 2026-05-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000004 | REH-MD01-ST-OC-Hil-1044-SCR-04 | 00 | REH-MDU- Wadi Yemm - Clarification For Stair Details | 1044 | 2026-05-11 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000009 | REH-MD01-ST-OC-Hil-1029-SCR-09 | 00 | REH-MDU- Wadi Yemm - Clarification For Stair DetailsSuper Plot 01 – Discrepancy in Column Dimensions | 1029 | 2026-05-12 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000010 | REH-MD01-ST-OC-Hil-1029-SCR-10 | 00 | REH-MDU- Wadi Yemm - Clarification Request Regarding Missing Column Information at Lower Ground Level | 1029 | 2026-05-12 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000006 | REH-MD01-ST-OC-Hil-1060-SCR-06 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN IFC MODELS & CLASHES BETWEEN ELEMENTS | 1060 | 2026-05-12 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000007 | REH-MD01-ST-OC-Hil-1060-SCR-07 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN STR.& ARCH. MODELS | 1060 | 2026-05-12 | 2026-05-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000008 | REH-MD01-ST-OC-Hil-1060-SCR-08 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN STR.& ARCH. MODELS | 1060 | 2026-05-12 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000002 | REH-MD01-ST-OC-Hil-XXXX-SCR-02 | 00 | REH-MDU- Wadi Yemm - Conflict in concrete compressive strength between the specifications and the general notes on the IFC drawings | XXXX | 2026-05-12 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000002 | OC-SCR-000027 | 00 | REH-MDU- Wadi Yemm - Clarifications at super plot 06-plot 1022- Ground Floor | 1022 | 2026-05-12 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000012 | OC-SCR-000028 | 00 | REH-MDU- Wadi Yemm - Proposed detail for the ended columns with slab for your approval. | 1036 | 2026-05-12 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000013 | OC-SCR-000029 | 00 | REH-MDU- Wadi Yemm - New IFC design package (HillInt-TRANSMIT-001143)& according to the current site stiuation | 1036 | 2026-05-13 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000014 | OC-SCR-000031 | 00 | REH-MDU- Wadi Yemm -Clarification Request Regarding Discrepancy Between Longitudinal Bars and Shape Code for Column Type C55 | 1036 | 2026-05-13 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000015 | OC-SCR-000033 | 00 | REH-MDU- Wadi Yemm - Plot-1036 Mising column | 1036 | 2026-05-13 | 2026-05-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000003 | OC-SCR-000030 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-13 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000009 | OC-SCR-000032 | 00 | REH-MDU- Wadi Yemm - Conflicts in the IFC. Package | 1060 | 2026-05-13 | 2026-05-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000002 | OC-SCR-000035 | 00 | REH-MDU- Wadi Yemm - Fortaleza - Sump Level Clarification | 1027 | 2026-05-13 | 2026-05-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000004 | OC-SCR-000039 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-14 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000002 | OC-SCR-000040 | 00 | REH-MDU- Wadi Yemm - proposal for the slab level difference detail – Plot 1025 | 1025 | 2026-05-14 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000003 | OC-SCR-000041 | 00 | REH-MDU- Wadi Yemm - Plot 1047- Modification of the position on beam no. (FB97) in First Floors. | 1047 | 2026-05-14 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000010 | OC-SCR-000042 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN STR.MODEL & IFC PACKAGE | 1060 | 2026-05-14 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000011 | OC-SCR-000043 | 00 | REH-MDU- Wadi Yemm - DESCREPANCY BETWEEN STR.MODEL & IFC PACKAGE | 1060 | 2026-05-14 | 2026-05-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000002 | OC-SCR-000044 | 00 | REH-MDU- Wadi Yemm - Discrepancies in (Columns & axes plan & RC Plan) | 1031 | 2026-05-16 | 2026-05-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000016 | OC-SCR-000045 | 00 | REH-MDU- Wadi Yemm - Plot-1036 START LEVEL OF ATTACHED PLANTED COLUMNS | 1036 | 2026-05-16 | 2026-05-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000005 | OC-SCR-000046 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-16 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000006 | OC-SCR-000047 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-16 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000005 | OC-SCR-000049 | 00 | REH-MDU - Wadi Yemm - Clarification For Ballanced Tank Details | 1044 | 2026-05-17 | 2026-06-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000005 | OC-SCR-000048 | 00 | REH-MDU - Wadi Yemm - Light house - columns location conflict with raft and RW | 1043 | 2026-05-17 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000017 | OC-SCR-000054 | 00 | REH-MDU - Wadi Yemm - Light house - Conflict between columns reinforcement schedule and IFC structure plans &revit model for columns dimension . | 1036 | 2026-05-17 | 2026-05-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000006 | OC-SCR-000053 | 00 | REH-MDU - Wadi Yemm - Conflict in Beams and Slabs levels in Ground floor- Plot 1024 | 1024 | 2026-05-17 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000004 | OC-SCR-000052 | 00 | REH-MDU - Wadi Yemm - Missing Planted column Details - Plot 1021 | 1021 | 2026-05-17 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000018 | OC-SCR-000055 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding Missing Reinforcement Slab for in Drawings as marked with arevision cloud. | 1036 | 2026-05-18 | 2026-05-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000005 | OC-SCR-000056 | 00 | REH-MDU - Wadi Yemm - Missing roof slab over staircase(5) Dimensions and Reinforcement Details– Plot 1028- Part 3 | 1028 | 2026-05-18 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000011 | OC-SCR-000057 | 00 | REH-MDU - Wadi Yemm - Request for Clarification: Exact Lengths and T.O.C. for Indicated Walls | 1029 | 2026-05-18 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000005 | OC-SCR-000062 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Missing parts of Ground Floor plans | 1021 | 2026-05-19 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000007 | OC-SCR-000063 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-19 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000008 | OC-SCR-000064 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-05-19 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000001 | OC-SCR-000065 | 00 | REH-MDU - Wadi Yemm - Plot 1023 - Foundation plan discrepancies | 1023 | 2026-05-19 | 2026-06-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000019 | OC-SCR-000066 | 00 | REH-MDU - Wadi Yemm - MISSING UPDATED DRAWINGS AND SCEDULES | 1036 | 2026-05-19 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000020 | OC-SCR-000067 | 00 | REH-MDU - Wadi Yemm - Conflict of beams and connected slabs. | 1036 | 2026-05-19 | 2026-05-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000006 | OC-SCR-000071 | 00 | REH-MDU - Wadi Yemm - 1028 - Part1-Stair 1&2 - finishes & beams levels | 1028 | 2026-05-20 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000007 | OC-SCR-000072 | 00 | REH-MDU - Wadi Yemm - 1028 - Ground floor Level - Swimming Pools,Fountain,Stairs and ramps on the ground. | 1028 | 2026-05-20 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000008 | OC-SCR-000073 | 00 | REH-MDU - Wadi Yemm - 1028 - Ground floor Level -barrier wall for the ramp slab. | 1028 | 2026-05-20 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000012 | OC-SCR-000074 | 00 | REH-MDU - Wadi Yemm - Super Plot 01 - Raft Thickening | 1029 | 2026-05-20 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000001 | OC-SCR-000075 | 00 | REH-MDU - Wadi Yemm - Amphitheatre 1041 – Excavation Recommendation | 1041 | 2026-05-20 | 2026-06-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000004 | OC-SCR-000076 | 00 | REH-MDU - Wadi Yemm - Plot 1047 - Stair core openings | 1047 | 2026-05-20 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000005 | OC-SCR-000077 | 00 | REH-MDU - Wadi Yemm - Plot 1047- First Floors Beam ( FB32)modification. | 1047 | 2026-05-20 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000012 | OC-SCR-000078 | 00 | REH-MDU - Wadi Yemm - Conflicts in the IFC. Package ( COL& AXES with col. Table) and cores with slab beams | 1060 | 2026-05-20 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000001 | OC-SCR-000087 | 00 | REH-MDU - Wadi Yemm - Boutique Cluster 1020 – Excavation and Blinding | 1020 | 2026-05-21 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000009 | OC-SCR-000085 | 00 | REH-MDU - Wadi Yemm - 1028 - Ground & First floor Level -Missed Post columns types. | 1028 | 2026-05-21 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000021 | OC-SCR-000081 | 00 | REH-MDU - Wadi Yemm - Plot-1036 Missing Ramp | 1036 | 2026-05-21 | 2026-05-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000006 | OC-SCR-000080 | 00 | REH-MDU - Wadi Yemm - Slab Configuration at Stair Landing Area | 1044 | 2026-05-21 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000006 | OC-SCR-000086 | 00 | REH-MDU - Wadi Yemm - Plot 1047- First Floors Beam ( B00) modification. | 1047 | 2026-05-21 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000013 | OC-SCR-000083 | 00 | REH-MDU - Wadi Yemm - Clarification for some conflicts in the raft rft. In the IFC. Package | 1060 | 2026-05-21 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000009 | OC-SCR-000088 | 00 | REH-MDU - Wadi Yemm - Clarifications at super plot 06-plot 1022-Core RFT. | 1022 | 2026-05-21 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000010 | OC-SCR-000089 | 00 | REH-MDU - Wadi Yemm - 1028 - Ground Floor Slab Level Discrepancy . | 1028 | 2026-05-22 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000011 | OC-SCR-000090 | 00 | REH-MDU - Wadi Yemm - 1028 - Ground Floor-Beams connection to the slab. | 1028 | 2026-05-22 | 2026-05-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000022 | OC-SCR-000091 | 00 | REH-MDU - Wadi Yemm - DEFFERENCE IN LEVEL | 1036 | 2026-05-22 | 2026-06-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000013 | OC-SCR-000092 | 00 | REH-MDU - Wadi Yemm - Clarifications on Columns Type/Continuity & Drop Panel Depth. | 1029 | 2026-05-23 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000014 | OC-SCR-000093 | 00 | REH-MDU - Wadi Yemm - CLARIFY MESH RFT BORDER . | 1029 | 2026-05-23 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000015 | OC-SCR-000094 | 00 | REH-MDU - Wadi Yemm - DRAWINGS OVERLAP AND MISMATCH | 1029 | 2026-05-23 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000002 | OC-SCR-000095 | 00 | REH-MDU - Wadi Yemm - Plot 1023 - columns and axes descripincy | 1023 | 2026-05-24 | 2026-06-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000023 | OC-SCR-000096 | 00 | REH-MDU - Wadi Yemm - Difference in beam model. | 1036 | 2026-05-24 | 2026-05-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000007 | OC-SCR-000099 | 00 | REH-MDU - Wadi Yemm - Conflicts in the Ground , First , Second plan In the IFC. Package | 1024 | 2026-05-24 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000008 | OC-SCR-000100 | 00 | REH-MDU - Wadi Yemm - Columns supporting ground floor Ramp | 1024 | 2026-05-24 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000016 | OC-SCR-000101 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding Correct Mesh Reinforcement for Plot 1030 Basement Level | 1029 | 2026-05-24 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000017 | OC-SCR-000102 | 00 | REH-MDU - Wadi Yemm - Clarification for Column T.O.C. – SP01 (Lower Ground & Ground Levels) | 1029 | 2026-05-24 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000006 | OC-SCR-000103 | 00 | REH-MDU - Wadi Yemm - Light house - retaining wall level clirfication | 1043 | 2026-05-25 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000003 | OC-SCR-000105 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -conflict between columns schedual and columns and axes | 1023 | 2026-05-25 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000007 | OC-SCR-000109 | 00 | REH-MDU - Wadi Yemm - levels contradictions- Plot 1026- at ground floor | 1026 | 2026-05-25 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000003 | OC-SCR-000111 | 00 | REH-MDU - Wadi Yemm - Fortaleza - Discrepancies and Missing Data | 1027 | 2026-05-25 | 2026-06-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000018 | OC-SCR-000106 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1037 | 1029 | 2026-05-25 | 2026-06-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000019 | OC-SCR-000107 | 00 | REH-MDU - Wadi Yemm - Missing Slab Boundries | 1029 | 2026-05-25 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000003 |  | 00 | REH-MDU - Wadi Yemm - Corrupted and Oversized Model File | 1031 | 2026-05-25 | 2026-06-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000007 | OC-SCR-000110 | 00 | REH-MDU - Wadi Yemm - Retaining Wall Discrepancy Between Architectural, Structural & Landscape Models | 1044 | 2026-05-25 | 2026-06-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000008 | OC-SCR-000112 | 00 | REH-MDU - Wadi Yemm - Clarification For Stairs Details | 1044 | 2026-05-25 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000004 | OC-SCR-000113 | 00 | REH-MDU - Wadi Yemm - Missing raft reinforcement data | 1023 | 2026-05-25 | 2026-06-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000005 | OC-SCR-000118 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -Inquiry – Avoiding the Use of Couplers in Column CF14 | 1023 | 2026-06-02 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000006 | OC-SCR-000120 | 00 | REH-MDU - Wadi Yemm - Plot 1021 basement slab- - additional Bottom RFT above columns | 1021 | 2026-06-02 | 2026-06-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000007 | OC-SCR-000121 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Basement 01 - Openings & Missing stair. | 1021 | 2026-06-02 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000010 | OC-SCR-000129 | 00 | REH-MDU - Wadi Yemm - Clarifications at super plot 06-plot 1022-Columns. | 1022 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000020 | OC-SCR-000122 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1037. | 1029 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000021 | OC-SCR-000123 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1037. | 1029 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000022 | OC-SCR-000124 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1037. | 1029 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000023 | OC-SCR-000125 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1037. | 1029 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000024 | OC-SCR-000128 | 00 | REH-MDU - Wadi Yemm - Clarification Required for Dashed Lines and Beam Types. | 1029 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000014 | OC-SCR-000126 | 00 | REH-MDU - Wadi Yemm - Required setting out plans - Plot 1060 | 1060 | 2026-06-02 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000015 | OC-SCR-000127 | 00 | REH-MDU - Wadi Yemm - DESCREPANCY BETWEEN B02.MODEL & B01.MODEL | 1060 | 2026-06-02 | 2026-06-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000025 | OC-SCR-000130 | 00 | REH-MDU - Wadi Yemm - Ground Floor missing data | 1029 | 2026-06-03 | 2026-06-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000009 | OC-SCR-000131 | 00 | REH-MDU - Wadi Yemm - Missing Ground Floor Column Information | 1044 | 2026-06-03 | 2026-06-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000010 | OC-SCR-000133 | 00 | REH-MDU - Wadi Yemm - Clarification For Beams Details | 1044 | 2026-06-03 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000011 | OC-SCR-000134 | 00 | REH-MDU - Wadi Yemm - Ground Floor Slab Discrepancy Between Models | 1044 | 2026-06-03 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000012 |  | 00 | REH-MDU - Wadi Yemm - Ground Floor Slab Discrepancy Between Models | 1044 | 2026-06-03 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000013 |  | 00 | REH-MDU - Wadi Yemm - Ground Floor Slab Discrepancy Between Models | 1044 | 2026-06-03 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000014 |  | 00 | REH-MDU - Wadi Yemm - Clarification for Planter Walls Type and RFT | 1044 | 2026-06-03 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000002 | OC-SCR-000132 | 00 | REH-MDU - Wadi Yemm - Amphitheatre 1041 – Column Dimension Clarification | 1041 | 2026-06-03 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000003 | OC-SCR-000146 | 00 | REH-MDU - Wadi Yemm - Amphitheater (Plot 1041) - Columns Discrepancies and Missing Data | 1041 | 2026-06-04 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000006 | OC-SCR-000138 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -Elevator pit width | 1023 | 2026-06-04 | 2026-06-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000009 | OC-SCR-000139 | 00 | REH-MDU - Wadi Yemm - Beam level- ground floor Ramp | 1024 | 2026-06-04 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000008 | OC-SCR-000144 | 00 | REH-MDU- Wadi Yemm - Plot 1026 - Combined beams of Ramp from Basement 01 to Ground floor. | 1026 | 2026-06-04 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000004 | OC-SCR-000145 | 00 | REH-MDU - Wadi Yemm - Fortaleza - 1027 - Drop of Area at level +7.90 | 1027 | 2026-06-04 | 2026-06-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000005 | OC-SCR-000148 | 00 | REH-MDU - Wadi Yemm - Fortaleza - 1027 - Discrepancies and Missing Data | 1027 | 2026-06-04 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000015 |  | 00 | REH-MDU - Wadi Yemm - Clarification Required on Slab Level Difference and connections between them | 1044 | 2026-06-04 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000026 | OC-SCR-000140 | 00 | REH-MDU - Wadi Yemm - Clarification Required for Beam Type. | 1029 | 2026-06-04 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000027 | OC-SCR-000141 | 00 | REH-MDU - Wadi Yemm - Beams Clarification | 1029 | 2026-06-04 | 2026-06-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000028 | OC-SCR-000142 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Columns and Axes & Lower Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-04 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000029 | OC-SCR-000149 | 00 | REH-MDU - Wadi Yemm - Plot 1029 - Ground Slab STR-MEP coordination | 1029 | 2026-06-06 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000030 | OC-SCR-000150 | 00 | REH-MDU - Wadi Yemm - Plot 1029 - Lower ground Slab STR-MEP coordination | 1029 | 2026-06-06 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000024 | OC-SCR-000151 | 00 | REH-MDU - Wadi Yemm - Plot-1036 COLUMNS TYPE CHANGES | 1036 | 2026-06-06 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000025 | OC-SCR-000152 | 00 | REH-MDU - Wadi Yemm - Plot-1036 Discrepancy between Site Excution and Design | 1036 | 2026-06-06 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000031 | OC-SCR-000153 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-07 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000032 | OC-SCR-000154 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Revision Clouds at Lower Ground Level Structural IFC Drawings For Plot 1037 | 1029 | 2026-06-07 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000033 | OC-SCR-000155 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-07 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000009 | OC-SCR-000156 | 00 | REH-MDU - Wadi Yemm - conflict between slab level in 2D and the model | 1026 | 2026-06-07 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000012 | OC-SCR-000157 | 00 | REH-MDU - Wadi Yemm - 1028 - Part1-Stair 1&2 - finishes & beams levels | 1028 | 2026-06-07 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000034 | OC-SCR-000158 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Lower Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-07 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000035 | OC-SCR-000159 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-07 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000016 | OC-SCR-000160 | 00 | REH-MDU - Wadi Yemm - DESCREPANCY BETWEEN OPENING IN B01 STR. & ARCH. PLANS | 1060 | 2026-06-08 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000017 | OC-SCR-000161 | 00 | REH-MDU - Wadi Yemm - MISSING BEAM TYPE | 1060 | 2026-06-08 | 2026-06-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000008 | OC-SCR-000162 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Basement 01 - Openings . | 1021 | 2026-06-08 | 2026-06-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000011 | OC-SCR-000163 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-06-08 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000036 | OC-SCR-000164 | 00 | REH-MDU - Wadi Yemm - SP01-BASEMENT SLAB COORDINATION CONFLICT. | 1029 | 2026-06-08 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000037 | OC-SCR-000165 | 00 | REH-MDU - Wadi Yemm - SP01- GROUND SLAB CLARIFICATION | 1029 | 2026-06-08 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1030-SCR-000001 | OC-SCR-000166 | 00 | REH-MDU - Wadi Yemm - Plot-1030 BASEMENT SLAB COORDINATION CONFLICT. | 1030 | 2026-06-08 | 2026-06-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000004 | OC-SCR-000167 | 00 | REH-MDU - Wadi Yemm - Amphitheater (Plot 1041) - Clarification Required on Sump Pit Clearance, Fill Material, and MEP Service Space | 1041 | 2026-06-08 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000007 | OC-SCR-000168 | 00 | REH-MDU - Wadi Yemm - Plot 1047- Ground Floors -Part 01 Slab Drop panel on axes (CD &202) | 1047 | 2026-06-08 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000008 | OC-SCR-000169 | 00 | REH-MDU - Wadi Yemm - Revised design Ground Floor drawing -Part 02 (REH-MD01-MDU-ST-ECG-1047-DG-109203/ R 04)- (PC 63)on axis (CT)&behind axis(200). | 1047 | 2026-06-08 | 2026-06-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000004 | OC-SCR-000171 | 00 | REH-MDU - Wadi Yemm - Clarification Required on Sketch vs. Design Drawing Discrepancies – SP02 | 1031 | 2026-06-09 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000012 | OC-SCR-000173 | 00 | REH-MDU - Wadi Yemm - Clarifications at super plot 06-plot 1018-slab. | 1022 | 2026-06-09 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000003 | OC-SCR-000175 | 00 | REH-MDU - Wadi Yemm - COLUMN REBAR @ FIRST STAGE IS SMALLER THAN SECOND STAGE | 1025 | 2026-06-09 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000038 | OC-SCR-000172 | 00 | REH-MDU - Wadi Yemm - MARKED BEAMS CONFLICT-PLOT 1035-AXIS (35BA) | 1029 | 2026-06-09 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000010 | OC-SCR-000177 | 00 | REH-MDU- Wadi Yemm - Clarification For Stairs missing data | 1024 | 2026-06-09 | 2026-06-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000010 | OC-SCR-000176 | 00 | REH-MDU - Wadi Yemm - Plot 1026 - Conflict Retaining wall at Groung Floor | 1026 | 2026-06-09 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000039 | OC-SCR-000179 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-09 | 2026-06-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000040 | OC-SCR-000180 | 00 | REH-MDU - Wadi Yemm - CONFLICT IN LEVELS | 1029 | 2026-06-09 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000041 | OC-SCR-000181 | 00 | REH-MDU - Wadi Yemm - CLARIFY Main Reinforcement Direction & Mesh RFT Border | 1029 | 2026-06-10 | 2026-06-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000026 | OC-SCR-000182 | 00 | REH-MDU - Wadi Yemm - Plot-1036 COLUMN STARTER BARS REINFORCEMENT ISSUE | 1036 | 2026-06-10 | 2026-06-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000009 | OC-SCR-000183 | 00 | REH-MDU- Wadi Yemm - Discrepancy in Wall Thickness (W2) | 1021 | 2026-06-10 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000011 | OC-SCR-000185 | 00 | REH-MDU - Wadi Yemm - Clarification on Stair 1 Part 6 Section and Finishing Layers | 1024 | 2026-06-10 | 2026-06-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000011 | OC-SCR-000186 | 00 | REH-MDU - Wadi Yemm - Missing floor for slab | 1026 | 2026-06-10 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000013 | OC-SCR-000188 | 00 | REH-MDU - Wadi Yemm - Clarifications at super plot 06 - plot 1018 - ground floor | 1022 | 2026-06-10 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000042 | OC-SCR-000187 | 00 | REH-MDU - Wadi Yemm - SP01- COLUMNS SCHEDULE CLARIFICATION | 1029 | 2026-06-10 | 2026-06-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000043 | OC-SCR-000189 | 00 | REH-MDU - Wadi Yemm - Retaining Wall Extent, Connection, and Dashed Lines | 1029 | 2026-06-10 | 2026-06-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000010 | OC-SCR-000190 | 00 | REH-MDU - Wadi Yemm - Required Design Drawings for Typical Floors in Plot 1021 | 1021 | 2026-06-11 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000014 | OC-SCR-000191 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022- GR-01 Slabs | 1022 | 2026-06-11 | 2026-06-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000005 | OC-SCR-000197 | 00 | REH-MDU - Wadi Yemm - Discrepancies in axes-1031 B1-1032 B2-1033 B2 - SP02 | 1031 | 2026-06-11 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000027 | OC-SCR-000198 | 00 | REH-MDU - Wadi Yemm - Plot-1036 Shafts conflict | 1036 | 2026-06-11 | 2026-06-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000044 | OC-SCR-000200 | 00 | REH-MDU - Wadi Yemm - Plot 1034 - GR Slab opennings conflict | 1029 | 2026-06-11 | 2026-06-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000007 | OC-SCR-000201 | 00 | REH-MDU - Wadi Yemm - Light house - Basement 01 Columns and Axes Conflict | 1043 | 2026-06-11 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000002 | OC-SCR-000202 | 00 | REH-MDU - Wadi Yemm - Boutique Cluster 1020 – Discrebancy between Excavation and Blinding levels | 1020 | 2026-06-11 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000012 | OC-SCR-000203 | 00 | REH-MDU - Wadi Yemm - Conflict in STR. Design data | 1024 | 2026-06-11 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000013 | OC-SCR-000204 | 00 | REH-MDU - Wadi Yemm - Conflict in STR. Design data | 1024 | 2026-06-11 | 2026-06-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000006 | OC-SCR-000205 | 00 | REH-MDU - Wadi Yemm - Fortaleza - Discrepancies and Missing Data | 1027 | 2026-06-11 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000028 | OC-SCR-000208 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Structural IFC Drawings – First Floor Level – Plot 1036 | 1036 | 2026-06-13 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000029 | OC-SCR-000209 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Structural IFC Drawings – First Floor Level – Plot 1036 | 1036 | 2026-06-14 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000016 | OC-SCR-000211 | 00 | REH-MDU - Wadi Yemm - Clarification For Ballanced Tank Details | 1044 | 2026-06-14 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000045 | OC-SCR-000213 | 00 | REH-MDU - Wadi Yemm - SP01- COLUMNS SCHEDULE CLARIFICATION | 1029 | 2026-06-14 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000008 | OC-SCR-000214 | 00 | REH-MDU - Wadi Yemm - Light house - Basement 01 slab discrepancies | 1043 | 2026-06-14 | 2026-06-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000005 | OC-SCR-000218 | 00 | REH-MDU - Wadi Yemm - Amphitheater (Plot 1041) – Clarifications Required for the IFC Foundation Package | 1041 | 2026-06-15 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000004 | OC-SCR-000219 | 00 | REH-MDU - Wadi Yemm - BEAMS LEVEL AT END SUPPORT | 1025 | 2026-06-15 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000015 | OC-SCR-000221 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022-1018- GR-01 Slabs (2) | 1022 | 2026-06-15 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000007 | OC-SCR-000228 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -basement 01 columns discrepancies | 1023 | 2026-06-15 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000014 | OC-SCR-000229 | 00 | REH-MDU - Wadi Yemm - Beams STR. Design, in the first floor, part 2 | 1024 | 2026-06-15 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000016 | OC-SCR-000231 | 00 | REH-MDU - Wadi Yemm - Clarifications at super plot 06 - plot 1018 - ground floor | 1022 | 2026-06-15 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000046 | OC-SCR-000230 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-15 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000015 | OC-SCR-000235 | 00 | REH-MDU - Wadi Yemm - Clarification For SCR (8) | 1024 | 2026-06-15 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000016 | OC-SCR-000236 | 00 | REH-MDU - Wadi Yemm - Conflict in Design Data First Floor Plot 1024 | 1024 | 2026-06-15 | 2026-06-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000017 |  | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-06-15 | 2026-06-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000047 | OC-SCR-000238 | 00 | REH-MDU - Wadi Yemm - missing type of beam in plot 1034 at lower ground level | 1029 | 2026-06-15 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000048 | OC-SCR-000239 | 00 | REH-MDU - Wadi Yemm - missing info. about (openings,slabs,pc boundary) | 1029 | 2026-06-15 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000049 | OC-SCR-000241 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-15 | 2026-06-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000017 | OC-SCR-000242 | 00 | REH-MDU - Wadi Yemm - Clarification for Planter Walls Type and RFT | 1044 | 2026-06-16 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000050 | OC-SCR-000243 | 00 | REH-MDU - Wadi Yemm - Plot 1035 - Column's top clarification | 1029 | 2026-06-16 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000051 | OC-SCR-000244 | 00 | REH-MDU - Wadi Yemm - CONFLICT BETWEEN THE LEVEL OF SLAB AND BEAM. & LOCATION OF BEAM.-PLOT 1035-SP01 | 1029 | 2026-06-16 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000030 | OC-SCR-000245 | 00 | REH-MDU - Wadi Yemm - CONFLICT IN THE WIDTH OF COLUMNS C56. | 1036 | 2026-06-16 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000018 |  | 00 | REH-MDU - Wadi Yemm - Clarification for Planter Walls Type and RFT | 1044 | 2026-06-16 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000012 | OC-SCR-000247 | 00 | REH-MDU - Wadi Yemm - Beam Discrepancies | 1026 | 2026-06-16 | 2026-06-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000013 | OC-SCR-000248 | 00 | REH-MDU - Wadi Yemm - Beam Discrepancies | 1026 | 2026-06-16 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000031 | OC-SCR-000249 | 00 | REH-MDU - Wadi Yemm - Plot-1036 Columns bracing | 1036 | 2026-06-16 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000018 | OC-SCR-000251 | 00 | REH-MDU - Wadi Yemm - Structural Design Clarifications – Super Plot 06, Plot 1045 – Ground Floor | 1022 | 2026-06-16 | 2026-06-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000019 | OC-SCR-000252 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-06-16 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000020 | OC-SCR-000253 | 00 | REH-MDU - Wadi Yemm -SP06 - Q4 1045 - Columns&Axis discrepancies and coordination issues in IFC drawings | 1022 | 2026-06-16 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000052 | OC-SCR-000254 | 00 | REH-MDU - Wadi Yemm -Plot 1030 - Lower ground Slab drop clarification | 1029 | 2026-06-16 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000053 | OC-SCR-000255 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Lower Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-16 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000054 | OC-SCR-000257 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-17 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000055 | OC-SCR-000258 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Basement Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-17 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000056 | OC-SCR-000261 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-06-17 | 2026-06-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000006 | OC-SCR-000260 | 00 | REH-MDU - Wadi Yemm - Amphitheater (Plot 1041) – Clarifications Required for the IFC Foundation Package | 1041 | 2026-06-17 | 2026-06-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000021 |  | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-06-17 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000009 | OC-SCR-000263 | 00 | REH-MDU - Wadi Yemm - Plot 1047- Revised design FIRST Floor drawing -Part 02 (REH-MD01-MDU-ST-ECG-1047-DG-109303/ R 01) | 1047 | 2026-06-17 | 2026-06-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000010 | OC-SCR-000269 | 00 | REH-MDU - Wadi Yemm - Plot 1047- Revised design FIRST Floor drawing -Part 03 (REH-MD01-MDU-ST-ECG-1047-DG-109304/ R 01) | 1047 | 2026-06-17 | 2026-06-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000022 | OC-SCR-000264 | 00 | REH-MDU - Wadi Yemm - SP06 - Q4 1045 -Coordination issue between ARCH and STR drawings for Columns & Axes | 1022 | 2026-06-17 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000008 | OC-SCR-000267 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -Basement 01 slab discrepancies | 1023 | 2026-06-17 | 2026-06-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000057 | OC-SCR-000265 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-17 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000032 | OC-SCR-000266 | 00 | REH-MDU - Wadi Yemm - New IFC design package (HillInt-TRANSMIT-001659)& according to the current site stiuation | 1036 | 2026-06-17 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000033 | OC-SCR-000268 | 00 | REH-MDU - Wadi Yemm - LOCATION OF C150 | 1036 | 2026-06-17 | 2026-06-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000023 | OC-SCR-000270 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-06-17 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000019 | OC-SCR-000271 | 00 | REH-MDU - Wadi Yemm - TRENCH DRAIN LOCATION CLARIFICATION – BASEMENT 01 | 1044 | 2026-06-17 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000013 | OC-SCR-000273 | 00 | REH-MDU - Wadi Yemm - 1028 - Ramp Slope Discrepancy (basement 01 up to ground floor). | 1028 | 2026-06-18 | 2026-06-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000058 | OC-SCR-000274 | 00 | REH-MDU - Wadi Yemm - 1029 - Clarification Required – Slab Thickness (Lower Ground vs Ground Floor). | 1029 | 2026-06-20 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000017 | OC-SCR-000275 | 00 | REH-MDU - Wadi Yemm - Discrepancies in levels-Part 03- Plot 1024- ground floor | 1024 | 2026-06-21 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000018 | OC-SCR-000277 | 00 | REH-MDU - Wadi Yemm - Stair,Shafts contradictions- Plot 1024- First floor | 1024 | 2026-06-21 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000059 | OC-SCR-000278 | 00 | REH-MDU - Wadi Yemm - 1029 - Depth of Beam need to be increased | 1029 | 2026-06-21 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000020 | OC-SCR-000279 | 00 | REH-MDU - Wadi Yemm - Clarification for Planter Walls Type and RFT | 1044 | 2026-06-21 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000009 | OC-SCR-000280 | 00 | REH-MDU - Wadi Yemm - Light house - Basement 01missing beams types | 1043 | 2026-06-21 | 2026-06-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000060 | OC-SCR-000281 | 00 | REH-MDU - Wadi Yemm - Beam conflicts and missing data | 1029 | 2026-06-21 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000021 | OC-SCR-000282 | 00 | REH-MDU - Wadi Yemm - Clarification for Planted Columns | 1044 | 2026-06-21 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000014 | OC-SCR-000285 | 00 | REH-MDU - Wadi Yemm - Plot 1026 - Conflict and missing data at Ground Floor | 1026 | 2026-06-22 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000007 | OC-SCR-000284 | 00 | REH-MDU - Wadi Yemm - Fortaleza (Plot 1027) – Clarifications Required for the IFC Foundation Package | 1027 | 2026-06-22 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000034 | OC-SCR-000283 | 00 | REH-MDU - Wadi Yemm - Plot-1036 MISSING BEAM TYPE AT BEAM REINFORCEMENT SCHEDULE | 1036 | 2026-06-22 | 2026-06-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000061 | OC-SCR-000286 | 00 | REH-MDU - Wadi Yemm - SP01-BASEMENT SLAB MISSING BEAMS TYPE | 1029 | 2026-06-22 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000035 | OC-SCR-000287 | 00 | REH-MDU - Wadi Yemm - Plot-1036 MISSING COLUMN TYPE AT GROUND AND FIRST IFC STRUCtURE | 1036 | 2026-06-22 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000062 | OC-SCR-000288 | 00 | REH-MDU - Wadi Yemm - Beam conflicts and missing data | 1029 | 2026-06-22 | 2026-06-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000063 | OC-SCR-000289 | 00 | REH-MDU - Wadi Yemm - Beam conflicts and missing data | 1029 | 2026-06-22 | 2026-06-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000011 | OC-SCR-000294 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Basement 01 - Openings . | 1021 | 2026-06-23 | 2026-07-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000022 |  | 00 | REH-MDU - Wadi Yemm - Confirmation for Beam Depth | 1044 | 2026-06-23 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000064 | OC-SCR-000296 | 00 | REH-MDU - Wadi Yemm - Column conflicts | 1029 | 2026-06-23 | 2026-06-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000024 | OC-SCR-000297 | 00 | REH-MDU - Wadi Yemm - Confliction ARCH & Structure drawings SP06-1022 | 1022 | 2026-06-23 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000065 | OC-SCR-000299 | 00 | REH-MDU - Wadi Yemm - Super Plot 01 - Plot-1037 Clarify Structural Adequacy and Verification of Wall Openings between Water Tank and Pump Room (Domestic Tank) | 1029 | 2026-06-24 | 2026-06-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000066 | OC-SCR-000300 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-06-24 | 2026-06-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000008 | OC-SCR-000301 | 00 | REH-MDU - Wadi Yemm - Fortaleza (Plot 1027) -IFC Foundation Clarification | 1027 | 2026-06-24 | 2026-06-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000007 | OC-SCR-000302 | 00 | REH-MDU - Wadi Yemm - Amphitheater (Plot 1041) – Clarifications Required for the IFC Foundation Package | 1041 | 2026-06-24 | 2026-06-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000067 | OC-SCR-000304 | 00 | REH-MDU - Wadi Yemm - slab opening for SP01-PLOT 1030 LOWER GROUND | 1029 | 2026-06-24 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000036 | OC-SCR-000309 | 00 | REH-MDU - Wadi Yemm - Plot-1036: WALLS REINFORCEMENT AT CORNERS. | 1036 | 2026-06-24 | 2026-06-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000019 | OC-SCR-000313 | 00 | REH-MDU - Wadi Yemm - Proposal For increase Beam Depth Part (1) Ground Plot 1024 | 1024 | 2026-06-25 | 2026-06-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000068 | OC-SCR-000315 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-06-25 | 2026-07-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000018 | OC-SCR-000316 | 00 | REH-MDU - Wadi Yemm - MISSING DATA IN IFC | 1060 | 2026-06-25 | 2026-06-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000025 | OC-SCR-000319 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-06-25 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000009 | OC-SCR-000326 | 00 | REH-MDU - Wadi Yemm - SP05 -Clarifications between architecture drawings and structure drawing foundation plans | 1023 | 2026-06-27 | 2026-07-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000020 | OC-SCR-000328 | 00 | REH-MDU - Plot 1024- first floor- a conflict in STR. Design drawing. | 1024 | 2026-06-27 | 2026-06-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000011 | OC-SCR-000329 | 00 | REH-MDU - Plot 1024- first floor- Conflict in STR. Design-PLOT 1047- FIRST FLOOR-PART 3. | 1047 | 2026-06-28 | 2026-06-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000026 | OC-SCR-000330 | 00 | REH-MDU -SP06 - Q4 1045 & Q 1046 - Conflict between Expansion joint with Landscape package | 1022 | 2026-06-28 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000010 | OC-SCR-000331 | 00 | REH-MDU -SP05 -Missing RFT and Concrete dimensions for some elements in foundation plans | 1023 | 2026-06-28 | 2026-07-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000006 | OC-SCR-000332 | 00 | REH-MDU - Required Design Drawings for Typical Floors in (SP-02) | 1031 | 2026-06-28 | 2026-07-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000069 | OC-SCR-000333 | 00 | REH-MDU - Shaft Openening & Drop Panel Clarification for SP01-PLOT 1034 GROUND | 1029 | 2026-06-28 | 2026-07-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000070 | OC-SCR-000335 | 00 | REH-MDU - Wadi Yemm - Plot 1034 - Ground level beam clarification | 1029 | 2026-06-29 | 2026-07-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000003 | OC-SCR-000337 | 00 | REH-MDU - Wadi Yemm - Plot XXXX - Request For General Details for Rft of Light weight Concrete Stairs | XXXX | 2026-06-29 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000015 | OC-SCR-000339 | 00 | REH-MDU - Wadi Yemm - Plot 1026 - structural sysytrm at Ramp | 1026 | 2026-06-29 | 2026-07-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000071 | OC-SCR-000340 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-06-29 | 2026-07-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000007 | OC-SCR-000344 | 00 | REH-MDU - Wadi Yemm - Discrepancies in opening-1032 B1- SP02 | 1031 | 2026-06-30 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000016 | OC-SCR-000346 | 00 | REH-MDU - Wadi Yemm - Plot 1026 - Conflict and missing data at Ground Floor | 1026 | 2026-06-30 | 2026-07-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000019 | OC-SCR-000347 | 00 | REH-MDU - Wadi Yemm - Shafts contradictions- Plot 1060- at basement 02 floor | 1060 | 2026-06-30 | 2026-07-02 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000072 | OC-SCR-000348 | 00 | REH-MDU - Wadi Yemm - Plot 1035 - Landscape stairs missing | 1029 | 2026-06-30 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000073 | OC-SCR-000349 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Foundation Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-06-30 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000037 | OC-SCR-000350 | 00 | REH-MDU - Wadi Yemm - Plot-1036: Proposal for Reinforcement of Transferred Columns (C100 & C35) | 1036 | 2026-06-30 | 2026-07-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000021 | OC-SCR-000351 | 00 | REH-MDU - Wadi Yemm - Proposal For Increase Column Width Part (2) First As per Site Conditions Plot 1024 | 1024 | 2026-06-30 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000008 | OC-SCR-000353 | 00 | REH-MDU - Wadi Yemm - Missing data in SP02 | 1031 | 2026-06-30 | 2026-07-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000009 | OC-SCR-000354 | 00 | REH-MDU - Wadi Yemm - Level Difference-1032 B1- SP02 | 1031 | 2026-06-30 | 2026-07-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000010 | OC-SCR-000355 | 00 | REH-MDU - Wadi Yemm - Missing data and conflicting information | 1031 | 2026-06-30 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000009 | OC-SCR-000358 | 00 | REH-MDU - Wadi Yemm - Fortaleza (Plot 1027) - Basement 01 IFC Package – Clarification Required | 1027 | 2026-06-30 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000010 | OC-SCR-000359 | 00 | REH-MDU - Wadi Yemm - Fortaleza Hotel (Plot 1027) –Structural IFC Foundation Package Rev.01 vs. Plumbing 50% DD Package –Location Discrepancies | 1027 | 2026-06-30 | 2026-07-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000027 | OC-SCR-000363 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-07-01 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000012 | OC-SCR-000368 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Basement 01 - Openings . | 1021 | 2026-07-01 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000011 | OC-SCR-000369 | 00 | REH-MDU - Wadi Yemm - Opening Contradiction -1031 L.G & GR. PLANS- SP02 | 1031 | 2026-07-01 | 2026-07-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000020 | OC-SCR-000370 | 00 | REH-MDU - Wadi Yemm - Clarification Required – Structural IFC vs Architectural Design (Plot 1060) | 1060 | 2026-07-01 | 2026-07-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000074 | OC-SCR-000372 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-07-01 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000075 | OC-SCR-000373 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-04 | 2026-07-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000076 | OC-SCR-000374 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Lower Ground Level Structural IFC Drawings For Plot 1034 | 1029 | 2026-07-04 | 2026-07-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000077 | OC-SCR-000375 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-05 | 2026-07-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000078 | OC-SCR-000377 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 01 plot 1035 | 1029 | 2026-07-05 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000079 | OC-SCR-000378 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-05 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000011 | OC-SCR-000379 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -Basement 01 slab discrepancies | 1023 | 2026-07-05 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000022 | OC-SCR-000380 | 00 | REH-MDU - Wadi Yemm - Missing Drawings of Roof Level Plot 1024 | 1024 | 2026-07-05 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000010 | OC-SCR-000382 | 00 | REH-MDU - Wadi Yemm - Light house - Sump pits missing data | 1043 | 2026-07-05 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000013 | OC-SCR-000384 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - ground - Columns | 1021 | 2026-07-05 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000023 | OC-SCR-000386 | 00 | REH-MDU - Wadi Yemm - Ramp Details for Plot 1024 | 1024 | 2026-07-05 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000080 | OC-SCR-000383 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-07-05 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000081 | OC-SCR-000388 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-05 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000038 | OC-SCR-000389 | 00 | REH-MDU - Wadi Yemm - Plot-1036: Proposal for Reinforcement of Transferred Columns (C100 & C35 & C92 & C94 & C2 & C12) | 1036 | 2026-07-05 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000023 | OC-SCR-000385 | 00 | REH-MDU - Wadi Yemm - Ramp & Trench Drain Construction Detail Confirmation | 1044 | 2026-07-05 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000011 | OC-SCR-000390 | 00 | REH-MDU - Wadi Yemm - Fortaleza Hotel (Plot 1027) –Structural IFC Foundation Package Rev.02 – Location Discrepancy | 1027 | 2026-07-06 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000012 | OC-SCR-000391 | 00 | REH-MDU - Wadi Yemm - Plot 1023 -Basement 01 slab discrepancies | 1023 | 2026-07-06 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000024 | OC-SCR-000395 | 00 | REH-MDU - Wadi Yemm - Proposal For Increase Column Width Part (2) First As per Site Execution Plot 1024 | 1024 | 2026-07-06 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000012 | OC-SCR-000394 | 00 | REH-MDU - Wadi Yemm - Revit model's Shared Coordinates-SP02-RA08-1031 | 1031 | 2026-07-06 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000013 | OC-SCR-000397 | 00 | REH-MDU - Wadi Yemm - Plot 1023 - SP05 -conflict in pedestal dimensions at raft | 1023 | 2026-07-06 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000025 | OC-SCR-000398 | 00 | REH-MDU - Wadi Yemm - Request of Typical Detail of Columns At Edge of Retaining Wall Plot 1024 | 1024 | 2026-07-06 | 2026-07-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000014 | OC-SCR-000402 | 00 | REH-MDU - Wadi Yemm - 1028 -Ground Floor- Part3 - Clarification Required Regarding Attic Slab at Swimming Pool Area | 1028 | 2026-07-07 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000082 | OC-SCR-000403 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 01 | 1029 | 2026-07-07 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000012 | OC-SCR-000404 | 00 | REH-MDU - Wadi Yemm - Design-PLOT 1047- 1st Floor- Part 02- position of (PC19). | 1047 | 2026-07-07 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000083 | OC-SCR-000405 | 00 | REH-MDU - Wadi Yemm - CONCRETE DIMENSIONS OF CORE 02-PLOT1030-SP01 | 1029 | 2026-07-07 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000004 | OC-SCR-000406 | 00 | REH-MDU - Wadi Yemm - Plot XXXX - Upgrade Project BIM Software from Autodesk Revit 2024 to Autodesk Revit 2026 | XXXX | 2026-07-07 | 2026-07-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000003 | OC-SCR-000409 | 00 | REH-MDU - Wadi Yemm - Clarification For foundations | 1020 | 2026-07-07 | 2026-07-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000017 | OC-SCR-000410 | 00 | REH-MDU - Wadi Yemm - Plot 1026 - Ground Floor conflict in levels. | 1026 | 2026-07-07 | 2026-07-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000013 | OC-SCR-000412 | 00 | REH-MDU - Wadi Yemm - Plot 1047- missing shaft in 3rd, and 4th str. Design drawings. | 1047 | 2026-07-08 | 2026-07-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000084 | OC-SCR-000413 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 01 plot 1029 | 1029 | 2026-07-08 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000085 | OC-SCR-000416 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Lower Ground Level Structural IFC Drawings For Plot 1034 | 1029 | 2026-07-08 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000086 | OC-SCR-000417 | 00 | REH-MDU - Wadi Yemm - SP01- LOWER GROUND BEAMS TYPE CHANGE. | 1029 | 2026-07-08 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000021 | OC-SCR-000419 | 00 | REH-MDU - Wadi Yemm - Clarification Required – Plot 1060 - Basement 01 - Conflict in Openings & elevator pit | 1060 | 2026-07-09 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000087 | OC-SCR-000424 | 00 | REH-MDU - Wadi Yemm - Plot 1037 - S.O.G level modification clarification | 1029 | 2026-07-09 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000088 | OC-SCR-000425 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-07-09 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000089 | OC-SCR-000426 | 00 | REH-MDU - Wadi Yemm - THE START LEVEL OF REDUCTION FOR C09&C10 | 1029 | 2026-07-09 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000090 | OC-SCR-000427 | 00 | REH-MDU - Wadi Yemm - DETERMINE THE END OF BEAM AND ITS SUPPORT. | 1029 | 2026-07-09 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000028 | OC-SCR-000428 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06-Plot 1018-attic slab | 1022 | 2026-07-11 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000091 | OC-SCR-000432 | 00 | REH-MDU - Wadi Yemm - SP01- GROUND BEAMS TYPE CHANGE. | 1029 | 2026-07-12 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000005 | OC-SCR-000433 | 00 | REH-MDU - Wadi Yemm - Plot 1025- Super structure coordination | 1025 | 2026-07-12 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000015 | OC-SCR-000434 | 00 | REH-MDU - Wadi Yemm -1028 -From Foundation to Basement Slab Level- Part3 - Column C8 Executed Size and Reinforcement Discrepancy | 1028 | 2026-07-12 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000092 | OC-SCR-000436 | 00 | REH-MDU - Wadi Yemm - Plot 1035 - STAIR 03 - A11 | 1029 | 2026-07-12 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000093 | OC-SCR-000437 | 00 | REH-MDU - Wadi Yemm - Beam Type Clarification | 1029 | 2026-07-12 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000094 | OC-SCR-000438 | 00 | REH-MDU - Wadi Yemm - COLUMN AND AXIS for SP01-PLOT 1030 FOR FIRST LEVEL | 1029 | 2026-07-12 | 2026-07-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000024 | OC-SCR-000440 | 00 | REH-MDU - Wadi Yemm - Confirmation for Beam Depth | 1044 | 2026-07-12 | 2026-07-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000095 | OC-SCR-000441 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-07-12 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000096 | OC-SCR-000442 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 01 plot 1035 | 1029 | 2026-07-13 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000029 | OC-SCR-000443 | 00 | REH-MDU - Wadi Yemm - Request for Latest Updated Landscape Package – Super Plot 06, Plot 1045 & 1046 | 1022 | 2026-07-13 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000097 | OC-SCR-000444 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 01 plot 1035 | 1029 | 2026-07-13 | 2026-07-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000013 | OC-SCR-000445 | 00 | REH-MDU - Wadi Yemm - COLUMNS DIMENSIONS -Plot 1031 L.G PLAN- SP02 | 1031 | 2026-07-13 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000098 | OC-SCR-000446 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-13 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000014 | OC-SCR-000448 | 00 | REH-MDU - Wadi Yemm - Discrepancies in opening and slab -1033 Lower GR- SP02 | 1031 | 2026-07-13 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000018 | OC-SCR-000451 | 00 | REH-MDU - Wadi Yemm - Shaft Contradictions – Plot 1026 – First Floor. | 1026 | 2026-07-13 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000014 | OC-SCR-000452 | 00 | REH-MDU - Wadi Yemm - Plot 1023 - SP05 -RFT of column C34 | 1023 | 2026-07-13 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000030 | OC-SCR-000453 | 00 | REH-MDU - Wadi Yemm - STRUCTURAL CLARIFICATIONS – Super Plot 06, Plot 1022 | 1022 | 2026-07-13 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000012 | OC-SCR-000454 | 00 | REH-MDU - Wadi Yemm - Fortaleza Hotel (Plot 1027) –Structural IFC - Early Works - Ground Floor IFC | 1027 | 2026-07-14 | 2026-07-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000099 | OC-SCR-000457 | 00 | REH-MDU - Wadi Yemm - Beam Type Clarification | 1029 | 2026-07-14 | 2026-07-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000011 | OC-SCR-000459 | 00 | REH-MDU - Wadi Yemm - Light house - Lower ground columns conflict | 1043 | 2026-07-14 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000100 | OC-SCR-000460 | 00 | REH-MDU - Wadi Yemm - SP01- GROUND BEAMS and SLAB TOC CLARIFICATION | 1029 | 2026-07-14 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000101 | OC-SCR-000461 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-14 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000012 | OC-SCR-000462 | 00 | REH-MDU - Wadi Yemm - Light house - SIKKA Road Retaining wall foundation RFT details | 1043 | 2026-07-14 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000102 | OC-SCR-000465 | 00 | REH-MDU - Wadi Yemm - SP01- PLANTED COLUMNS LOCATION CLARIFICATION | 1029 | 2026-07-15 | 2026-07-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000025 | OC-SCR-000468 | 00 | REH-MDU - Wadi Yemm - CConflict Between Attachment 01 & Attachment 02 – Slab Edge and Opening Dimensions | 1044 | 2026-07-15 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000103 | OC-SCR-000469 | 00 | REH-MDU - Wadi Yemm - conflicts between the beams and openning in the wall | 1029 | 2026-07-15 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000013 | OC-SCR-000471 | 00 | REH-MDU - Wadi Yemm - Light house - Lower Ground Slab descrapincies | 1043 | 2026-07-15 | 2026-07-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000004 | OC-SCR-000479 | 00 | REH-MDU - Wadi Yemm - Discrepancies Between ARCH & STR MODELS | 1020 | 2026-07-15 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000104 | OC-SCR-000480 | 00 | REH-MDU - Wadi Yemm - conflicts between the beams | 1029 | 2026-07-15 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000014 | OC-SCR-000481 | 00 | REH-MDU - Wadi Yemm - Light house - Light house - Lower Ground Slab descrapincies | 1043 | 2026-07-15 | 2026-07-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000026 | OC-SCR-000482 | 00 | REH-MDU - Wadi Yemm -Missing Areas in Str. Design DWG. For Second Level Plot 1024 | 1024 | 2026-07-15 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000019 | OC-SCR-000483 | 00 | REH-MDU - Wadi Yemm - Conflict in Column C42 dimensions at plot 1026 | 1026 | 2026-07-15 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000027 | OC-SCR-000485 | 00 | REH-MDU - Wadi Yemm - Plot 1024 - Second floor - Openings . | 1024 | 2026-07-15 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000105 | OC-SCR-000486 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1034 | 1029 | 2026-07-15 | 2026-07-18 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000013 | OC-SCR-000487 | 00 | REH-MDU - Wadi Yemm - Fortaleza (Plot 1027) – Tower Crane Part H - Concrtet Dimension | 1027 | 2026-07-16 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000028 | OC-SCR-000490 | 00 | REH-MDU - Wadi Yemm - Ramp Details for Plot 1024 | 1024 | 2026-07-16 | 2026-07-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000020 | OC-SCR-000492 | 00 | REH-MDU - Wadi Yemm - Conflict Level in Ground Slab at Plot -1026 | 1026 | 2026-07-16 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000021 | OC-SCR-000491 | 00 | REH-MDU - Wadi Yemm - MISSING Beam Tyeps in Ground FLOOR at Plot -1026 | 1026 | 2026-07-16 | 2026-07-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000014 | OC-SCR-000495 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Basement 01 - Openings . | 1021 | 2026-07-16 | 2026-07-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000026 | OC-SCR-000496 | 00 | REH-MDU - Wadi Yemm - Slab Opening Discrepancy Between Architectural and Structural Drawings | 1044 | 2026-07-16 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000031 | OC-SCR-000502 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – Part 14 – Clarification of Ground Slab Coordination Issues | 1022 | 2026-07-19 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000032 | OC-SCR-000503 | 00 | REH-MDU - Wadi Yemm - SP06 – Q3 1046 – Part 20 – Clarification of Ground Slab Coordination Issues | 1022 | 2026-07-19 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000033 | OC-SCR-000504 | 00 | REH-MDU - Wadi Yemm - SP06 – Q3 1046 – Part 21 – Clarification of Ground Slab Coordination Issues | 1022 | 2026-07-19 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000034 | OC-SCR-000505 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06 | 1022 | 2026-07-19 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000029 | OC-SCR-000506 | 00 | REH-MDU - Wadi Yemm - Conflict and Missing Data in Str. Design DWG. For Second Level Plot 1024 | 1024 | 2026-07-19 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000106 | OC-SCR-000507 | 00 | REH-MDU - Wadi Yemm - Plot 1035 - Slabs connection | 1029 | 2026-07-19 | 2026-07-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000107 | OC-SCR-000511 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Lower Ground Level Structural IFC Drawings For Plot 1034 | 1029 | 2026-07-19 | 2026-07-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000108 | OC-SCR-000512 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) -LOWER Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-20 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000030 | OC-SCR-000514 | 00 | REH-MDU - Wadi Yemm - Drilled and Missing RFT of Vertical RW Part (4) For Ground Level Plot 1024 | 1024 | 2026-07-20 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000109 | OC-SCR-000516 | 00 | REH-MDU - Wadi Yemm - Super Plot 01 - Plot-1035 Clarify Structural Adequacy and Verification of Beam Type & Dimensions | 1029 | 2026-07-20 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000031 | OC-SCR-000518 | 00 | REH-MDU - Wadi Yemm - Updates in Str. Design for First Floor Plot 1024 Dated 13-7-2026 | 1024 | 2026-07-20 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000035 | OC-SCR-000519 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-07-20 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000036 | OC-SCR-000520 | 00 | REH-MDU - Wadi Yemm - Columns & Axis Clarifications at SP06-plot 1022 | 1022 | 2026-07-21 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000037 | OC-SCR-000521 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – Clarification of Ground Slab Coordination Issues | 1022 | 2026-07-21 | 2026-07-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000032 | OC-SCR-000522 | 00 | REH-MDU - Wadi Yemm - Stairs 3&7 Details- Plot 1024 | 1024 | 2026-07-21 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000110 | OC-SCR-000523 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-21 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000111 | OC-SCR-000524 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-07-21 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000112 | OC-SCR-000527 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-07-21 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000113 | OC-SCR-000537 | 00 | REH-MDU - Wadi Yemm - MISSED SLAB IN IFC DRAWINGS-PLOT1030-SP01 | 1029 | 2026-07-21 | 2026-07-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000114 | OC-SCR-000540 | 00 | REH-MDU - Wadi Yemm - Clarification Regarding Intermediate Beams | 1029 | 2026-07-22 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000039 | OC-SCR-000541 | 00 | REH-MDU - Wadi Yemm - Plot-1036 COLUMN C71 DEWELS BAR REINFORCEMENT ISSUE | 1036 | 2026-07-22 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000115 | OC-SCR-000542 | 00 | REH-MDU - Wadi Yemm - CLARIFY BEAM SUPPORT. | 1029 | 2026-07-22 | 2026-07-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000038 | OC-SCR-000545 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-07-22 | 2026-08-02 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000033 | OC-SCR-000546 | 00 | REH-MDU - Wadi Yemm -Adding new drainage shaft in ground slab of part 3- Plot 1024 | 1024 | 2026-07-22 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000040 | OC-SCR-000547 | 00 | REH-MDU - Wadi Yemm - Plot-1036 Typical staircase landing slab opening | 1036 | 2026-07-22 | 2026-07-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000039 | OC-SCR-000549 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – STAIRS ISSUES | 1022 | 2026-07-22 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000022 | OC-SCR-000550 | 00 | REH-MDU - Wadi Yemm - Clarification Required – in SCR num.(REH-MD01-MDU-ST-OC-Hil-1060-SCR-000020) (Plot 1060) | 1060 | 2026-07-22 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000023 | OC-SCR-000551 | 00 | REH-MDU - Wadi Yemm - Clarification Required – in SCR num.(REH-MD01-MDU-ST-OC-Hil-1060-SCR-000019) (Plot 1060) | 1060 | 2026-07-22 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000024 | OC-SCR-000552 | 00 | REH-MDU - Wadi Yemm - Clarification Required for the punching details in foundation (Plot 1060) | 1060 | 2026-07-22 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000116 | OC-SCR-000555 | 00 | REH-MDU - Wadi Yemm - CONFLICT BETWEEN PLAN PUNCHING DETAIL AND TABLE | 1029 | 2026-07-23 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000040 | OC-SCR-000557 | 00 | REH-MDU - Wadi Yemm - STRUCTURAL CLARIFICATIONS – Super Plot 06, Plot 1022 | 1022 | 2026-07-26 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000117 | OC-SCR-000560 | 00 | REH-MDU - Wadi Yemm -Clarification Regarding Landing Elevation and Stair Starter Bar location | 1029 | 2026-07-26 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000025 | OC-SCR-000563 | 00 | REH-MDU - Wadi Yemm - Clarification Required – in SCR num.(Hil-1060-SCR-000019)&(Hil-1060-SCR-000012) (Plot 1060) | 1060 | 2026-07-26 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000015 | OC-SCR-000564 | 00 | REH-MDU - Wadi Yemm - Light house - Ground columns conflict | 1043 | 2026-07-26 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000034 | OC-SCR-000566 | 00 | REH-MDU - Wadi Yemm - Proposal for Beam Depth Modification at part 06 to Achieve Uniform Soffit Level | 1024 | 2026-07-26 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000041 | OC-SCR-000567 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-07-27 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000118 | OC-SCR-000568 | 00 | REH-MDU - Wadi Yemm - CLARIFY BEAM SUPPORT AND LEVEL. | 1029 | 2026-07-27 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000015 | OC-SCR-000575 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Ground - slab discrepancies | 1021 | 2026-07-27 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000022 | OC-SCR-000576 | 00 | REH-MDU - Wadi Yemm - Coordination Issues and Drawing Discrepancies in Ground FLOOR at Plot -1026 | 1026 | 2026-07-27 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000119 | OC-SCR-000577 | 00 | REH-MDU - Wadi Yemm - CLARIFY EXPANSION JOINT AND ITS SUPPORT. | 1029 | 2026-07-27 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000035 | OC-SCR-000578 | 00 | REH-MDU - Wadi Yemm - Conflict and Missing Data in Str. Design DWG. For Second Level Plot 1024 | 1024 | 2026-07-27 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000014 | OC-SCR-000579 | 00 | REH-MDU - Wadi Yemm - Fortaleza (Plot 1027) – Clarification of Structural Reinforcement and Ramp Beam Discrepancies | 1027 | 2026-07-27 | 2026-07-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000120 | OC-SCR-000580 | 00 | REH-MDU - Wadi Yemm - CLARIFY MISSED EXPANSION JOINT. | 1029 | 2026-07-27 | 2026-07-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000016 | OC-SCR-000588 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Basement 01 - pools . | 1021 | 2026-07-28 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000036 | OC-SCR-000582 | 00 | REH-MDU - Wadi Yemm - Conflict and Missing Data in Str. Design DWG. For First Level Plot 1024 | 1024 | 2026-07-28 | 2026-07-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000016 | OC-SCR-000583 | 00 | REH-MDU - Wadi Yemm - Light house - Ground Slab descrapincies | 1043 | 2026-07-28 | 2026-08-02 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000042 | OC-SCR-000593 | 00 | REH-MDU - Wadi Yemm - STRUCTURAL CLARIFICATIONS – Super Plot 06 | 1022 | 2026-07-28 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000041 | OC-SCR-000595 | 00 | REH-MDU - Wadi Yemm - Plot-1036 Slab edge coordination | 1036 | 2026-07-28 | 2026-08-02 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000027 | OC-SCR-000594 | 00 | REH-MDU - Wadi Yemm - Conflict Between Tower Crane Opening and Kids Pool Location | 1044 | 2026-07-28 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000121 | OC-SCR-000597 | 00 | REH-MDU - Wadi Yemm - Super Plot 01 - Request for Shop Drawing Proposal – Continuous Beams / Detail Modification | 1029 | 2026-07-29 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000122 | OC-SCR-000603 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Lower Ground Level Structural IFC Drawings For Plot 1034 | 1029 | 2026-07-29 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000017 | OC-SCR-000605 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - first - Conflict in Openings. | 1021 | 2026-07-30 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000043 | OC-SCR-000610 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – PART 15 Ground Slab Coordination Issues | 1022 | 2026-07-30 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000016 | OC-SCR-000611 | 00 | REH-MDU - Wadi Yemm - Plot 1028 -Clarification Required for Beam Type B00 at Ground Level Not Listed in Beam Schedule | 1028 | 2026-07-30 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000044 | OC-SCR-000612 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1022 | 2026-07-30 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000017 | OC-SCR-000613 | 00 | REH-MDU - Wadi Yemm - Light house - Additional RFT Length For Retaining wall | 1043 | 2026-07-30 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000028 | OC-SCR-000614 | 00 | REH-MDU - Wadi Yemm - Clarification of Wall Details and Slab Reinforcement | 1044 | 2026-07-30 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000029 | OC-SCR-000615 | 00 | REH-MDU - Wadi Yemm - Clarification For Beams Details | 1044 | 2026-07-30 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000037 | OC-SCR-000616 | 00 | REH-MDU - Wadi Yemm - Conflict in Beams and Slabs levels in Ground floor- Plot 1024 | 1024 | 2026-07-30 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000018 | OC-SCR-000623 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Conflict and missing data at Ground Floor | 1021 | 2026-07-30 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000023 | OC-SCR-000624 | 00 | REH-MDU - Wadi Yemm - Plot 1026 – 1st Floor – Architectural & Structural Drawing Conflicts | 1026 | 2026-07-30 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000123 | OC-SCR-000629 | 00 | REH-MDU - Wadi Yemm - SP01 - RAMPS' THIKNESS | 1029 | 2026-08-01 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000124 | OC-SCR-000631 | 00 | REH-MDU - Wadi Yemm - 1034 - LANDSCAPE STAIR | 1029 | 2026-08-02 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000125 | OC-SCR-000632 | 00 | REH-MDU - Wadi Yemm - Beam Type Clarification | 1029 | 2026-08-02 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000126 | OC-SCR-000633 | 00 | REH-MDU - Wadi Yemm - Missing Grid at Ramp Area | 1029 | 2026-08-02 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000018 | OC-SCR-000634 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding the Use of Couplers for Columns with Reinforcement Ratio Exceeding 4%- SP07 | 1043 | 2026-08-02 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000006 | OC-SCR-000635 | 00 | REH-MDU - Wadi Yemm - Plot 1025- Super structure stairs | 1025 | 2026-08-02 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000038 | OC-SCR-000637 | 00 | REH-MDU - Wadi Yemm - Slab edge contradictions-second slab - Plot 1024 | 1024 | 2026-08-02 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000008 | OC-SCR-000642 | 00 | REH-MDU - Wadi Yemm - Amphitheater Lower Ground- IFC updated as per comment | 1041 | 2026-08-02 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000039 | OC-SCR-000647 | 00 | REH-MDU - Wadi Yemm - Clarification For Reply of SCR (REH-MD01-MDU-ST-OC-Hil-1024-SCR-000036-00) | 1024 | 2026-08-03 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000024 | OC-SCR-000646 | 00 | REH-MDU - Wadi Yemm - Plot 1026 - Conflict and missing data at Ground Floor | 1026 | 2026-08-03 | 2026-08-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000015 | OC-SCR-000648 | 00 | REH-MDU - Wadi Yemm - Plot 1032- Conflict and missing data at Basemen-01 Floor | 1031 | 2026-08-03 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000016 | OC-SCR-000649 | 00 | REH-MDU - Wadi Yemm - Discrepancies in opening at retaining wall & Façade conflict -1033 L.GR-1031 L.GR&elevation- SP02 | 1031 | 2026-08-03 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000040 | OC-SCR-000651 | 00 | REH-MDU - Wadi Yemm - Plot 1024- Part 2 in 2nd floor - FB153 proposed new width | 1024 | 2026-08-03 | 2026-08-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000127 | OC-SCR-000650 | 00 | REH-MDU - Wadi Yemm -SP01- PLOT 1030 CONFLICTS AND CLARIFICATIONS. | 1029 | 2026-08-03 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000005 | OC-SCR-000652 | 00 | REH-MDU - Wadi Yemm - Missing Door Opening In Stair Cores | 1020 | 2026-08-03 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000006 | OC-SCR-000653 | 00 | REH-MDU - Wadi Yemm - Discrepancies Between 2D DWGS & STR MODELS | 1020 | 2026-08-03 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000128 |  | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 01 plot 1029 | 1029 | 2026-08-03 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000042 | OC-SCR-000658 | 00 | REH-MDU - Wadi Yemm - Plot-1036 COLUMN C70 PART6 | 1036 | 2026-08-03 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000129 | OC-SCR-000664 | 00 | REH-MDU - Wadi Yemm -SP01 - POOLS' STAIR | 1029 | 2026-08-04 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000041 | OC-SCR-000665 | 00 | REH-MDU - Wadi Yemm -Opening &Slab edge contradictions-third slab - Plot 1024 | 1024 | 2026-08-04 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000130 | OC-SCR-000666 | 00 | REH-MDU - Wadi Yemm - conflicts between the beams | 1029 | 2026-08-04 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000131 | OC-SCR-000667 | 00 | REH-MDU - Wadi Yemm - Ramps – Coordination Conflicts and Clarifications | 1029 | 2026-08-04 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000042 | OC-SCR-000669 | 00 | REH-MDU - Wadi Yemm -Missing Areas in Str. Design DWG. For Second Level Plot 1024 | 1024 | 2026-08-04 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000043 | OC-SCR-000668 | 00 | REH-MDU - Wadi Yemm - Plot-1036 GROUND FLOOR STAIRS BASE | 1036 | 2026-08-04 | 2026-08-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000045 | OC-SCR-000671 | 00 | REH-MDU - Wadi Yemm - SP06 - Q4 1045 & Q 1046 - Request for Latest Updated Landscape Package for periority parts | 1022 | 2026-08-04 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000017 | OC-SCR-000672 | 00 | REH-MDU - Wadi Yemm - Plot 1032- Conflict data at Basemen-01 Floor | 1031 | 2026-08-04 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000132 | OC-SCR-000674 | 00 | REH-MDU - Wadi Yemm -SP01 - POOLS' STAIR | 1029 | 2026-08-04 | 2026-08-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000043 | OC-SCR-000676 | 00 | REH-MDU - Wadi Yemm - Clarification on Internal Stairs at ground level- Plot 1024 | 1024 | 2026-08-05 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000133 | OC-SCR-000678 | 00 | REH-MDU - Wadi Yemm - SP01- SLAB TOC CLARIFICATION | 1029 | 2026-08-05 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000046 | OC-SCR-000679 | 00 | REH-MDU - Wadi Yemm - SP06 - Q4 1045 & Q3 1046 - Contradicts of the Drainage System for the Landscape Pools | 1022 | 2026-08-05 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000026 | OC-SCR-000680 | 00 | REH-MDU - Wadi Yemm - Clarification Required – conflicts in columns and axes from foundation to ground floor | 1060 | 2026-08-05 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000134 | OC-SCR-000681 | 00 | REH-MDU - Wadi Yemm - Clarification Required for Slab Support | 1029 | 2026-08-05 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000047 | OC-SCR-000682 | 00 | REH-MDU - Wadi Yemm - STRUCTURAL CLARIFICATIONS – Super Plot 06, Plot 1022 | 1022 | 2026-08-05 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000007 | OC-SCR-000683 | 00 | REH-MDU - Wadi Yemm - Clarification Regarding Structural Levels and Beam Clash at Third & Fourth Floors | 1025 | 2026-08-06 | 2026-08-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000019 | OC-SCR-000684 | 00 | REH-MDU - Wadi Yemm - Light house - Ground Slab descrapincies | 1043 | 2026-08-06 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000008 | OC-SCR-000692 | 00 | REH-MDU - Wadi Yemm - Plot 1025- planted columns supported on slabs | 1025 | 2026-08-06 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000135 | OC-SCR-000696 | 00 | REH-MDU - Wadi Yemm - Beam Connection & Reinforcement Detail | 1029 | 2026-08-06 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000015 | OC-SCR-000711 | 00 | REH-MDU - Wadi Yemm -SP05 -Clarification of RFT for Vertical elements | 1023 | 2026-08-08 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000136 | OC-SCR-000712 | 00 | REH-MDU - Wadi Yemm - CLARIFICATION STATICAL SYSTEM AROUND STAIR SLAB AT GROUND LEVEL (+21.30) | 1029 | 2026-08-09 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000018 | OC-SCR-000714 | 00 | REH-MDU - Wadi Yemm - Plot 1032- Conflict data at Basemen-01 Floor | 1031 | 2026-08-09 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000019 | OC-SCR-000715 | 00 | REH-MDU - Wadi Yemm - Coordination Issues and Drawing Discrepancies in Lower Ground FLOOR at Plot -1031 | 1031 | 2026-08-09 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000025 | OC-SCR-000716 | 00 | REH-MDU - Wadi Yemm - Shaft Contradictions – Plot 1026 – second Floor | 1026 | 2026-08-09 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000137 | OC-SCR-000717 | 00 | REH-MDU - Wadi Yemm - conflicts between the beams | 1029 | 2026-08-09 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000020 | OC-SCR-000718 | 00 | REH-MDU - Wadi Yemm - Plot 1032- Conflict data at Basemen-01 Floor | 1031 | 2026-08-09 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000048 | OC-SCR-000721 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-08-09 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000138 | OC-SCR-000722 | 00 | REH-MDU - Wadi Yemm - ENDED COLUMNS LEVEL | 1029 | 2026-08-09 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000139 | OC-SCR-000726 | 00 | REH-MDU - Wadi Yemm - PLOT 1035-A11 – Stair 03 – Beam Clash with Stair Shaft | 1029 | 2026-08-09 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000021 | OC-SCR-000725 | 00 | REH-MDU - Wadi Yemm - Conflict data in SP02-Plot-1032 | 1031 | 2026-08-09 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000140 | OC-SCR-000727 | 00 | REH-MDU - Wadi Yemm - SP01- BEAM DEPTH MODIFICATION. | 1029 | 2026-08-09 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000005 | OC-SCR-000728 | 00 | REH-MDU - Wadi Yemm - clarification regarding the backfill material to be used under SOG for all plots (ECG-SHAKER) scope of work | XXXX | 2026-08-09 | 2026-08-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000141 | OC-SCR-000730 | 00 | REH-MDU - Wadi Yemm - SP01 – PLOT 1035-C11 – Stair 09 – Clarification of Slab Elevations beyond the door | 1029 | 2026-08-09 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000016 | OC-SCR-000732 | 00 | REH-MDU - Wadi Yemm - SP05-COLUMNS AND AXES AT Ground Level | 1023 | 2026-08-09 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000142 | OC-SCR-000733 | 00 | REH-MDU - Wadi Yemm - THE TYPE AND LEVEL OF UPSTANDS | 1029 | 2026-08-09 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000049 | OC-SCR-000741 | 00 | REH-MDU - Wadi Yemm - STRUCTURAL CLARIFICATIONS – Super Plot 06, Plot 1022 | 1022 | 2026-08-09 | 2026-08-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000050 | OC-SCR-000748 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot (1018 - 1022) | 1022 | 2026-08-10 | 2026-08-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000017 | OC-SCR-000749 | 00 | REH-MDU - Wadi Yemm - SP05-Ground Level Descrapincies | 1023 | 2026-08-10 | 2026-08-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000026 | OC-SCR-000753 | 00 | REH-MDU - Wadi Yemm - Stair case issue in Ground,First FLOOR at Plot -1026 | 1026 | 2026-08-10 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000143 | OC-SCR-000750 | 00 | REH-MDU - Wadi Yemm - STARTER BARS OF RAMP LOCATION | 1029 | 2026-08-10 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000144 | OC-SCR-000751 | 00 | REH-MDU - Wadi Yemm - Clarification Required for Slab Support | 1029 | 2026-08-10 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000027 | OC-SCR-000752 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding the Use of Couplers for Columns with Reinforcement- at 1060 | 1060 | 2026-08-10 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000027 | OC-SCR-000754 | 00 | REH-MDU - Wadi Yemm - Openings Spacing in first FLOOR at Plot -1026 | 1026 | 2026-08-10 | 2026-08-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000145 | OC-SCR-000756 | 00 | REH-MDU - Wadi Yemm - Ramp & Floor Clash & Level Verification Plot 1030 | 1029 | 2026-08-10 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000146 | OC-SCR-000757 | 00 | REH-MDU - Wadi Yemm - Missing Data AND COLUMNS TYPES CHANGED | 1029 | 2026-08-10 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000147 | OC-SCR-000758 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-10 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000015 | OC-SCR-000759 | 00 | REH-MDU - Wadi Yemm - Fortaleza (Plot 1027) – Basement 01 Slab IFC Package – Stair Clarification | 1027 | 2026-08-10 | 2026-08-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000044 | OC-SCR-000761 | 00 | REH-MDU - Wadi Yemm - Plot 1024- Part 1 in First Floor. | 1024 | 2026-08-10 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000148 | OC-SCR-000760 | 00 | REH-MDU - Wadi Yemm - STARTER BARS OF RAMP LOCATION | 1029 | 2026-08-10 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000149 | OC-SCR-000762 | 00 | REH-MDU - Wadi Yemm - REH-MD01-MDU-ST-OC-Hil-1029-SCR-000149 | 1029 | 2026-08-11 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000007 | OC-SCR-000763 | 00 | REH-MDU - Wadi Yemm - 1020 Boutrique - Punching Shear Reinforcement and Wall Link Detail Clarification | 1020 | 2026-08-11 | 2026-08-12 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000016 | OC-SCR-000764 | 00 | REH-MDU - Wadi Yemm - The Fortaleza 1027 - Confirmation of Punching Shear Reinforcement Detail | 1027 | 2026-08-11 | 2026-08-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000150 | OC-SCR-000766 | 00 | REH-MDU - Wadi Yemm - Plot 1030 - Shifted axes | 1029 | 2026-08-11 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000151 | OC-SCR-000772 | 00 | REH-MDU - Wadi Yemm - SP01- BEAM TYPE CONFLICT & SLAB INFORMATION CLARIFICATION | 1029 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000022 | OC-SCR-000771 | 00 | REH-MDU - Wadi Yemm - Plot 1031- Conflict in Columns Dimensions between Plans & Schedules | 1031 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000152 | OC-SCR-000773 | 00 | REH-MDU - Wadi Yemm - The existing of LandScape Stairs at Ground Floor Plot 1035 | 1029 | 2026-08-12 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000051 | OC-SCR-000774 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000153 | OC-SCR-000776 | 00 | REH-MDU - Wadi Yemm - conflicts between the beams and t.o.c for hatched slab | 1029 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000154 | OC-SCR-000777 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000155 | OC-SCR-000778 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000156 | OC-SCR-000785 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-08-12 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000020 | OC-SCR-000786 | 00 | REH-MDU - Wadi Yemm - Light house - Protection layer around Columns inside water tank | 1043 | 2026-08-12 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000157 | OC-SCR-000787 | 00 | REH-MDU - Wadi Yemm - CONFLICT BETWEEN R.W ENDED LEVEL AND SLAB LEVEL (PLOT 1030) | 1029 | 2026-08-12 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000158 | OC-SCR-000789 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000023 | OC-SCR-000792 | 00 | REH-MDU - Wadi Yemm - Plot 1032- Conflict data at Basement-01 Floor | 1031 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000052 | OC-SCR-000795 | 00 | REH-MDU - Wadi Yemm - SP06 - Q1045 - PART 16 GROUND FLOOR SLAB COORDINATION ISSUES | 1022 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000028 | OC-SCR-000796 | 00 | REH-MDU - Wadi Yemm - asking for approvel | 1026 | 2026-08-13 | 2026-08-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000159 | OC-SCR-000797 | 00 | REH-MDU - Wadi Yemm - PLOT 1035-BUILDING C-FIRST FLOOR | 1029 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000160 | OC-SCR-000798 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000024 | OC-SCR-000800 | 00 | REH-MDU - Wadi Yemm - Plot 1033- Inquiry about structural condition of a footing. | 1031 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000053 | OC-SCR-000801 | 00 | REH-MDU - Wadi Yemm - STRUCTURAL CLARIFICATIONS – Super Plot 06, Plot 1022 | 1022 | 2026-08-13 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000008 | OC-SCR-000803 | 00 | REH-MDU - Wadi Yemm - CLARIFICATIONS FOR MISSING DATA | 1020 | 2026-08-13 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000028 | OC-SCR-000804 | 00 | REH-MDU - Wadi Yemm - Plot 1060 – Ramp Type 02 – Beam overlapping at Basement02 & Basement 03 levels | 1060 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000025 | OC-SCR-000805 | 00 | REH-MDU - Wadi Yemm - Plot 1033- Clarification Regarding Lower Ground Beams | 1031 | 2026-08-13 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000161 | OC-SCR-000807 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-08-13 | 2026-08-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000054 | OC-SCR-000812 | 00 | REH-MDU - Wadi Yemm - SP06 – Q3 1046 – Part 19&22 – Clarification of Ground Slab Coordination Issues | 1022 | 2026-08-13 | 2026-08-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000017 | OC-SCR-000813 | 00 | REH-MDU - Wadi Yemm - The Fortaleza 1027 - Request for Basement 02 Slab Reinforcement Details | 1027 | 2026-08-13 | 2026-08-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000162 | OC-SCR-000814 | 00 | REH-MDU - Wadi Yemm - Clarification of T.O.C. of Attic Slab and conflicts between Surrounding Beams | 1029 | 2026-08-16 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000045 | OC-SCR-000816 | 00 | REH-MDU - Wadi Yemm - Missing Beams Type and Level in Str. Design DWG. For First Level Plot 1024 | 1024 | 2026-08-16 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000163 | OC-SCR-000817 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-16 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000029 | OC-SCR-000818 | 00 | REH-MDU - Wadi Yemm - Staircase Issue at Ground and First Floors – Plot 1026 | 1026 | 2026-08-16 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000164 | OC-SCR-000819 | 00 | REH-MDU - Wadi Yemm - Missing Data | 1029 | 2026-08-16 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000165 | OC-SCR-000825 | 00 | REH-MDU - Wadi Yemm - SP01 - Pool stairs | 1029 | 2026-08-17 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000166 | OC-SCR-000824 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-17 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000167 | OC-SCR-000823 | 00 | REH-MDU - Wadi Yemm - Missing Data and conflect with architectural drawings | 1029 | 2026-08-17 | 2026-08-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000055 | OC-SCR-000827 | 00 | REH-MDU - Wadi Yemm - Landscape Walls,stairs &ramps – Clarification for super plot 6 (1046-1045-1022-1018) | 1022 | 2026-08-17 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000056 | OC-SCR-000826 | 00 | REH-MDU - Wadi Yemm - RFI – Stair No. 6 Landing Extension and Handrail PLOT 1046 | 1022 | 2026-08-17 | 2026-08-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000021 | OC-SCR-000822 | 00 | REH-MDU - Wadi Yemm - Light house - SIKKA Road Retaining wall RFT details | 1043 | 2026-08-17 | 2026-08-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000168 | OC-SCR-000834 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-17 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000169 | OC-SCR-000833 | 00 | REH-MDU - Wadi Yemm - PLOT 1035-BUILDING B-FIRST FLOOR | 1029 | 2026-08-17 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000170 | OC-SCR-000836 | 00 | REH-MDU - Wadi Yemm - Conflicts between the beams and t.o.c for slab | 1029 | 2026-08-17 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000171 | OC-SCR-000838 | 00 | REH-MDU - Wadi Yemm - PLOT 1035-BUILDING B-FIRST FLOOR | 1029 | 2026-08-17 | 2026-08-19 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000022 | OC-SCR-000839 | 00 | REH-MDU - Wadi Yemm - Light house - Elevator Pit and added upstands dimensions | 1043 | 2026-08-17 | 2026-08-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000009 | OC-SCR-000850 | 00 | REH-MDU - Wadi Yemm - CLARIFICATIONS FOR MISSING DATA | 1020 | 2026-08-18 | 2026-08-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000172 | OC-SCR-000854 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-19 | 2026-08-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000173 | OC-SCR-000859 | 00 | REH-MDU - Wadi Yemm -PLOT 1034-BUILDING C-FIRST FLOOR | 1029 | 2026-08-19 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000174 | OC-SCR-000864 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-19 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000175 | OC-SCR-000865 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-08-19 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000176 | OC-SCR-000869 | 00 | REH-MDU - Wadi Yemm -Technical Proposal – Proposed Solution for Over-Poured Columns- Plot 1037 - part 25 | 1029 | 2026-08-19 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000057 | OC-SCR-000863 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-08-19 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000058 | OC-SCR-000868 | 00 | REH-MDU - Wadi Yemm - Subject: Concrete Slab Construction Between Plot 1018 and Plot 1022 – Level Differences | 1022 | 2026-08-19 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000046 | OC-SCR-000870 | 00 | REH-MDU - Wadi Yemm - Clarification of Slab Thickness | 1024 | 2026-08-19 | 2026-08-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000026 | OC-SCR-000866 | 00 | REH-MDU - Wadi Yemm - Expansion Joint at SP02 & RAMP Plot 1031 | 1031 | 2026-08-19 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000029 | OC-SCR-000867 | 00 | REH-MDU - Wadi Yemm - Plot 1060 – Ramp Type 01 – Beams overlapping | 1060 | 2026-08-19 | 2026-08-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000018 | OC-SCR-000878 | 00 | REH-MDU - Wadi Yemm - SP05-Lower Ground Level Descrapincies | 1023 | 2026-08-19 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000177 | OC-SCR-000879 | 00 | REH-MDU - Wadi Yemm - Proposed Structural Modification – Replacement of Wall with RC Beam - Plot 1037 - part 23 | 1029 | 2026-08-19 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000059 | OC-SCR-000880 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06-Plot 1018 | 1022 | 2026-08-19 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000019 | OC-SCR-000883 | 00 | REH-MDU - Wadi Yemm - SP05 -Coordination Discrepancies Between Structural IFC and Architectural Package | 1023 | 2026-08-20 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000178 | OC-SCR-000884 | 00 | REH-MDU - Wadi Yemm - SP05 -SP01- BEAM & SLAB OPENINGS CONFLICT CLARIFICATION | 1029 | 2026-08-20 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000179 | OC-SCR-000887 | 00 | REH-MDU - Wadi Yemm - conflicts between the columns | 1029 | 2026-08-20 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000027 | OC-SCR-000888 | 00 | REH-MDU - Wadi Yemm - Levels Naming Conflict -1032 - SP02 | 1031 | 2026-08-20 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000180 | OC-SCR-000890 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-08-20 | 2026-08-25 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000023 | OC-SCR-000891 | 00 | REH-MDU - Wadi Yemm - Light house - Balancing Tank height | 1043 | 2026-08-20 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000018 | OC-SCR-000893 | 00 | REH-MDU - Wadi Yemm - Walls – Clarification for Fortaleza Hotel | 1027 | 2026-08-20 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000060 | OC-SCR-000900 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06-Plot 1018 | 1022 | 2026-08-20 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000061 | OC-SCR-000903 | 00 | REH-MDU - Wadi Yemm - Carifications at super plot 06-Plot 1018 | 1022 | 2026-08-22 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000181 | OC-SCR-000909 | 00 | REH-MDU - Wadi Yemm - PLOT 1035 - SUNKEN SLAB CONFLICT | 1029 | 2026-08-23 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000009 | OC-SCR-000910 | 00 | REH-MDU - Wadi Yemm - Amphitheatre Lower Ground IFC – Missing Levels and Slab Thickness | 1041 | 2026-08-23 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000182 | OC-SCR-000911 | 00 | REH-MDU - Wadi Yemm - Clarification Required – Slab and Backfilling Arrangement ¦ Plot 1037 Parts 24 & 25 | 1029 | 2026-08-23 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000009 | OC-SCR-000912 | 00 | REH-MDU - Wadi Yemm - Plot 1025- Super structure floors coordination | 1025 | 2026-08-23 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000010 | OC-SCR-000918 | 00 | REH-MDU - Wadi Yemm - Amphitheatre 1041 Foundation Level Revision from +0.85 m to +0.90 m | 1041 | 2026-08-24 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000014 | OC-SCR-000920 | 00 | REH-MDU - Wadi Yemm - Discrepancy in Column existing on grid( CO,CN &222) in Structre design drawings. | 1047 | 2026-08-24 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000183 | OC-SCR-000921 | 00 | REH-MDU - Wadi Yemm - PLOT 1029 - COLUMN CLARIFICATION | 1029 | 2026-08-24 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000062 | OC-SCR-000922 | 00 | REH-MDU - Wadi Yemm - Concrete Slab Construction Between Plot 1018 and Plot 1022 – Level Differences | 1022 | 2026-08-24 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000063 | OC-SCR-000923 | 00 | REH-MDU - Wadi Yemm - SP06 – Q3 1046 – Part 19– Clarification of Ground Slab and columns Coordination Issues | 1022 | 2026-08-24 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000011 | OC-SCR-000925 | 00 | REH-MDU - Wadi Yemm - Amphitheatre 1041 Lower Ground Slab – Structural Clarifications | 1041 | 2026-08-24 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000064 | OC-SCR-000926 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1045&1046 - Reinforcement details for the pools overflow system | 1022 | 2026-08-24 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000012 | OC-SCR-000930 | 00 | REH-MDU - Wadi Yemm - Discrepancies and Clarifications for Drop Panels, Planted Columns, Planter Walls, Beams, and Openings Alignment | 1041 | 2026-08-25 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000024 | OC-SCR-000935 | 00 | REH-MDU - Wadi Yemm - Light house - Basement 02 SOG Discrepancies | 1043 | 2026-08-25 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000020 | OC-SCR-000938 | 00 | REH-MDU - Wadi Yemm - SP05-Upper Ground Level Descrapincies | 1023 | 2026-08-25 | 2026-09-02 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000010 | OC-SCR-000939 | 00 | REH-MDU - Wadi Yemm - Confirmation of RFT Details at Raft and Retaining Wall Connection | 1020 | 2026-08-26 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000013 | OC-SCR-000940 | 00 | REH-MDU - Wadi Yemm - Amphitheatre 1041 Tank Walls and Retaining walls – Structural Clarifications | 1041 | 2026-08-26 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000019 | OC-SCR-000942 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Stair 8 - Finishing Thickness | 1021 | 2026-08-26 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000044 | OC-SCR-000943 | 00 | REH-MDU - Wadi Yemm - Plot-1036 SECOND FLOOR BEAM CLARIFICATION | 1036 | 2026-08-26 | 2026-08-26 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000184 | OC-SCR-000944 | 00 | REH-MDU - Wadi Yemm - PLOT 1035-BUILDING B-FIRST FLOOR | 1029 | 2026-08-26 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000028 | OC-SCR-000945 | 00 | REH-MDU - Wadi Yemm - Clarify l type OF structure framing | 1031 | 2026-08-26 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000047 | OC-SCR-000947 | 00 | REH-MDU - Wadi Yemm - Missing Water stop in Tank of Ground Level Plot 1024 | 1024 | 2026-08-26 | 2026-08-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000020 | OC-SCR-000950 | 00 | REH-MDU - Wadi Yemm - Plot 1021 - Ground Floor - Stair Levels | 1021 | 2026-08-26 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000048 | OC-SCR-000951 | 00 | REH-MDU - Wadi Yemm - stair 2 statical system clarification on grids (FM,FN AND 526,528) | 1024 | 2026-08-26 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000185 | OC-SCR-000952 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-08-26 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000025 | OC-SCR-000953 | 00 | REH-MDU - Wadi Yemm - Light house - Core 06 door opening | 1043 | 2026-08-26 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000030 | OC-SCR-000955 | 00 | REH-MDU - Wadi Yemm - Request for Clarification Regarding Discrepancies Between IFC Drawings – Plot 1060 | 1060 | 2026-08-26 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000065 | OC-SCR-000956 | 00 | REH-MDU - Wadi Yemm - SP06 - Q1045 - PART 15&16 GROUND FLOOR SLAB COORDINATION ISSUES | 1022 | 2026-08-26 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000186 | OC-SCR-000958 | 00 | REH-MDU - Wadi Yemm - conflicts between the PC Columns for plot 1030 building A | 1029 | 2026-08-26 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000015 | OC-SCR-000966 | 00 | REH-MDU - Wadi Yemm - A proposal for the ID of the column existing on grid( CO,CN & 222) | 1047 | 2026-08-29 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000021 | OC-SCR-000978 | 00 | REH-MDU - Wadi Yemm - SP05 -Beams Interferrence in Floor and Ramp - B1 | 1023 | 2026-08-30 | 2026-09-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000187 | OC-SCR-000979 | 00 | REH-MDU - Wadi Yemm - PLOT 1030 - RAMP BEAMS | 1029 | 2026-08-30 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000049 | OC-SCR-000981 | 00 | REH-MDU - Wadi Yemm - Missing Data and Conflict in Ground Level Plot 1024 | 1024 | 2026-08-30 | 2026-08-31 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000014 | OC-SCR-000982 | 00 | REH-MDU - Wadi Yemm - Amphitheatre Lower Ground IFC – Stair Level Clarifications | 1041 | 2026-08-31 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000015 | OC-SCR-000983 | 00 | REH-MDU - Wadi Yemm - Amphitheatre Lower Ground IFC – Ramp Structural Details | 1041 | 2026-08-31 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000066 | OC-SCR-000992 | 00 | REH-MDU - Wadi Yemm -SP06 - PLOT 1045&1046 - CONFLICT BETWEEN ARCH AND STR IFC DRAWINGS | 1022 | 2026-08-31 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000188 | OC-SCR-000993 | 00 | REH-MDU - Wadi Yemm - SP01- PLOT 1030 - The clear distance between the adjacent slabs | 1029 | 2026-09-01 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000189 |  | 00 | REH-MDU - Wadi Yemm - SP01- PLOT 1030 - Confirmation of Beam Supporting PC Column – Beam Type & TOC | 1029 | 2026-09-01 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000190 | OC-SCR-000996 | 00 | REH-MDU - Wadi Yemm - SP01- Plot 1037 - GROUND FLOOR | 1029 | 2026-09-01 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000191 | OC-SCR-001006 | 00 | REH-MDU - Wadi Yemm - SP01- Plot 1037 - GROUND FLOOR | 1029 | 2026-09-01 | 2026-09-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000067 | OC-SCR-001000 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1045&1046 - Conflict in the planter wall at pool | 1022 | 2026-09-01 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000030 | OC-SCR-001001 | 00 | REH-MDU - Wadi Yemm - Clarify location and type for structure framing | 1026 | 2026-09-01 | 2026-09-03 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000016 | OC-SCR-001009 | 00 | REH-MDU - Wadi Yemm - Amphitheatre Replacement soil Below Foundation Plain conccrete | 1041 | 2026-09-02 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000022 | OC-SCR-001011 | 00 | REH-MDU - Wadi Yemm - SP05 -Beams Interferrence in Floor and Ramp - B1 after reply of SCR #21 | 1023 | 2026-09-02 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000068 | OC-SCR-001015 | 00 | REH-MDU - Wadi Yemm - Concrete Slab Construction Between Plot 1018 and Plot 1022 – Level Differences | 1022 | 2026-09-02 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000192 | OC-SCR-001030 | 00 | REH-MDU - Wadi Yemm - PLOT 1034-Lower Ground Slab | 1029 | 2026-09-02 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000069 | OC-SCR-001031 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-09-02 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000193 | OC-SCR-001032 | 00 | REH-MDU - Wadi Yemm - PLOT 1037-Lower Ground Slab | 1029 | 2026-09-02 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000021 | OC-SCR-001037 | 00 | REH-MDU - Wadi Yemm - Plot 1021 -Tank Levels | 1021 | 2026-09-03 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000029 | OC-SCR-001036 | 00 | REH-MDU - Wadi Yemm - Plot -1031- Ground Foor Plans | 1031 | 2026-09-03 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000070 | OC-SCR-001038 | 00 | REH-MDU - Wadi Yemm - SP06 – Q3 1046 – Kids Pool Design conflict | 1022 | 2026-09-03 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000071 | OC-SCR-001040 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – Part 16 clarifications | 1022 | 2026-09-03 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000031 | OC-SCR-001041 | 00 | REH-MDU - Wadi Yemm - First Floor – Terraces – Dropped Panels | 1026 | 2026-09-03 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000194 | OC-SCR-001042 | 00 | REH-MDU - Wadi Yemm - Clarification Required – Slab and Backfilling Arrangement ¦ SP01- Plot 1037 Parts 24 & 25 after reply of SCR #182 | 1029 | 2026-09-03 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000072 | OC-SCR-001044 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-09-03 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000023 | OC-SCR-001050 | 00 | REH-MDU - Wadi Yemm - SP05 -Basement1 slab Main mesh and additional RFT clarification | 1023 | 2026-09-06 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000050 | OC-SCR-001051 | 00 | REH-MDU - Wadi Yemm - Proposal for Anchoring Reinforcement for Staircase Supporting Beams into poured Core Walls and Columns | 1024 | 2026-09-06 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000019 | OC-SCR-001052 | 00 | REH-MDU - Wadi Yemm - Fortaleza – Ground Slab IFC – Structural Clarifications | 1027 | 2026-09-06 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000195 | OC-SCR-001053 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding (SCR) - First Level Structural IFC Drawings For Plot 1030 | 1029 | 2026-09-06 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000196 | OC-SCR-001054 | 00 | REH-MDU - Wadi Yemm - PLOT 1029 - BRIDGE EXPANSION CONFLICT | 1029 | 2026-09-06 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000197 | OC-SCR-001055 | 00 | REH-MDU - Wadi Yemm - PLOT 1029 - MISSING DROP PANEL SOLUTION | 1029 | 2026-09-06 | 2026-09-09 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000198 | OC-SCR-001056 | 00 | REH-MDU - Wadi Yemm - PLOT 1029 - MISSING PC TYPES | 1029 | 2026-09-06 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000031 | OC-SCR-001057 | 00 | REH-MDU - Wadi Yemm - Plot 1060 – Sump pits / Walls clash & Floor drains | 1060 | 2026-09-06 | 2026-09-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000026 | OC-SCR-001058 | 00 | REH-MDU - Wadi Yemm - Light house - SP07 - Updated IFC For Lower Ground Columns & Axes Descrapincies | 1043 | 2026-09-06 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000027 | OC-SCR-001059 | 00 | REH-MDU - Wadi Yemm - Light house - SP07 - Stairs Descrapincies | 1043 | 2026-09-06 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000199 | OC-SCR-001070 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-09-06 | 2026-09-08 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000200 | OC-SCR-001073 | 00 | REH-MDU - Wadi Yemm - MISSING DATA – BEAMS TYPES & BEAMS DEPTH NEED CLARIFICATIONS ¦ SP01- Plot 1037 | 1029 | 2026-09-07 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000073 | OC-SCR-001075 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – Planter walls missing levels | 1022 | 2026-09-07 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000074 | OC-SCR-001076 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – PART 14 - STORAGE ROOM OPENING | 1022 | 2026-09-07 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000201 | OC-SCR-001077 | 00 | REH-MDU - Wadi Yemm - Clarify the column type at Plot 1030, Building C | 1029 | 2026-09-07 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000202 | OC-SCR-001078 | 00 | REH-MDU - Wadi Yemm - MISSING DATA – BEAMS NEED CLARIFICATIONS ¦ SP01- Plot 1037 | 1029 | 2026-09-07 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000075 | OC-SCR-001082 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1046 - Building (B) - Clashes and Discrepancies | 1022 | 2026-09-07 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000076 | OC-SCR-001087 | 00 | REH-MDU - Wadi Yemm - SP06 – Q4 1045 – PART 16 - Door Opening at Ground Floor Stair. 04 Core | 1022 | 2026-09-08 | 2026-10-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000203 | OC-SCR-001088 | 00 | REH-MDU - Wadi Yemm - Clarification of Column Positions at Plot 1030, Building B – First Level | 1029 | 2026-09-08 | 2026-09-10 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000029 | OC-SCR-001108 | 00 | REH-MDU - Light house - Lower Ground Discrepancies | 1043 | 2026-09-08 | 2026-09-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000077 |  | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1046 - Building (A) - Clashes and Discrepancies | 1022 | 2026-09-08 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000078 | OC-SCR-001102 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1046 - Building (C) - Clashes and Discrepancies | 1022 | 2026-09-08 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000024 | OC-SCR-001103 | 00 | REH-MDU - Wadi Yemm - SP05 -Basement1 and Ground Level Stairs RFT clarification | 1023 | 2026-09-08 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000010 | OC-SCR-001104 | 00 | REH-MDU - Wadi Yemm - Clarification Required For The Planted Columns at the Fourth Floor | 1025 | 2026-09-08 | 2026-09-13 | Responded
| REH-MD01-MDU-ST-OC-HILL-1029-SCR-000204 |  | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1029-BUILDING A | 1029 | 2026-09-08 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-HILL-1029-SCR-000205 |  | 00 | REH-MDU - Wadi Yemm - Ramp Beams and Slab Beams conflict – Clarification - plot 1030 | 1029 | 2026-09-08 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000028 | OC-SCR-001107 | 00 | REH-MDU - Wadi Yemm - Light house - Basement 02 SOG Discrepancies | 1043 | 2026-09-08 | 2026-09-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000020 | OC-SCR-001111 | 00 | REH-MDU - Wadi Yemm - Fortaleza Hotel – Stair Landing & Floor Finish Level Coordination | 1027 | 2026-09-09 | 2026-09-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000206 | OC-SCR-001112 | 00 | REH-MDU - Wadi Yemm - Clarification of Column Positions at Plot 1030, Building C – First Level | 1029 | 2026-09-09 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000016 | OC-SCR-001114 | 00 | REH-MDU - Wadi Yemm - conflect between column table and floors plane | 1047 | 2026-09-09 | 2026-09-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000207 | OC-SCR-001115 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1029-BUILDING B | 1029 | 2026-09-09 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000208 | OC-SCR-001116 | 00 | REH-MDU - Wadi Yemm - PLOT 1034-Lower Ground&GROUND SlabS | 1029 | 2026-09-09 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000209 | OC-SCR-001117 | 00 | REH-MDU - Wadi Yemm - PLOT 1034-Lower Ground&GROUND SlabS | 1029 | 2026-09-09 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000030 | OC-SCR-001120 | 00 | REH-MDU - Wadi Yemm - Light house - SP07 - Basement 01 Descrapincies. | 1043 | 2026-09-10 | 2026-09-14 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000079 | OC-SCR-001121 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1018 - Stairs Clarifications | 1022 | 2026-09-10 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000210 | OC-SCR-001122 | 00 | REH-MDU - Wadi Yemm - Clarification of Column Positions at Plot 1037, Building B –Columns from first to second Level | 1029 | 2026-09-10 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000211 | OC-SCR-001123 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1029-BUILDING B | 1029 | 2026-09-10 | 2026-09-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000030 | OC-SCR-001125 | 00 | REH-MDU - Wadi Yemm - Plot 1031- beams Conflict at Lower Ground floor Plans | 1031 | 2026-09-10 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000080 | OC-SCR-001126 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-09-10 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000051 | OC-SCR-001127 | 00 | REH-MDU - Wadi Yemm - Fire Tank – Walls Top Level | 1024 | 2026-09-10 | 2026-09-13 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000021 | OC-SCR-001128 | 00 | REH-MDU - Wadi Yemm - Fortaleza – Basement Slab IFC – Beam Type and Details Clarification | 1027 | 2026-09-10 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000212 | OC-SCR-001129 | 00 | REH-MDU - Wadi Yemm - Beams and Slab openning conflict – Clarification - plot 1030 | 1029 | 2026-09-12 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000081 | OC-SCR-001130 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022-Discrepancy Between Revit model & IFC 2D PKG | 1022 | 2026-09-12 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000052 | OC-SCR-001134 | 00 | REH-MDU - Wadi Yemm - Discrepancy in Part 04 - 1st floor | 1024 | 2026-09-13 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000031 | OC-SCR-001137 | 00 | REH-MDU - Wadi Yemm - Plot 1032- Conflict and missing data at lower ground Floor | 1031 | 2026-09-13 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000032 | OC-SCR-001138 | 00 | REH-MDU - Wadi Yemm - Plot 1031- Discrepancies at Lower Ground floor Plans | 1031 | 2026-09-13 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000082 | OC-SCR-001140 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1018 - Building (A) - Level 01 Clashes and Discrepancies | 1022 | 2026-09-13 | 2026-09-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000006 | OC-SCR-001143 | 00 | REH-MDU - Wadi Yemm - S.O.G Design – Proposal for Standardized Detail Across DP1 for all plots (ECG-SHAKER) scope of work | XXXX | 2026-09-13 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000213 | OC-SCR-001146 | 00 | REH-MDU - Wadi Yemm - Clarification Required – Slab and Backfilling Arrangement ¦ Plot 1037 Parts 24 & 25 | 1029 | 2026-09-14 | 2026-09-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000214 | OC-SCR-001147 | 00 | REH-MDU - Wadi Yemm - PLOT 1034-Lower Ground&GROUND SlabS | 1029 | 2026-09-14 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000215 | OC-SCR-001148 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - First Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-09-14 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000216 | OC-SCR-001149 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - Ground Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-09-14 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000032 | OC-SCR-001162 | 00 | REH-MDU - Wadi Yemm - Clarification Request Regarding Missing/Cancelled Sump Pits – Plot 1060 | 1060 | 2026-09-14 | 2026-09-15 | Responded
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000022 | OC-SCR-001169 | 00 | REH-MDU - Wadi Yemm - Structural Coordination Discrepancies and Clarifications for Beams, Ramps, Attic Boundaries, Openings, and Staircase Framing | 1027 | 2026-09-15 | 2026-09-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000053 | OC-SCR-001173 | 00 | REH-MDU - Wadi Yemm - Updates in Str. Design for First Floor Plot 1024 Dated 14-9-2026 | 1024 | 2026-09-15 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000054 | OC-SCR-001174 | 00 | REH-MDU - Wadi Yemm - proposal for construction joint between axis (FAA,FAR AND 512,523) first floor | 1024 | 2026-09-15 | 2026-09-16 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000083 | OC-SCR-001175 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1046 - Building (D) - Clashes and Discrepancies | 1022 | 2026-09-15 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000055 | OC-SCR-001176 | 00 | REH-MDU - Wadi Yemm - Confirmation Required for Highlighted Beam at Stair 5-part 6 | 1024 | 2026-09-15 | 2026-09-17 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000017 | OC-SCR-001183 | 00 | REH-MDU - Wadi Yemm - Amphitheatre - Clarification Required – Staircase Concrete Thickness at Cores | 1041 | 2026-09-15 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000084 | OC-SCR-001186 | 00 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-09-16 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000085 | OC-SCR-001199 | 00 | REH-MDU - Wadi Yemm - SP06 - Plot 1046 - Building (D) - L02 - Clashes and Discrepancies | 1022 | 2026-09-16 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000031 | OC-SCR-001200 | 00 | REH-MDU - Wadi Yemm - Light house - Foundation and Basement 02 S.O.G. Clarifications | 1043 | 2026-09-16 | 2026-09-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000217 | OC-SCR-001202 | 00 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - First Level and Second Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-09-17 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000025 | OC-SCR-001212 | 00 | REH-MDU - Wadi Yemm - SP05-Basement Level Descrapincies | 1023 | 2026-09-17 | 2026-09-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000056 | OC-SCR-001214 | 00 | REH-MDU - Wadi Yemm - Conflict and Missing Data in Str. Design DWG. For First Level Plot 1024 | 1024 | 2026-09-17 | 2026-09-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000086 | OC-SCR-001219 | 00 | REH-MDU - Wadi Yemm - SP06 - PLOT 1045&1046 - Landscape Stairs Clarifications | 1022 | 2026-09-17 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000087 | OC-SCR-001227 | 0 | REH-MDU - Wadi Yemm - Subject: Conflict between column scheduel & IFC plan | 1022 | 2026-09-17 | 2026-09-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000033 | OC-SCR-001229 | 0 | REH-MDU - Wadi Yemm - Clarification of Core Type 15 Reference | 1060 | 2026-09-19 | 2026-09-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000032 | OC-SCR-001230 | 0 | REH-MDU - Wadi Yemm - First Floor – Clarifications | 1026 | 2026-09-19 | 2026-09-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000033 | OC-SCR-001231 | 0 | REH-MDU - Wadi Yemm - First Floor – Clarifications | 1026 | 2026-09-19 | 2026-09-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000088 | OC-SCR-001239 | 0 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-09-19 | 2026-09-20 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000017 | OC-SCR-001240 | 0 | REH-MDU - Wadi Yemm - First level - Part 03 - Coordination | 1047 | 2026-09-19 | 2026-09-21 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000218 | OC-SCR-001241 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1035-BUILDING A | 1029 | 2026-09-20 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000219 | OC-SCR-001243 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - First and Second Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-09-20 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000220 | OC-SCR-001244 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1035-BUILDING B | 1029 | 2026-09-20 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000221 | OC-SCR-001245 | 0 | REH-MDU - Wadi Yemm - Clarification Required ¦ BEAMS ¦ LOWER GROUND ¦ Plot 1034 Part 19 | 1029 | 2026-09-20 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000026 | OC-SCR-001255 | 0 | REH-MDU - Wadi Yemm - SP05-Basement 01 Level Descrapincies | 1023 | 2026-09-20 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000018 | OC-SCR-001257 | 0 | REH-MDU - Wadi Yemm - Proposal: Alignment of Identical Beams with Ramp | 1047 | 2026-09-20 | 2026-09-22 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000222 | OC-SCR-001259 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1035-BUILDING c | 1029 | 2026-09-21 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1028-SCR-000017 | OC-SCR-001263 | 0 | REH-MDU - Wadi Yemm - Plot 1028 -Clarification Required for Missing Structural Information and discrepancies – Fifth and Roof Floors | 1028 | 2026-09-21 | 2026-09-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000034 | OC-SCR-001264 | 0 | REH-MDU - Wadi Yemm - First Floor – slab edge clarifications beams & expantion joints | 1026 | 2026-09-21 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1041-SCR-000018 | OC-SCR-001265 | 0 | REH-MDU - Wadi Yemm - Amphitheatre - Amphitheatre Foundation Level inside the sea | 1041 | 2026-09-21 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000089 | OC-SCR-001281 | 0 | REH-MDU - Wadi Yemm - CLARIFICATIONS FOR CONCRETE DIMENSIONS PART1-LEVEL02-PLOT 1022 | 1022 | 2026-09-22 | 2026-09-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000223 | OC-SCR-001282 | 0 | REH-MDU - Wadi Yemm - SP01 - SLAB DEPRESSIONS | 1029 | 2026-09-22 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000027 | OC-SCR-001283 | 0 | REH-MDU - Wadi Yemm - SP05 - Ground Level (Lower & Upper) Discrepancies with the Architectural Model . | 1023 | 2026-09-22 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000032 | OC-SCR-001284 | 0 | REH-MDU - Wadi Yemm - Light house - Raft boundaries against S.O.G & Planters | 1043 | 2026-09-22 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000007 | OC-SCR-001294 | 0 | REH-MDU - Wadi Yemm - Lightweight Concrete Strength for all DP1 plots | XXXX | 2026-09-23 | 2026-09-24 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000090 | OC-SCR-001300 | 0 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-09-23 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000019 | OC-SCR-001301 | 0 | REH-MDU - Wadi Yemm - Proposal for using shear links in punching reinforcement at slabs | 1047 | 2026-09-23 | 2026-09-23 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000091 | OC-SCR-001303 | 0 | REH-MDU - Wadi Yemm - SP06 - PLOT 1046 - PART 20 (BUILDING A) LEVEL 01 Slab clarifications | 1022 | 2026-09-23 | 2026-09-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000022 | OC-SCR-001305 | 0 | REH-MDU - Wadi Yemm - Plot 1021 Overlap between tank walls and column. | 1021 | 2026-09-23 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000028 | OC-SCR-001307 | 0 | REH-MDU - Wadi Yemm - SP05 - Basement 1 level Coordination and Discrepancies between structure and Architectural drawings. | 1023 | 2026-09-23 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000226 | OC-SCR-001319 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1029-BUILDING A | 1029 | 2026-09-24 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000033 | OC-SCR-001320 | 0 | REH-MDU - Wadi Yemm - Light house - SP07 - Lower Ground Descrapincies | 1043 | 2026-09-24 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000092 | OC-SCR-001316 | 0 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-09-24 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000224 | OC-SCR-001317 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1029-BUILDING A | 1029 | 2026-09-24 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000225 | OC-SCR-001318 | 0 | REH-MDU - Wadi Yemm - columns and Slab conflict – Clarification - plot 1037 - Building A - Second Level | 1029 | 2026-09-24 | 2026-09-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000093 | OC-SCR-001323 | 0 | REH-MDU - Wadi Yemm - Clarifications at SP6-plot 1022 | 1022 | 2026-09-24 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000020 | OC-SCR-001326 | 0 | REH-MDU - Wadi Yemm - Attic Slab at Level +27.52 – Confirmation of Non-Execution | 1047 | 2026-09-24 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000057 | OC-SCR-001335 | 0 | REH-MDU - Wadi Yemm -Confirmation Required for Highlighted Beam at Stair 1-part 1 | 1024 | 2026-09-26 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000011 | OC-SCR-001337 | 0 | REH-MDU - Wadi Yemm - CONFLICT BETWEEN COLUMN DIMENSIONS ON PLAN AND SCHEDULE | 1020 | 2026-09-27 | 2026-10-04 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000094 | OC-SCR-001339 | 0 | REH-MDU - Wadi Yemm - SP06 - PLOT 1045 - Part 14 - Clarifications Required for First Floor Slab - Level 01 (Building C) | 1022 | 2026-09-27 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000029 | OC-SCR-001341 | 0 | REH-MDU - Wadi Yemm - SP05 - Design Review for Basement 1 Floor and Ground Floor | 1023 | 2026-09-27 | 2026-09-27 | Responded
| REH-MD01-MDU-ST-OC-Hil-1044-SCR-000030 | OC-SCR-001345 | 0 | REH-MDU - Wadi Yemm - Column Alignment at the Slab Edge and Omission of Beam CA3 | 1044 | 2026-09-28 | 2026-10-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1024-SCR-000058 | OC-SCR-001348 | 0 | REH-MDU - Wadi Yemm - Confirmation Required for Highlighted Beam at Stair 7-Part 4 -ground floor | 1024 | 2026-09-28 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000008 | OC-SCR-001349 | 0 | REH-MDU - Wadi Yemm - SOG Details for all DP1 plots | XXXX | 2026-09-28 | 2026-09-28 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000227 | OC-SCR-001350 | 0 | REH-MDU - Wadi Yemm - SP01- PLANTED COL TYPE CLARIFICATION. | 1029 | 2026-09-28 | 2026-09-30 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000030 | OC-SCR-001352 | 0 | REH-MDU - Wadi Yemm - Proposal for construction joints at Baesment-1 slab SP5. | 1023 | 2026-09-29 | 2026-09-29 | Responded
| REH-MD01-MDU-ST-OC-Hil-1026-SCR-000035 | OC-SCR-001353 | 0 | REH-MDU - Wadi Yemm - Plot 1026 - Stair Dimensions and Configuration – Fire Exit Room No. 114 | 1026 | 2026-09-29 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000228 | OC-SCR-001355 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - FIRST Level Structural IFC Drawings For Plot 1035-BUILDING B | 1029 | 2026-09-29 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000229 | OC-SCR-001356 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - SECOND Level Structural IFC Drawings For Plot 1029-BUILDING A | 1029 | 2026-09-29 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000230 | OC-SCR-001361 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - First Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-09-30 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000231 | OC-SCR-001362 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - SECOND Level Structural IFC Drawings For Plot 1029 | 1029 | 2026-09-30 | 2026-10-01 | Responded
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000033 | OC-SCR-001367 | 0 | REH-MDU - Wadi Yemm - Plot -1031- Lower Ground & Ground Plans & Schedules | 1031 | 2026-09-30 | 2026-10-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1047-SCR-000021 | OC-SCR-001368 | 0 | REH-MDU - Wadi Yemm - Missing Door Opening for Core 04 at Ground Floor Level | 1047 | 2026-09-30 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000234 | OC-SCR-001373 | 0 | REH-MD01-MDU-ST-OC-Hil-1029-SCR-000234 - SUPER PLOT 01 Clarification Request Regarding (SCR) - SECOND Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-10-01 | 2026-10-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000233 | OC-SCR-001371 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - SECOND Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-10-01 | 2026-10-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000235 | OC-SCR-001372 | 0 | REH-MDU - Wadi Yemm - SUPER PLOT 01 Clarification Request Regarding (SCR) - First and Second Level and Second Level Structural IFC Drawings For Plot 1035 | 1029 | 2026-10-01 | 2026-10-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-XXXX-SCR-000009 | OC-SCR-001377 | 0 | REH-MDU - Wadi Yemm - The backfill material to be used under SOG for all DP1 plots. | XXXX | 2026-10-01 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000023 | OC-SCR-001379 | 0 | REH-MD01-MDU-ST-OC-Hil-1021-SCR-000023 - Plot 1021 -Ground level -ADDITIONAL RFT -PART02 | 1021 | 2026-10-01 | 2026-10-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000034 | OC-SCR-001389 | 0 | REH-MDU - Wadi Yemm - Light house - SP07 - Stairs Descrapincies | 1043 | 2026-10-03 | 2026-10-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000031 | OC-SCR-001391 | 0 | REH-MD01-MDU-ST-OC-Hil-1023-SCR-000031 - SP05 - Basement 1 level - missing data for structure ramps | 1023 | 2026-10-04 | 2026-10-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000095 | OC-SCR-001392 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000095 - Clarifications at SP6-plot 1018 | 1022 | 2026-10-04 | 2026-10-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000096 | OC-SCR-001398 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000096 - Clarifications at SP6-plot 1022-Building C | 1022 | 2026-10-04 | 2026-10-05 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000099 | OC-SCR-001421 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000099 - SP06 - PLOT 1045&1046 - Landscape stair on grade contradicts | 1022 | 2026-10-05 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000024 | OC-SCR-001420 | 0 | REH-MD01-MDU-ST-OC-Hil-1021-SCR-000024 - Plot 1021-Ground Level- Beam Reinforcement Arrangement and Over-Reinforcement Check. | 1021 | 2026-10-05 | 2026-10-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000098 | OC-SCR-001416 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000098 - SP06 - PLOT 1045 - Part 14 - Coordination issues | 1022 | 2026-10-05 | 2026-10-07 | Responded
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000011 | OC-SCR-001414 | 0 | REH-MD01-MDU-ST-OC-Hil-1025-SCR-000011-00 - Clarification on Structural and Arch. Discrepancies – Beams at Fifth Floor & Level at Fourth Floor & Parapet Details | 1025 | 2026-10-05 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000097 | OC-SCR-001413 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000097-00 - SP06 - Plot 1046 - Building (B) - Level 01 Openings | 1022 | 2026-10-05 | 2026-10-06 | Responded
| REH-MD01-MDU-ST-OC-Hil-1043-SCR-000035 | OC-SCR-001430 | 0 | REH-MD01-MDU-ST-OC-Hil-1043-SCR-000035-00 - Light house - SP07 - Stairs Descrapincies | 1043 | 2026-10-05 |  | Pending
| REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000005 | OC-SCR-001428 | 0 | REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000005 - Discrepancy in the distance between the concrete slab and Block work | XXXX | 2026-10-05 | 2026-10-11 | Responded
| REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000004 | OC-SCR-001427 | 0 | REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000004 - There are differences for MESH BED JOINT | XXXX | 2026-10-05 | 2026-10-11 | Responded
| REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000003 | OC-SCR-001426 | 0 | REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000003 - RC stiffeners with thickness 100, 150,& 400, etc mm | XXXX | 2026-10-05 | 2026-10-11 | Responded
| REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000002 | OC-SCR-001425 | 0 | REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000002 - RC stiffening for blockwork | XXXX | 2026-10-05 | 2026-10-11 | Responded
| REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000001 | OC-SCR-001424 | 0 | REH-MD01-MDU-BW-OC-Hil-XXXX-SCR-000001 - Following ECG specs & typical details | XXXX | 2026-10-05 | 2026-10-11 | Responded
| REH-MD01-MDU-BK-OC-Hil-XXXX-SCR-000007 | OC-SCR-001443 | 0 | REH-MD01-MDU-BK-OC-Hil-XXXX-SCR-000007 - Insulation of External Walls | XXXX | 2026-10-06 | 2026-10-11 | Responded
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000025 | OC-SCR-001431 | 0 | REH-MD01-MDU-ST-OC-Hil-1021-SCR-000025 - Plot 1021 -BASEMENT LEVEL -RW ACCESS -PART01 | 1021 | 2026-10-06 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000237 | OC-SCR-001433 | 0 | REH-MD01-MDU-ST-OC-Hil-1029-SCR-000237 - Plot 1029 - Columns conflict | 1029 | 2026-10-06 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000100 | OC-SCR-001439 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000100 - Clarifications at SP6-plot 1022 | 1022 | 2026-10-06 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000101 | OC-SCR-001440 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000101 - SP06 - PLOT 1045 - Part 15 - Clarifications Required for First Floor Slab - Level 01 (Building A) | 1022 | 2026-10-06 |  | Pending
| REH-MD01-MDU-BK-OC-Hil-XXXX-SCR-000006 | OC-SCR-001441 | 0 | REH-MD01-MDU-BK-OC-Hil-XXXX-SCR-000006 - Top fixation between blockwork and slab | XXXX | 2026-10-06 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000102 | OC-SCR-001452 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000102 - SP06 - Plot 1018 - Building (B) - Level 01 | 1022 | 2026-10-06 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1025-SCR-000012 | OC-SCR-001451 | 0 | REH-MD01-MDU-ST-OC-Hil-1025-SCR-000012 - Level Discrepancies and Clarifications – Structural & Architectural IFC Drawings – Plot 1025 | 1025 | 2026-10-06 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000035 | OC-SCR-001455 | 0 | REH-MD01-MDU-ST-OC-Hil-1031-SCR-000035-00 - 1032 – Structural Beam Discrepancies - Ground Floor Slab | 1031 | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1021-SCR-000026 | OC-SCR-001454 | 0 | REH-MD01-MDU-ST-OC-Hil-1021-SCR-000026-00 - Structural Discrepancies ¦ Ground Floor Slab Plot 1021 | 1021 | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000104 | OC-SCR-001458 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000104 - SP06 - Plot 1046 - Building (C) - Clashes and Discrepancies | 1022 | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000105 | OC-SCR-001459 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000105 - SP06 - Plot 1046 - Building (B) - Level 02 Clashes and Discrepancies | 1022 | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1036-SCR-000045 | OC-SCR-001467 | 0 | REH-MD01-MDU-ST-OC-Hil-1036-SCR-000045 - backfilling masonry clarification | 1036 | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1023-SCR-000032 | OC-SCR-001468 | 0 | REH-MD01-MDU-ST-OC-Hil-1023-SCR-000032-SP05 - Lower Ground Level Discrepancies | 1023 | 2026-10-07 |  | Pending
| REH-MD01-RUS-ST-OC-Hil-XXXX-SCR-000006 | OC-SCR-001470 | 0 | REH-MD01-RUS-ST-OC-Hil-XXXX-SCR-000006 - Required reinforcement Details For Manhole Depth Less than 1.50 m (TYPE A) for sewage and storm manholes | XXXX | 2026-10-07 |  | Pending
| REH-MD01-RUS-ST-OC-Hil-XXXX-SCR-000005 | OC-SCR-001469 | 0 | REH-MD01-RUS-ST-OC-Hil-XXXX-SCR-000005 - Required reinforcement Details for rectangular manholes in sewage and storm network | XXXX | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000012 | OC-SCR-001474 | 0 | REH-MD01-MDU-ST-OC-Hil-1020-SCR-000012 - Confirmation of Slab Level and Proposed Adjustment of Beam B15 | 1020 | 2026-10-07 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000106 | OC-SCR-001487 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000106-00 - Clarification slab level01-building B plot 1022 | 1022 | 2026-10-10 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1060-SCR-000034 | OC-SCR-001489 | 0 | REH-MD01-MDU-ST-OC-Hil-1060-SCR-000034-00 - Stair 1 (Plot 1060) Coordination Issues (core type 07) | 1060 | 2026-10-10 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000107 | OC-SCR-001493 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000107-00 - Clarification slab level01-building B plot 1022-conflict between revit model &2D IFC | 1022 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000108 | OC-SCR-001494 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000108 - Carifications at super plot 06-Plot 1018 | 1022 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000109 | OC-SCR-001495 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000109-Clarification slab level01-building B plot 1022-conflict between revit model &2D IFC | 1022 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1022-SCR-000110 | OC-SCR-001498 | 0 | REH-MD01-MDU-ST-OC-Hil-1022-SCR-000110 - SP06 - Plot 1018 - Building (E) - Clashes and Discrepancies | 1022 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1029-SCR-000240 | OC-SCR-001503 | 0 | REH-MD01-MDU-ST-OC-Hil-1029-SCR-000240 - Clarification Required ¦ BEAMS ¦ LOWER GROUND ¦ Plot 1034 Part 19 | 1029 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1020-SCR-000013 | OC-SCR-001504 | 0 | REH-MD01-MDU-ST-OC-Hil-1020-SCR-000013 - Confirmation of Slab Level and Proposed Adjustment of Beam B15 | 1020 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000036 | OC-SCR-001510 | 0 | REH-MD01-MDU-ST-OC-Hil-1031-SCR-000036 - Plot 1032 – Wall Detail at Ground Floor Slab | 1031 | 2026-10-11 |  | Pending
| REH-MD01-MDU-ST-OC-Hil-1027-SCR-000023 | OC-SCR-001516 | 0 | REH-MD01-MDU-ST-OC-Hil-1027-SCR-000023-00 - FORTALEZA HOTEL (Plot 1027) - Structural Coordination Discrepancies and Clarifications | 1027 | 2026-10-11 |  | Pending
OC-SCR-001515
| REH-MD01-MDU-ST-OC-Hil-1031-SCR-000037 | OC-SCR-001517 | 0 | REH-MD01-MDU-ST-OC-Hil-1031-SCR-000037-00 - Plot 1032 – Structural Discrepancies – Lower Ground Floor Slab | 1031 | 2026-10-12 |  | Pending
0
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Ras Al Hekma Cape, Egypt.
Employer:- MoDon
Lead Consultant:- SHAKER & ECG

## AR
Site Clarification Request ( Architectural )
Ref. | Mail No | Rev. | Subject | Sub-Building | Issue Date | Received Date | Action
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000001 | REH-MD01-AR-OC-Hil-1036-SCR-01 | 00 | REH-MDU- Wadi Yemm - Provide us the final IFC architectural drawings for the ground floor of Plot-1036 | 1036 | 2026-05-10 | 2026-05-12 | Responded
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000002 | OC-SCR-000034 | 00 | REH-MDU- Wadi Yemm - Plot-1036 Doors schedule | 1036 | 2026-05-13 | 2026-06-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000003 | OC-SCR-000051 | 00 | REH-MDU- Wadi Yemm - Plot-1036 Ramps' slopes | 1036 | 2026-05-17 | 2026-06-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1034-SCR-000001 | OC-SCR-000097 | 00 | REH-MDU- Wadi Yemm - PLOT-1034 Missing Columns | 1034 | 2026-05-24 | 2026-06-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1030-SCR-000001 | OC-SCR-000119 | 00 | REH-MDU- Wadi Yemm - PLOT-1030 Pavement & Stairs finishes | 1030 | 2026-06-02 | 2026-06-10 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000001 | OC-SCR-000216 | 00 | REH-MDU- Wadi Yemm - PLOT-1034 Missing plan | 1029 | 2026-06-14 | 2026-06-17 | Responded
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000004 | OC-SCR-000312 | 00 | REH-MDU- Wadi Yemm - Plot-1036 Slab openings conflict | 1036 | 2026-06-25 | 2026-07-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000005 | OC-SCR-000317 | 00 | REH-MDU- Wadi Yemm - Plot-1036 Stairs AR-ST Conflict | 1036 | 2026-06-25 | 2026-07-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000001 | OC-SCR-000318 | 00 | REH-MDU- Wadi Yemm - Conflict Door Opening Dimensions and Door Schedule Conflicts for Plot 1025 | 1025 | 2026-06-25 | 2026-07-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1031-SCR-000001 | OC-SCR-000345 | 00 | REH-MDU- Wadi Yemm - SPLOT 02-1032-B1- Pavement & Stairs finishes | 1031 | 2026-06-30 | 2026-07-15 | Responded
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000001 | OC-SCR-000362 | 00 | REH-MDU- Wadi Yemm - Clarification on Stairs Sections details -1024 Stair 5 | 1024 | 2026-07-01 | 2026-07-07 | Responded
REH-MD01-MDU-AR-OC-Hil-1031-SCR-000002 | OC-SCR-000364 | 00 | REH-MDU- Wadi Yemm - Request for Missing Architectural and Landscape Drawings– Super Plot 2 | 1031 | 2026-07-01 | 2026-07-05 | Responded
REH-MD01-MDU-AR-OC-Hil-1031-SCR-000003 | OC-SCR-000371 | 00 | REH-MDU- Wadi Yemm - Conflicts in Levels -1031 B1. PLAN- SP02 | 1031 | 2026-07-01 | 2026-07-14 | Responded
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000002 | OC-SCR-000381 | 00 | REH-MDU- Wadi Yemm - Architectural Files Discrepancies | 1024 | 2026-07-05 | 2026-07-08 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000002 | OC-SCR-000407 | 00 | REH-MDU- Wadi Yemm - Discrapncies Between The Structural Ifc and the Architectural Detailed Design 100% For Second Floor | 1025 | 2026-07-07 | 2026-07-18 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000002 | OC-SCR-000470 | 00 | REH-MDU- Wadi Yemm - PLOT-1030 Core escape path | 1029 | 2026-07-15 | 2026-07-27 | Responded
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000003 | OC-SCR-000488 | 00 | REH-MDU- Wadi Yemm - Clarification on Stairs Sections details -1024 Stair 2 | 1024 | 2026-07-16 | 2026-07-21 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000003 | OC-SCR-000494 | 00 | REH-MDU- Wadi Yemm - Plot : 1037 Missing Access door | 1029 | 2026-07-16 | 2026-07-29 | Responded
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000004 | OC-SCR-000617 | 00 | REH-MDU- Wadi Yemm - Clarification on opening at First Floor plan - Plot 1024 | 1024 | 2026-07-30 | 2026-08-02 | Responded
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000006 | OC-SCR-000670 | 00 | REH-MDU- Wadi Yemm - Plot-1036 STAIR BLOCK WALL | 1036 | 2026-08-04 | 2026-08-10 | Responded
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000005 | OC-SCR-000675 | 00 | REH-MDU- Wadi Yemm - Clarification on internal stair finishing -plot 1024 | 1024 | 2026-08-05 | 2026-08-06 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000004 | OC-SCR-000768 | 00 | REH-MDU- Wadi Yemm - PLOT-1035 Floor finish clash | 1029 | 2026-08-11 | 2026-08-19 | Responded
REH-MD01-MDU-AR-OC-Hil-1027-SCR-000001 | OC-SCR-000770 | 00 | REH-MDU- Wadi Yemm - Fortaleza (Plot 1027) – Technical Clarification – Accessories Material for Internal Blockwork | 1027 | 2026-08-11 | 2026-08-19 | Responded
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000001 | OC-SCR-000779 | 00 | REH-MDU- Wadi Yemm - SP06 – Q4 1045 – STAIRS ISSUES | 1022 | 2026-08-12 | 2026-08-22 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000005 | OC-SCR-000846 | 00 | REH-MDU- Wadi Yemm - PLOT-1030 Missing outdor finish level | 1029 | 2026-08-18 | 2026-09-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000002 | OC-SCR-000849 | 00 | REH-MDU- Wadi Yemm - SP06 – Q3 1046 – STAIR 09 clarifications | 1022 | 2026-08-18 | 2026-09-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1036-SCR-000007 | OC-SCR-000874 | 00 | REH-MDU- Wadi Yemm -Plot-1036 Façade wall conflict | 1036 | 2026-08-19 | 2026-08-23 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000006 | OC-SCR-000907 | 00 | REH-MDU- Wadi Yemm - SP01 LANDSCAPE STAIRS CONFLICT | 1029 | 2026-08-23 | 2026-09-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1027-SCR-000002 | OC-SCR-000929 | 00 | REH-MDU- Wadi Yemm - Fortaleza (Plot 1027) –Clarification of Masonry Accessories Material and Connection Requirements | 1027 | 2026-08-24 | 2026-09-03 | Responded
REH-MD01-MDU-AR-OC-Hil-1029-SCR-000007 | OC-SCR-000998 | 00 | REH-MDU- Wadi Yemm - SP01 EXPOSED SHAFT IN ARCH DWG | 1029 | 2026-09-01 | 2026-09-06 | Responded
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000001 | OC-SCR-001062 | 00 | REH-MDU- Wadi Yemm - Clarification regarding the Master Bathroom for Residential Plots. | XXXX | 2026-09-06 | 2026-09-13 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000003 | OC-SCR-001066 | 00 | REH-MDU- Wadi Yemm - FLOORING FINISH DISCREPANCIES BETWEEN ARCHITECTURAL FLOORING PLAN AND FINISH SCHEDULE AT B2- Plot 1025 | 1025 | 2026-09-06 | 2026-09-09 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000004 | OC-SCR-001067 | 00 | REH-MDU- Wadi Yemm - CEILING FINISH DISCREPANCIES BETWEEN ARCHITECTURAL CEILING PLAN AND FINISH SCHEDULE AT B2- Plot 1025 | 1025 | 2026-09-06 | 2026-09-09 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000005 | OC-SCR-001079 | 00 | REH-MDU- Wadi Yemm - FLOORING FINISH DISCREPANCIES BETWEEN ARCHITECTURAL FLOORING PLAN AND FINISH SCHEDULE AT B1- Plot 1025 | 1025 | 2026-09-07 | 2026-09-09 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000006 | OC-SCR-001080 | 00 | REH-MDU- Wadi Yemm - CEILING FINISH DISCREPANCIES BETWEEN ARCHITECTURAL CEILING PLAN AND FINISH SCHEDULE AT B1- Plot 1025 | 1025 | 2026-09-07 | 2026-09-14 | Responded
REH-MD01-MDU-AR-OC-Hil-1027-SCR-000003 | OC-SCR-001090 | 00 | REH-MDU- Wadi Yemm - Fortaleza (Plot 1027) – Clarification of Masonry Insulation Details | 1027 | 2026-09-08 | 2026-09-10 | Responded
REH-MD01-MDU-AR-OC-Hil-1027-SCR-000004 | OC-SCR-001091 | 00 | REH-MDU- Wadi Yemm - Fortaleza (Plot 1027) –Acoustic and Fire Rating Clarification | 1027 | 2026-09-08 | 2026-09-15 | Responded
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000003 | OC-SCR-001124 | 00 | REH-MDU- Wadi Yemm - SP06 – Q3 1046 – Planters sizes and locations around the family pool | 1022 | 2026-09-10 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1031-SCR-000004 | OC-SCR-001135 | 00 | REH-MDU- Wadi Yemm - Architectural Files Discrepancies -1031 lower ground plan- SP02 | 1031 | 2026-09-13 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000004 | OC-SCR-001185 | 00 | REH-MDU- Wadi Yemm - SP06 - PLOT 1045&1046 - PLANTER WALLS CLARIFICATIONS | 1022 | 2026-09-16 | 2026-10-06 | Responded
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000002 | OC-SCR-001191 | 00 | REH-MDU- Wadi Yemm - Cement hollow blocks in basement floors | XXXX | 2026-09-16 |  | Pending
REH-MD01-MDU-ID-OC-Hil-XXXX-SCR-000001 | OC-SCR-001206 | 00 | REH-MDU- Wadi Yemm - DISCREPANCIES BETWEEN ID PLAN AND ID FINISH SCHEDULE AT RESIDENTIAL PLOTS TYPE (Q2) | XXXX | 2026-09-17 | 2026-10-01 | Responded
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000005 | OC-SCR-001228 | 00 | REH-MDU- Wadi Yemm - SP06 - PLOT 1045 - Part 16 Planter walls clarifications | 1022 | 2026-09-19 | 2026-09-27 | Responded
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000006 | OC-SCR-001249 | 00 | REH-MDU- Wadi Yemm - SP06 - Plot 1018 - Stairs Clarifications | 1022 | 2026-09-20 | 2026-10-07 | Responded
REH-MD01-MDU-AR-OC-Hil-1031-SCR-000005 | OC-SCR-001256 | 00 | REH-MDU- Wadi Yemm - Clarification Required for Stair No. 6 door opening -1032 - SP02 | 1031 | 2026-09-20 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000007 | OC-SCR-001267 | 00 | REH-MDU- Wadi Yemm - Clarifications at SP6-plot 1018 | 1022 | 2026-09-21 | 2026-10-07 | Responded
REH-MD01-MDU-AR-OC-Hil-1025-SCR-000007 | OC-SCR-001293 | 00 | REH-MDU- Wadi Yemm - Fourth Floor Structural & Architectural Coordination Clarifications | 1025 | 2026-09-22 | 2026-09-28 | Responded
REH-MD01-MDU-ID-OC-Hil-XXXX-SCR-000002 | OC-SCR-001297 | 0 | REH-MDU- Wadi Yemm - DISCREPANCIES BETWEEN ID PLAN AND ID FINISH SCHEDULE AT RESIDENTIAL PLOTS TYPE (Q3) | XXXX | 2026-09-23 | 2026-09-29 | Responded
REH-MD01-MDU-ID-OC-Hil-XXXX-SCR-000003 | OC-SCR-001296 | 0 | REH-MDU- Wadi Yemm - DISCREPANCIES BETWEEN ID PLAN AND ID FINISH SCHEDULE AT RESIDENTIAL PLOTS TYPE (Q4) | XXXX | 2026-09-23 | 2026-09-29 | Responded
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000006 | OC-SCR-001340 | 0 | REH-MDU- Wadi Yemm - Clarification on internal stairs Naming - Plot 1024 | 1024 | 2026-09-27 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1024-SCR-000007 | OC-SCR-001360 | 0 | REH-MDU- Wadi Yemm - Clarification on Stair 07 missing data -plot 1024 | 1024 | 2026-09-30 | 2026-10-07 | Responded
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000003 | OC-SCR-001370 | 0 | REH-MDU- Wadi Yemm - Block work details (100 mm, 150 mm & 400 mm) | XXXX | 2026-10-01 | 2026-10-01 | Responded
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000004 | OC-SCR-001374 | 0 | REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000004 - Clarification of Door Structural Opening Dimensions | XXXX | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-AR-OC-Hil-1022-SCR-000008 | OC-SCR-001423 | 0 | REH-MD01-MDU-AR-OC-Hil-1022-SCR-000008- Discrepancies Between Arch. IFC and the Wall Types, Acoustic & Life Safety Requirements – First Floor | 1022 | 2026-10-05 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1047-SCR-000001 | OC-SCR-001417 | 0 | REH-MD01-MDU-AR-OC-Hil-1047-SCR-000001 - Missing Door - Basement 01 & Wall Extension Typical Floors | 1047 | 2026-10-05 | 2026-10-05 | Responded
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000005 | OC-SCR-001438 | 0 | REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000005 - Plaster Thickness | XXXX | 2026-10-06 | 2026-10-07 | Responded
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000006 | OC-SCR-001490 | 0 | REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000006-00 - Following ECG specs & typical details | XXXX | 2026-10-11 |  | Pending
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000007 | OC-SCR-001491 | 0 | REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000007-00 - RC stiffening for blockwork | XXXX | 2026-10-11 |  | Pending
REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000008 | OC-SCR-001492 | 0 | REH-MD01-MDU-AR-OC-Hil-XXXX-SCR-000008-00 - DPC CAVITY TRAY AND WEEPHOLES CANCELLATION | XXXX | 2026-10-11 |  | Pending
EH-MD01-MDU-AR-OC-Hil-1060-SCR-000001 | OC-SCR-001497 | 0 | REH-MD01-MDU-AR-OC-Hil-1060-SCR-000001 - Coordination Issues Related to Sump Pit Access Requirements | 1060 | 2026-10-11 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1021-SCR-000005 | OC-SCR-001512 | 0 | REH-MD01-MDU-AR-OC-Hil-1021-SCR-000005 - Design Discrepancy Between Architectural and Structural IFC – Waste Lift Core Wall (Basement 02) | 1021 | 2026-10-11 |  | Pending
REH-MD01-MDU-AR-OC-Hil-1021-SCR-000004 | OC-SCR-001511 | 0 | REH-MD01-MDU-AR-OC-Hil-1021-SCR-000004 - Design Discrepancies and Missing Information regarding FLS & Acoustic documents | 1021 | 2026-10-11 |  | Pending
0
0
0
0
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Ras Al Hekma Cape, Egypt.
Employer:- MoDon
Lead Consultant:- SHAKER & ECG

## EL
Site Clarification Request ( Electrical )
Ref. | Mail No | Rev. | Subject | Sub-Building | Issue Date | Received Date | Action
P0155-RA04-SCR-EL-OC-DAR-000001 | Darr-GNC-000383 | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Data for Earthing System at plot 1025 | RA04 | 2025-12-25 | 2026-06-25 | Responded
P0155-RA06-SCR-EL-OC-DAR-000001 | Darr-GNC-000384 | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Data for Earthing System at plot 1024 | RA06 | 2025-12-25 | 2026-03-18 | Responded
P0155-RA06-SCR-MV-OC-DAR-000001 | Darr-GNC-000393 | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MV Routing at plot 1024 | RA06 | 2026-01-04 |  | Pending
P0155-RA06-SCR-EL-OC-DAR-000002 | Darr-GNC-000384 | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Missing Data for Earthing System at plot 1024 | RA06 | 2026-02-03 | 2026-02-15 | Responded
P0155-RA00-SCR-EL-OC-DAR-000001 | Darr-GNC-000364 | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Embedded MEP works at Wadi Yemm | RA00 | 2026-02-14 | 2026-03-04 | Responded
P0155-RA00-SCR-EL-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Lightning down conductor general details at Wadi Yemm | RA00 | 2026-02-17 | 2026-03-04 | Responded
REH-MD01-MDU-EL-OC-DAR-XXXX-SCR-000001 |  | 1 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Lightning down conductor general details at Wadi Yemm | RA00 | 2026-03-01 | 2026-03-06 | Responded
REH-MD01-MDU-EL-OC-DAR-1024-SCR-000001 |  | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Request for Cable Cellar Details at RA06 - Plot 1024 | 1024 | 2026-04-16 | 2026-04-29 | Responded
REH-MD01-MDU-EL-OC-DAR-1024-SCR-000002 |  | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Conflict in Power Shaft Location & Request for Cable Data for Slab Openings at RA06 - Plot 1024 | 1024 | 2026-04-16 | 2026-04-30 | Responded
REH-MD01-MDU-EL-OC-DAR-1026-SCR-000001 |  | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Telecome Shaft opening of Basement slap at RA05 - Plot 1026 | 1026 | 2026-04-18 | 2026-04-21 | Responded
REH-MD01-MDU-EL-OC-DAR-1024-SCR-000003 |  | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Clarification of Electrical Riser Size (LV & ELV) - RA06-1024 | 1024 | 2026-04-22 | 2026-04-30 | Responded
REH-MD01-MDU-EL-OC-DAR-1025-SCR-000001 |  | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Clarification of Electrical Riser Size (LV & ELV) - RA04-1025 | 1025 | 2026-04-22 | 2026-04-30 | Responded
REH-MD01-MDU-EL-OC-DAR-1024-SCR-000004 | REH-MD01-EL-OC-DAR-1024-SCR-04 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Clarify the Routing For Low Voltage cables between grid 519, 523 at basement- RA06 - Plot 1024 | 1024 | 2026-04-28 | 2026-04-30 | Responded
REH-MD01-MDU-EL-OC-DAR-1024-SCR-000005 | REH-MD01-EL-OC-DAR-1024-SCR-05 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Shaft Opening for Low Current Cables at Entrance Facility room at basement- RA06 - Plot 1024 | 1024 | 2026-04-28 | 2026-05-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000001 |  | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Clarification of Shaft for Retails in RA06 | 1024 | 2026-05-06 | 2026-05-19 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000002 | REH-MD01-EL-OC-Hil-1024-SCR-02 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Clash between Electrical Trench and Mechanical Shaft in RMU Room Plot 1024 | 1024 | 2026-05-06 | 2026-05-17 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000001 | REH-MD01-EL-OC-Hil-1028-SCR-01 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - LV SLD vs Cable Routing Drawings Conflict at (RA02 - Plot 1028). | 1028 | 2026-05-06 | 2026-05-12 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000002 | REH-MD01-EL-OC-Hil-1028-SCR-02 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Conflict between the Electrical down conductor Ground Floor - Plot 1028 | 1028 | 2026-05-06 | 2026-05-13 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000001 | REH-MD01-EL-OC-Hil-1036-SCR-01 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - LV SLD vs Cable Routing Drawings Conflict at (RA01 - Plot 1036). | 1036 | 2026-05-10 | 2026-05-11 | Responded
REH-MD01-MDU-EL-OC-Hil-1030-SCR-000001 | REH-MD01-EL-OC-Hil-1030-SCR-01 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - RMU Room Location at (RA07 - Plot 1030). | 1030 | 2026-05-10 | 2026-05-14 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000002 | REH-MD01-EL-OC-Hil-1036-SCR-02 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Location of panel boards at business lounge and kids room at Building (RA01 - Plot 1036). | 1036 | 2026-05-11 | 2026-05-13 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000001 | REH-MD01-EL-OC-Hil-XXXX-SCR-01 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Control System Conflict (Shaker) | XXXX | 2026-05-12 | 2026-05-14 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000002 | REH-MD01-EL-OC-Hil-XXXX-SCR-02 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification for Electrical Legend and Lighting Control System (ECG) | XXXX | 2026-05-12 | 2026-06-01 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000001 | OC-SCR-000058 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict between SLD and plans and missing feeding power for retail (RA03 - Plot 1047). | 1047 | 2026-05-19 | 2026-06-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000001 | OC-SCR-000068 | 0 | REH-MD01-MDU -Wadi Yemm - VIA Occupancy Sensor Connection Clarification- Plot 1025- Ground Floor | 1025 | 2026-05-20 | 2026-06-02 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000002 | OC-SCR-000069 | 0 | REH-MD01-MDU -Wadi Yemm - Wall Mounted Lighting Fixture Host Issue - Plot 1025 -Ground Floor. | 1025 | 2026-05-20 | 2026-06-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000003 | OC-SCR-000070 | 0 | REH-MD01-MDU - Wadi Yemm - Ceiling Speaker Wiring and Riser Diagram Clarification- Plot 1025-Ground Floor | 1025 | 2026-05-20 | 2026-06-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000003 | OC-SCR-000104 | 0 | REH-MD01-MDU - Wadi Yemm - Down Conductors. At RA02 – Plot 1028 | 1028 | 2026-05-25 | 2026-06-02 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000003 | OC-SCR-000114 | 0 | REH-MD01-MDU -Wadi Yemm - Relocation of Socket Outlet | XXXX | 2026-06-01 | 2026-06-02 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000004 | OC-SCR-000115 | 0 | REH-MD01-MDU -Wadi Yemm - Data and TV points on Concrete column - Ground Floor | XXXX | 2026-06-01 | 2026-06-01 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000005 | OC-SCR-000117 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Lighting Control System for Apartments (ECG) | XXXX | 2026-06-02 | 2026-06-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000004 | OC-SCR-000116 | 0 | REH-MD01-MDU -Wadi Yemm - Data outlets on Concrete column - Ground Floor | 1025 | 2026-06-02 | 2026-06-07 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000002 |  | 0 | REH-MD01-MDU -Wadi Yemm - RMU Room Location of RA03 - Plot 1047 at Basement Level | 1047 | 2026-06-09 | 2026-06-10 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000006 | OC-SCR-000184 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Regarding CS (Conventional Smoke Detector) scope | XXXX | 2026-06-10 | 2026-06-23 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000007 | OC-SCR-000207 | 0 | REH-MD01-MDU -Wadi Yemm - Required for Fire Alarm Detection Concept at Apartments | XXXX | 2026-06-13 | 2026-06-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1032-SCR-000001 | OC-SCR-000212 | 0 | REH-MD01-MDU -Wadi Yemm - RMU Room Location of SP02 - Plot 1032 - Conflict between the columns and trench. | 1032 | 2026-06-14 | 2026-06-18 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000008 | OC-SCR-000220 | 0 | REH-MD01-MDU -Wadi Yemm - Discrepancies in Earthing Cable Sizes between Layout and Riser Drawings (Shaker Package) | XXXX | 2026-06-15 | 2026-06-17 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000009 | OC-SCR-000225 | 0 | REH-MD01-MDU -Wadi Yemm -Power System Clashes Between Electrical and Interior Design (ELEC & ID) – 100% (DD) Shaker Package – Apartment Layouts – (Q2). | XXXX | 2026-06-15 | 2026-06-23 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000010 | OC-SCR-000226 | 0 | REH-MD01-MDU -Wadi Yemm -Power System Clashes Between Electrical and Interior Design (ELEC & ID) – 100% (DD) Shaker Package – Apartment Layouts – (Q3). | XXXX | 2026-06-15 | 2026-06-26 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000011 | OC-SCR-000227 | 0 | REH-MD01-MDU -Wadi Yemm -Power System Clashes Between Electrical and Interior Design (ELEC & ID) – 100% (DD) Shaker Package – Apartment Layouts – (Q4). | XXXX | 2026-06-15 | 2026-06-26 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000012 | OC-SCR-000232 | 0 | REH-MD01-MDU -Wadi Yemm -Discrepancy Lighting control scenario at Drawings (Shaker Package) | XXXX | 2026-06-15 | 2026-06-23 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000013 | OC-SCR-000233 | 0 | REH-MD01-MDU -Wadi Yemm -Conflict in conventional switch locations & types between Shaker 100% DD & Shaker 100% ID (Shaker Package) | XXXX | 2026-06-15 | 2026-06-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000003 | OC-SCR-000240 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict Between Retail Disconnect Switch Location and Architectural Layout Ground Floor ( RA06-1024) | 1024 | 2026-06-15 | 2026-06-17 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000014 | OC-SCR-000250 | 0 | REH-MD01-MDU -Wadi Yemm -Discrepancy between Design Concept and Drawings (Shaker Package) | XXXX | 2026-06-16 | 2026-06-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000005 | OC-SCR-000259 | 0 | REH-MD01-MDU -Wadi Yemm -Landscape Lighting Clarification – RA04, Plot 1025 | 1025 | 2026-06-17 | 2026-06-24 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000003 | OC-SCR-000290 | 0 | REH-MD01-MDU -Wadi Yemm - Proposed Devices In Fire Alarm System - Plot 1047 - Ground Floor | 1047 | 2026-06-22 | 2026-06-24 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000004 | OC-SCR-000291 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting design clarification - Plot 1047 - Ground Floor | 1047 | 2026-06-22 | 2026-06-24 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000005 | OC-SCR-000292 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict at Panels Locations and Lighting fixture - Plot 1047 - Ground Floor | 1047 | 2026-06-22 | 2026-06-25 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000006 | OC-SCR-000293 | 0 | REH-MD01-MDU -Wadi Yemm - Differences in Lighting Design & missing data for circuits - Plot 1047 - Ground Floor | 1047 | 2026-06-22 | 2026-06-25 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000007 | OC-SCR-000303 | 0 | REH-MD01-MDU -Wadi Yemm - FAÇADE Lighting - Ground Floor of RA03 - Plot 1047 | 1047 | 2026-06-24 | 2026-07-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000008 | OC-SCR-000305 | 0 | REH-MD01-MDU -Wadi Yemm - FAÇADE Lighting - Ground Floor of RA03 - Plot 1047 | 1047 | 2026-06-24 | 2026-07-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000009 | OC-SCR-000306 | 0 | REH-MD01-MDU -Wadi Yemm - Power System - Ground Floor of RA03 - Plot 1047 | 1047 | 2026-06-24 | 2026-07-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000010 | OC-SCR-000307 | 0 | REH-MD01-MDU -Wadi Yemm - Power System - Ground Floor of RA03 - Plot 1047 | 1047 | 2026-06-24 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000011 | OC-SCR-000308 | 0 | REH-MD01-MDU -Wadi Yemm - Power System - Ground Floor of RA03 - Plot 1047 | 1047 | 2026-06-24 | 2026-07-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000012 | OC-SCR-000310 | 0 | REH-MD01-MDU -Wadi Yemm - Clash between lighting fixture and structure column | 1047 | 2026-06-25 | 2026-07-07 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000004 | OC-SCR-000320 | 0 | REH-MD01-MDU -Wadi Yemm - SCR -Clarification Regarding unhosted lighting fixture & occupancy sensor- Ground floor- Plot-1024 | 1024 | 2026-06-27 | 2026-07-07 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000015 | OC-SCR-000321 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Regarding Electrical Services Located Within Reinforced Concrete Columns in Apartment Unit Drawings.Shaker Package | XXXX | 2026-06-27 | 2026-07-01 | Responded
REH-MD01-MDU-EL-OC-Hil-1031-SCR-000001 | OC-SCR-000322 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict and Missing Data Identified Between Earthing & Lightning Layout Drawings and Riser Diagrams for SP02 (Plots 1031, 1032 & 1033) | 1031 | 2026-06-27 | 2026-06-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000005 | OC-SCR-000323 | 0 | REH-MD01-MDU -Wadi Yemm - Missing lighting fixtures in ground floor in plot 1024 | 1024 | 2026-06-27 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000006 | OC-SCR-000324 | 0 | REH-MD01-MDU -Wadi Yemm - linear led design review -plot 1024 | 1024 | 2026-06-27 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000013 | OC-SCR-000338 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Power Outlets for Telecom and Mechanical Equipment. | 1047 | 2026-06-29 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000007 | OC-SCR-000352 | 0 | REH-MD01-MDU -Wadi Yemm - ELECTRICAL-LIFE SAFETY AND EMERGENCY LIGHTING GROUND FLOOR- PLOT-1024 | 1024 | 2026-06-30 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000004 | OC-SCR-000360 | 0 | REH-MD01-MDU -Wadi Yemm - Missing lighting fixtures in ground floor in plot 1028 | 1028 | 2026-07-01 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000005 | OC-SCR-000366 | 0 | REH-MD01-MDU -Wadi Yemm - Lift Lobby Lighting – Circuit Tag Identification – RA02 – Plot 1028 | 1028 | 2026-07-01 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000006 | OC-SCR-000367 | 0 | REH-MD01-MDU -Wadi Yemm - Exit Sign Clarification – Ground Floor of RA02 – Plot 1028 | 1028 | 2026-07-01 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000001 | OC-SCR-000357 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between Slab Openings in (100% DD ARCHITECTURAL & 100% DD ELECTRICAL & IFC STRUCTURAL ) PACKAGES SP2 - PLOT (1060) | 1060 | 2026-06-30 | 2026-07-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1044-SCR-000001 | OC-SCR-000376 | 00 | REH-MD01-MDU - Wadi Yemm - ONU Dedicated Power Supply Arrangement –SP03 – Plot 1044 | 1044 | 2026-07-05 | 2026-07-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000007 | OC-SCR-000392 | 00 | REH-MD01-MDU - Wadi Yemm - IEB Location Clarification – Ground Floor of RA02 – Plot 1028 | 1028 | 2026-07-06 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000008 | OC-SCR-000399 | 00 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding FTR Room Lighting Arrangement in the Ground Floor | 1024 | 2026-07-06 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000009 | OC-SCR-000400 | 00 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding CCTV/Telephone Points in the Ground Floor Elevator plot 1024 | 1024 | 2026-07-06 | 2026-07-08 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000010 | OC-SCR-000401 | 00 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding Façade Lighting Fixtures Coordination at Ground Floor – Plot 1024 | 1024 | 2026-07-07 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000011 | OC-SCR-000414 | 00 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding FCU Power Outlets & Power Circuits in the Ground Floor Elevator-Plot 1024. | 1024 | 2026-07-08 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000012 | OC-SCR-000415 | 00 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding Fire Alarm Device Arrangement in Electrical Utility Rooms | 1024 | 2026-07-08 | 2026-07-13 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000013 | OC-SCR-000418 | 00 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding Lighting Circuit Distribution at Ground Floor – Plot 1024 | 1024 | 2026-07-08 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000008 | OC-SCR-000420 | 00 | REH-MD01-MDU - Wadi Yemm - Lighting fixture without ceiling support – Ground Floor of RA02 – Plot 1028 | 1028 | 2026-07-09 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000009 | OC-SCR-000422 | 00 | REH-MD01-MDU - Wadi Yemm - A/C Disconnect Switch (DCS) Location | 1028 | 2026-07-09 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000016 | OC-SCR-000423 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required for Gas Shut-Off, CCU Switch Connection | XXXX | 2026-07-09 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000006 | OC-SCR-000429 | 0 | REH-MD01-MDU -Wadi Yemm - MISSING LCP PANELS AT GROUND FLOOR – RA04, Plot 1025. | 1025 | 2026-07-11 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000014 | OC-SCR-000431 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding All Power Outlets Distribution Across Floors plot 1024 | 1024 | 2026-07-12 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000010 | OC-SCR-000435 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Switching And Panel Issue At Plot 1028 | 1028 | 2026-07-12 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000014 | OC-SCR-000439 | 0 | REH-MD01-MDU -Wadi Yemm - Security System Camera Location Clarification – Ground Floor of RA03 – Plot 1047 | 1047 | 2026-07-12 | 2026-07-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000001 | OC-SCR-000447 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification for Down Conductor Routing - Sp06 | 1022 | 2026-07-13 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000015 | OC-SCR-000449 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding FTR Room Shaft Dimensions at Ground Floor – Plot 1024 | 1024 | 2026-07-13 | 2026-07-14 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000016 | OC-SCR-000450 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Missing Lighting Fixtures in Gym Area- plot 1024 | 1024 | 2026-07-13 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1032-SCR-000002 | OC-SCR-000463 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding conflict Distribution Board locations/naming at SP02-Plot 1032 | 1032 | 2026-07-14 | 2026-07-27 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000015 | OC-SCR-000464 | 0 | REH-MD01-MDU -Wadi Yemm - Low Current System - Plot 1047 - Ground Floor Plan | 1047 | 2026-07-14 | 2026-07-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000017 | OC-SCR-000466 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Regarding Missing Data Outlet for CCTV Camera at the staircase– Basement 01 PLOT 1024 | 1024 | 2026-07-15 | 2026-07-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000016 | OC-SCR-000472 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting System - Ground Floor of RA03 - Plot 1047 | 1047 | 2026-07-15 | 2026-07-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000018 | OC-SCR-000473 | 0 | REH-MD01-MDU -Wadi Yemm - Security Arm Barrier Location and its power outlet - Plot 1024-GF | 1024 | 2026-07-15 | 2026-07-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000003 | OC-SCR-000475 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Clarification on Lighting Fixture Symbol FAÇADE Lighting - Ground Floor of RA01 - Plot 1036 | 1036 | 2026-07-15 | 2026-07-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000004 | OC-SCR-000476 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Clarification on Landscape Lighting Fixture Type and Mounting Location - Ground Floor of RA01 - Plot 1036 | 1036 | 2026-07-15 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000005 | OC-SCR-000477 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Conflict in arm barrier location - Ground Floor of RA01 - Plot 1036 | 1036 | 2026-07-15 | 2026-07-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000006 | OC-SCR-000478 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -STRUCTURED CABLING SYSTEM floor boxes are not implemented in model- Ground Floor of RA01 - Plot 1036 | 1036 | 2026-07-15 | 2026-07-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000007 | OC-SCR-000484 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Clarification for Down Lights - Plot 1025 | 1025 | 2026-07-15 | 2026-07-18 | Responded
REH-MD01-MDU-EL-OC-Hil-1044-SCR-000002 | OC-SCR-000497 | 0 | REH-MD01-MDU -Wadi Yemm - Elevator Emergency Telephone Point and CCTV Location Clarification –SP03 – Plot 1044 | 1044 | 2026-07-18 | 2026-07-26 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000011 | OC-SCR-000500 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification of Elevator CCTV Camera and Telephone Outlet Locations At Plot 1028 | 1028 | 2026-07-19 | 2026-07-19 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000007 | OC-SCR-000501 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Clarification on Ceiling-Mounted Exit Sign Missing from 100% DD Submission | 1036 | 2026-07-19 | 2026-07-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1033-SCR-000001 | OC-SCR-000508 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center - Structural Beam Interference with Electrical & Low Current Shafts - SP02 - PLOT 1033. | 1033 | 2026-07-19 | 2026-07-26 | Responded
REH-MD01-MDU-EL-OC-Hil-1044-SCR-000003 | OC-SCR-000513 | 0 | REH-MD01-MDU -Wadi Yemm - Mssing cable type ,size and cable routing for BMS - Plot 1044 | 1044 | 2026-07-20 | 2026-07-29 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000008 | OC-SCR-000517 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Plot 1036- Conflict between Arch. topology and Telecommunication for Apartment Types | 1036 | 2026-07-20 | 2026-07-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000009 | OC-SCR-000526 | 0 | REH-MD01-MDU -Wadi Yemm - Sea Town Center -Plot -1036,IEB Location conflict between TE Drawing & Appartment layout | 1036 | 2026-07-21 | 2026-07-26 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000019 | OC-SCR-000544 | 0 | REH-MD01-MDU -Wadi Yemm - SCR - Clarification Regarding Multi Detector Inside Elevator at Ground Floor Plot 1024 | 1024 | 2026-07-22 | 2026-07-27 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000001 | OC-SCR-000548 | 0 | REH-MD01-MDU -Wadi Yemm - SCR - FTR Lighting Circuit unclear , occupancy sensor & Lighting Switch is missing Ground floor - Plot1026 | 1026 | 2026-07-22 | 2026-07-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000017 | OC-SCR-000553 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Location Clarification – Plot 1047 – First Floor | 1047 | 2026-07-22 | 2026-07-28 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000017 | OC-SCR-000554 | 0 | REH-MD01-MDU -Wadi Yemm - Confirmation of Fire Alarm Detectors Inside Apartments | XXXX | 2026-07-22 | 2026-07-29 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000002 | OC-SCR-000558 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Switch Missing - ground floor-plot 1026 | 1026 | 2026-07-26 | 2026-07-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000003 | OC-SCR-000559 | 0 | REH-MD01-MDU -Wadi Yemm - the lighting circuits arrangement - plot 1026 | 1026 | 2026-07-26 | 2026-07-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000020 | OC-SCR-000562 | 0 | REH-MD01-MDU -Wadi Yemm - SCR - Clarification Regarding Outlet Mounting Level Discrepancy Between Legend and Section Details at Ground Floor Plot 1024 | 1024 | 2026-07-26 | 2026-07-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000010 | OC-SCR-000574 | 0 | REH-MD01-MDU -Wadi Yemm - Plot 1036 Missing Camera Outlet In Parking System Ground Floor | 1036 | 2026-07-27 | 2026-07-28 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000018 | OC-SCR-000598 | 0 | REH-MD01-MDU -Wadi Yemm - POWER - CONFLICT IN ELECTRICAL OUTLETS LOCATION AT APPARTMENTS | XXXX | 2026-07-29 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1033-SCR-000002 | OC-SCR-000599 | 0 | REH-MD01-MDU -Wadi Yemm - Request for Approval of Proposed Shaft for Cable Trunk Routing - SP02 - PLOT 1033 | 1033 | 2026-07-29 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000018 | OC-SCR-000600 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification of Exit Sign Location - Emergency System - First Floor of RA03 - Plot 1047 | 1047 | 2026-07-29 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000019 | OC-SCR-000601 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification on Enclosure Rating for High-Rating ATS Units (1600A to 4000A) | XXXX | 2026-07-29 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000020 | OC-SCR-000604 | 0 | REH-MD01-MDU -Wadi Yemm - Q2-2BHK Standard Apartment Dish Washer Location. | XXXX | 2026-07-29 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000019 | OC-SCR-000608 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Smoke Detector Above False Ceiling -First Floor- Plot 1047 | 1047 | 2026-07-30 | 2026-07-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000011 | OC-SCR-000596 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required for Exit Sign Circuits and Emergency Lighting Arrangement | 1036 | 2026-07-29 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000012 | OC-SCR-000619 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Switch Missing - ground floor-plot 1036 | 1036 | 2026-07-30 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000013 | OC-SCR-000620 | 0 | REH-MD01-MDU -Wadi Yemm - the lighting circuits arrangement - plot 1036 | 1036 | 2026-07-30 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000014 | OC-SCR-000621 | 0 | REH-MD01-MDU -Wadi Yemm -Missing Circuits-ground floor-plot 1036 | 1036 | 2026-07-30 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000021 | OC-SCR-000622 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Switch Missing - ground floor-APARTMENT (Q2 4BHK-CORNER) | XXXX | 2026-07-30 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000022 | OC-SCR-000625 | 0 | REH-MD01-MDU -Wadi Yemm - SCR - conflict between the project specifications and the General details FOR down conductors | XXXX | 2026-07-30 | 2026-08-09 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000012 | OC-SCR-000627 | 0 | REH-MD01-MDU -Wadi Yemm - Floor Box Power Outlet Discrepancy at Entrance Lobby – Plot 1028 | 1028 | 2026-08-01 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000015 | OC-SCR-000628 | 0 | REH-MD01-MDU -Wadi Yemm - Missing lighting fixtures in ground floor in plot 1036 | 1036 | 2026-08-01 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000016 | OC-SCR-000630 | 0 | REH-MD01-MDU -Wadi Yemm -Missing Balcony Lighting Fixtures in Apartment Design Drawings-Ground Floor-Plot 1036 | 1036 | 2026-08-01 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000004 | OC-SCR-000636 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Clash &unclear lighting distributionAt Plot (1026) | 1026 | 2026-08-02 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000005 | OC-SCR-000641 | 0 | REH-MD01-MDU -Wadi Yemm - manual call points arrangement at ground floor - plot (1026) | 1026 | 2026-08-02 | 2026-08-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000001 | OC-SCR-000638 | 0 | REH-MD01-MDU -Wadi Yemm - Discrepancy Between Electrical Design Drawings and Latest Architectural Drawings - SP04 - PLOT 1021 | 1021 | 2026-08-02 | 2026-08-09 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000002 | OC-SCR-000639 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required Regarding Lighting Control System for SPA & GYM Rooms - SP04 - PLOT 1021 | 1021 | 2026-08-02 | 2026-08-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000003 | OC-SCR-000640 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required Regarding Electrical Panel Identification and Location - SP04 - PLOT 1021 | 1021 | 2026-08-02 | 2026-08-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000017 | OC-SCR-000654 | 0 | REH-MD01-MDU -Wadi Yemm -CONFLICT BETWEEN DESIGN AND REVIT MODEL IN LOW CURRENT PLOT 1036 GROUND FLOOR | 1036 | 2026-08-03 | 2026-08-04 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000023 | OC-SCR-000655 | 0 | REH-MD01-MDU -Wadi Yemm - Confirmation of Fire Alarm Detectors Inside Apartments - 100% ECG DD package | XXXX | 2026-08-03 | 2026-08-05 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000024 | OC-SCR-000656 | 0 | REH-MD01-MDU -Wadi Yemm - IEB Panel Location Clarification | XXXX | 2026-08-03 | 2026-08-05 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000025 | OC-SCR-000661 | 0 | REH-MD01-MDU -Wadi Yemm -Clarification Regarding Drawing Inconsistencies between type Q2 &Q3 | XXXX | 2026-08-03 | 2026-08-06 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000026 | OC-SCR-000662 | 0 | REH-MD01-MDU -Wadi Yemm -Clarification Required Regarding Home Automation type for Q3 | XXXX | 2026-08-03 | 2026-08-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000006 | OC-SCR-000663 | 0 | REH-MD01-MDU -Wadi Yemm - missing fire alarm detectors in staircases at ground floor - plot (1026) | 1026 | 2026-08-03 | 2026-08-05 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000027 | OC-SCR-000677 | 0 | REH-MD01-MDU -Wadi Yemm -Fire Alarm System Design Discrepancy Between 100% DD Shaker and 100% DD ECG Packages | XXXX | 2026-08-05 | 2026-08-11 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000002 | OC-SCR-000685 | 0 | REH-MD01-MDU -Wadi Yemm - EXTERIOR Lighting – Lighting Fixture Level Coordination-Plot 1022 | 1022 | 2026-08-06 | 2026-08-11 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000028 | OC-SCR-000686 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Regarding the Acceptability of Local Panel Builders | XXXX | 2026-08-06 | 2026-08-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000003 | OC-SCR-000687 | 0 | REH-MD01-MDU -Wadi Yemm - EXTERIOR Lighting don't match with Architectural Drawing -Plot 1022 | 1022 | 2026-08-06 | 2026-08-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1047-SCR-000020 | OC-SCR-000689 | 0 | REH-MD01-MDU -Wadi Yemm - POWER System - Second Floor of RA03 - Plot 1047 | 1047 | 2026-08-06 | 2026-08-10 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000029 | OC-SCR-000697 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Apartment Model for the lighting , power and low Current systems . | XXXX | 2026-08-08 |  | Pending
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000030 | OC-SCR-000698 | 0 | REH-MD01-MDU -Wadi Yemm - Installation Heights / levels for all wall-Mounted devices at Apartments | XXXX | 2026-08-08 | 2026-08-12 | Responded
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000002 | OC-SCR-000699 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict between riser diagram, design drawing and Earth Bar Connections in Mechanical Rooms at Sports Club - plot (1060) | 1060 | 2026-08-08 | 2026-08-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000003 | OC-SCR-000700 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict between Design Drawings, Riser Diagram and Missing Earthing System for some rooms AT Sports Club - plot (1060) | 1060 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000013 | OC-SCR-000723 | 0 | REH-MD01-MDU -Wadi Yemm - FAÇADE LIGHTING DISCREPANCY – FIRST FLOOR – PLOT 1028 | 1028 | 2026-08-09 | 2026-08-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000014 | OC-SCR-000724 | 0 | REH-MD01-MDU -Wadi Yemm - LIGHTING DISCREPANCY – FIRST FLOOR – PLOT 1028 | 1028 | 2026-08-09 | 2026-08-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1037-SCR-000001 | OC-SCR-000742 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Shafts in Structural Drawings - PLOT 1037 | 1037 | 2026-08-10 | 2026-08-17 | Responded
REH-MD01-MDU-EL-OC-Hil-1037-SCR-000002 | OC-SCR-000743 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Shafts in Structural Drawings - PLOT 1037 | 1037 | 2026-08-10 | 2026-08-11 | Responded
REH-MD01-MDU-EL-OC-Hil-1034-SCR-000001 | OC-SCR-000745 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Shafts in Structural Drawings - PLOT 1034 | 1034 | 2026-08-10 | 2026-08-13 | Responded
REH-MD01-MDU-EL-OC-Hil-1034-SCR-000002 | OC-SCR-000746 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Shafts in Structural Drawings - PLOT 1034 | 1034 | 2026-08-10 | 2026-08-12 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000021 | OC-SCR-000765 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Missing Fire Alarm Siren – First Floor – Plot 1024 | 1024 | 2026-08-11 | 2026-08-11 | Responded
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000001 | OC-SCR-000769 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Circuit Wiring Clarification | 1045 | 2026-08-11 | 2026-08-17 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000031 | OC-SCR-000775 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Conflict Between Two Apartment Types – First Floor – Plot 1024 | XXXX | 2026-08-12 | 2026-08-19 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000007 | OC-SCR-000783 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict between (low current, structured cablling, power drawings) and BOQ - ground floor - Plot (1026) | 1026 | 2026-08-12 | 2026-08-13 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000002 | OC-SCR-000794 | 0 | REH-MD01-MDU -Wadi Yemm - Switch Type Clarification | 1045 | 2026-08-13 | 2026-08-17 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000003 | OC-SCR-000799 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Circuit Source Clarification | 1045 | 2026-08-13 | 2026-08-17 | Responded
REH-MD01-MDU-SS-OC-Hil-1044-SCR-000004 | OC-SCR-000802 | 0 | REH-MD01-MDU -Wadi Yemm - Door Contact Clarification – SP03 – Plot 1044 | 1044 | 2026-08-13 | 2026-08-17 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000035 | OC-SCR-000811 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required – Lighting Home Automation for Q3 Apartments | XXXX | 2026-08-13 | 2026-08-22 | Responded
REH-MD01-MDU-FA-OC-Hil-1026-SCR-000008 | OC-SCR-000828 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict between (overall drawing & parts drawings) Fire Alarm system - ground floor - Plot (1026) | 1026 | 2026-08-17 | 2026-08-19 | Responded
REH-MD01-MDU-FA-OC-Hil-1045-SCR-000004 | OC-SCR-000829 | 0 | REH-MD01-MDU -Wadi Yemm - Ground Floor of Plot 1045 - Fire Alarm System - Missing Smoke Detector. | 1045 | 2026-08-17 | 2026-08-24 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000036 | OC-SCR-000821 | 0 | REH-MD01-MDU -Wadi Yemm -Discrepancy Between Interior Design Drawings and Electrical Design Drawings(IFC) - Q2 (SHAKER package) | XXXX | 2026-08-17 | 2026-08-19 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000037 | OC-SCR-000830 | 0 | REH-MD01-MDU -Wadi Yemm - Dressing Room Lighting Switch | XXXX | 2026-08-17 | 2026-08-19 | Responded
REH-MD01-MDU-LI-OC-Hil-1026-SCR-000009 | OC-SCR-000835 | 0 | REH-MD01-MDU -Wadi Yemm -Clarification Regarding Electrical Design and ID Coordination & Device Mounting for Life Safety & Emergency System – Ground Floor – Plot 1026 | 1026 | 2026-08-17 | 2026-08-23 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000003 | OC-SCR-000840 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Circuit – Normal & Emergency Panel Coordination | 1018 | 2026-08-18 | 2026-08-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000004 | OC-SCR-000841 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Missing Details in External Lighting and Façade Lighting Drawings (IFC) - PLOT 1021 | 1021 | 2026-08-18 | 2026-08-23 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000004 | OC-SCR-000844 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Circuit – Panel Connection Coordination | 1018 | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000039 |  | 0 | REH-MD01-MDU -Wadi Yemm - Heat Detectors in Kitchen Areas – IFC vs. Previous SCR Response | XXXX | 2026-08-18 | 2026-10-03 | Responded
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000005 | OC-SCR-000845 | 0 | REH-MD01-MDU -Wadi Yemm - Power circuits arrangement - plot 1045 | 1045 | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-SS-OC-Hil-1018-SCR-000006 | OC-SCR-000848 | 0 | REH-MD01-MDU -Wadi Yemm - Access Control Data Point Requirement _ plot 1018_ Ground Floor | 1018 | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000010 | OC-SCR-000851 | 0 | REH-MD01-MDU -Wadi Yemm -Adding 2 Smoke Detectors Above False Ceiling At Plot 1026 | 1026 | 2026-08-18 | 2026-08-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1044-SCR-000006 | OC-SCR-000852 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Request Regarding Control of Facade and Landscape Lighting - GROUND FLOOR - 1044 | 1044 | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000006 | OC-SCR-000855 | 0 | REH-MD01-MDU -Wadi Yemm - Emergency Lighting Fixture and Circuit Clarification | 1045 | 2026-08-19 | 2026-08-24 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000007 | OC-SCR-000856 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification of Lighting Control Arrangement - Plot 1018 - Ground Floor | 1018 | 2026-08-19 | 2026-08-24 | Responded
REH-MD01-MDU-FA-OC-Hil-1046-SCR-000001 | OC-SCR-000857 | 0 | REH-MD01-MDU -Wadi Yemm - DISCREPANCY BETWEEN FIRE ALARM DEVICES ON AV RACK & EVACUATION SPEAKERS - PLOT#1046 - GROUND FLOOR | 1046 | 2026-08-19 | 2026-08-24 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000008 | OC-SCR-000858 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification of Life Safety Lighting Circuiting - Plot 1018 - Ground floor | 1018 | 2026-08-19 | 2026-08-24 | Responded
REH-MD01-MDU-EL-OC-Hil-1018-SCR-000009 | OC-SCR-000871 | 0 | REH-MD01-MDU -Wadi Yemm - DAP Socket – Power Supply Source-PLOT 1018 - GROUND FLOOR | 1018 | 2026-08-19 | 2026-08-25 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000040 | OC-SCR-000860 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Discrepancy Between Two Apartment Types (Power Design) – First Floor – Plot 1024 | XXXX | 2026-08-19 | 2026-08-23 | Responded
REH-MD01-MDU-SS-OC-Hil-1045-SCR-000007 | OC-SCR-000872 | 0 | REH-MD01-MDU -Wadi Yemm -Access Control Devices Installation at Entrance Gate - Plot 1045 | 1045 | 2026-08-19 | 2026-08-30 | Responded
REH-MD01-MDU-FA-OC-Hil-1018-SCR-000010 | OC-SCR-000873 | 0 | REH-MD01-MDU -Wadi Yemm - Clarifying the smoke detector at Plot 1018 - Ground Floor | 1018 | 2026-08-19 | 2026-08-25 | Responded
REH-MD01-MDU-SS-OC-Hil-1045-SCR-000009 | OC-SCR-000876 | 0 | REH-MD01-MDU -Wadi Yemm -Access Control Device Located More Than 100 m from Associated Access Control Panel - Plot 1045 | 1045 | 2026-08-19 | 2026-08-25 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000011 | OC-SCR-000882 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixtures Missing and Control configuration - Plot -1018 | 1018 | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-SS-OC-Hil-1045-SCR-000010 | OC-SCR-000886 | 0 | REH-MD01-MDU -Wadi Yemm - Conduit Routing at Staircase – Installation Difficulty - Plot 1045 | 1045 | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-SS-OC-Hil-1018-SCR-000012 | OC-SCR-000889 | 0 | REH-MD01-MDU -Wadi Yemm - Door Contact and Access Control Requirements - Plot 1018 - Ground Floor | 1018 | 2026-08-20 | 2026-08-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1037-SCR-000003 | OC-SCR-000892 | 0 | REH-MD01-MDU -Wadi Yemm - Architectural Wall Conflict with Electrical Shaft | 1037 | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000042 | OC-SCR-000894 | 0 | REH-MD01-MDU -Wadi Yemm - Coordination Query Regarding Shutter and Curtain Switches in Apartments | XXXX | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000043 | OC-SCR-000895 | 0 | REH-MD01-MDU -Wadi Yemm - Technical Query Regarding Lighting Control Switches Layout and Circuiting - APARTMENT | XXXX | 2026-08-20 | 2026-08-26 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000044 | OC-SCR-000898 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification on the Necessity of the Indicated Switch - APARTMENTS | XXXX | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000045 | OC-SCR-000899 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Request Regarding Control of Facade and Landscape Lighting - Apartments | XXXX | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000013 | OC-SCR-000902 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixtures Control Zones - Plot 1018 - Ground Floor | 1018 | 2026-08-22 | 2026-08-26 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000046 | OC-SCR-000904 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification on Disconnect Switches, Industrial Sockets, and Outdoor/Life Safety Equipment Requirements | XXXX | 2026-08-23 | 2026-08-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000008 | OC-SCR-000905 | 0 | REH-MD01-MDU -Wadi Yemm - Missing IFC Drawings for Apartments - Plot 1025 | 1025 | 2026-08-23 | 2026-08-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000005 | OC-SCR-000906 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – IFC Drawing Review – Missing Electrical Power Supplies for Mechanical Fans - PLOT 1021 | 1021 | 2026-08-23 | 2026-08-31 | Responded
REH-MD01-MDU-SS-OC-Hil-1018-SCR-000014 | OC-SCR-000908 | 0 | REH-MD01-MDU -Wadi Yemm - Entrance Access Control and Payment Machine Clarification - Plot 1018 | 1018 | 2026-08-23 | 2026-09-02 | Responded
REH-MD01-MDU-SS-OC-Hil-1018-SCR-000015 | OC-SCR-000915 | 0 | REH-MD01-MDU -Wadi Yemm - Access Control Door Components Clarification - Plot 1018 | 1018 | 2026-08-24 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000002 | OC-SCR-000916 | 0 | REH-MD01-MDU -Wadi Yemm - Power Supply from Two Different Buildings (B & D) - Plot 1046 | 1046 | 2026-08-24 | 2026-08-26 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000016 | OC-SCR-000917 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Circuit – Building A / Building B Coordination | 1018 | 2026-08-24 | 2026-08-30 | Responded
REH-MD01-MDU-SS-OC-Hil-1018-SCR-000017 | OC-SCR-000919 | 0 | REH-MD01-MDU -Wadi Yemm - Access Control Panel Connection for Pool Entrance -Plot 1018 | 1018 | 2026-08-24 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000018 | OC-SCR-000924 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required – Storage Cage Lighting and Switches | 1018 | 2026-08-24 | 2026-08-30 | Responded
REH-MD01-MDU-FA-OC-Hil-1018-SCR-000019 | OC-SCR-000931 | 0 | REH-MD01-MDU -Wadi Yemm - clarifying the monitor modules at fire alarm system at Plot 1018 | 1018 | 2026-08-25 | 2026-08-31 | Responded
REH-MD01-MDU-LI-OC-Hil-1024-SCR-000022 | OC-SCR-000932 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Missing Lighting Fixtures & Occupancy Sensors – First Floor – Plot 1024 | 1024 | 2026-08-25 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1024-SCR-000023 | OC-SCR-000933 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Type of Storage Switch – First Floor – Plot 1024 | 1024 | 2026-08-25 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1024-SCR-000024 | OC-SCR-000934 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Missing Lighting Fixture in WM Room – First Floor – Plot 1024 | 1024 | 2026-08-25 | 2026-08-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000011 | OC-SCR-000937 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Life Safety lighting circuit at Stairs-07 At Plot 1026 | 1026 | 2026-08-25 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000047 | OC-SCR-000941 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Missing – Laundry Room | XXXX | 2026-08-26 | 2026-09-06 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000012 | OC-SCR-000946 | 0 | REH-MD01-MDU -Wadi Yemm - Life Safety lighting circuit At ground floor - Plot 1026(IFC) | 1026 | 2026-08-26 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000011 | OC-SCR-000948 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Information – Lighting Control Schematic Diagram – Plot 1045 | 1045 | 2026-08-26 | 2026-08-31 | Responded
REH-MD01-MDU-LI-OC-Hil-XXXX-SCR-000048 | OC-SCR-000949 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Request for Lighting Switch for Q4-1BHK-STANDARD APARTMENT | XXXX | 2026-08-26 | 2026-08-31 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000049 | OC-SCR-000967 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification about Home Automation System scope. | XXXX | 2026-08-29 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1024-SCR-000025 | OC-SCR-000968 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Lighting Fixture Conflicts – First Floor – Plot 1024 | 1024 | 2026-08-29 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1024-SCR-000026 | OC-SCR-000969 | 0 | REH-MD01-MDU -Wadi Yemm - SCR – Clarification Regarding Apartment Q3-1BHK ( Standard&Corner ) Issues – First Floor – Plot 1024 | 1024 | 2026-08-29 | 2026-08-30 | Responded
REH-MD01-MDU-FA-OC-Hil-1028-SCR-000015 | OC-SCR-000970 | 0 | REH-MD01-MDU -Wadi Yemm - Fire Alarm Devices Coordination and Missing Information - First Floor - Plot 1028 | 1028 | 2026-08-30 | 2026-08-30 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000016 | OC-SCR-000977 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Balcony Lighting Fixtures in First Floor IFC Façade Lighting Drawings | 1028 | 2026-08-30 | 2026-09-03 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000003 | OC-SCR-000980 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Location - PLOT 1046-GROUND FLOOR | 1046 | 2026-08-30 | 2026-09-03 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000004 | OC-SCR-000984 | 0 | REH-MD01-MDU -Wadi Yemm - Control of Lighting FIXTURE - PLOT 1046-GROUND FLOOR - 1046 | 1046 | 2026-08-31 | 2026-09-03 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000020 | OC-SCR-000985 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Supply and Control Configuration at Main Entrances - Plot 1018 | 1018 | 2026-08-31 | 2026-09-03 | Responded
REH-MD01-MDU-LI-OC-Hil-1026-SCR-000013 | OC-SCR-000988 | 0 | REH-MD01-MDU -Wadi Yemm - MISSING UPLIGHT FIXTURES FROM IFC DRAWINGS-Ground floor Plot-1026 | 1026 | 2026-08-31 | 2026-09-06 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000012 | OC-SCR-000989 | 0 | REH-MD01-MDU -Wadi Yemm - Exterior Lighting Electrical Circuit Discrepancy – EX.U1b Lighting Fixtures – plot 1045 | 1045 | 2026-08-31 | 2026-09-03 | Responded
REH-MD01-MDU-LI-OC-Hil-1026-SCR-000015 | OC-SCR-000991 | 0 | REH-MD01-MDU -Wadi Yemm - Missing lighting fixture arrangement in IFC drawings - ground floor plot (1026) | 1026 | 2026-08-31 | 2026-09-06 | Responded
REH-MD01-MDU-LI-OC-Hil-1044-SCR-000007 | OC-SCR-001005 | 0 | REH-MD01-MDU -Wadi Yemm - LIGHTING CONTROL - GROUND FLOOR - 1044 | 1044 | 2026-09-01 | 2026-09-07 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000050 | OC-SCR-000997 | 0 | REH-MD01-MDU -Wadi Yemm - Incomplete IFC Documentation for BMS IFC Shaker Package | XXXX | 2026-09-01 | 2026-09-08 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000013 | OC-SCR-001008 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Control - Ground Floor - Plot 1045 | 1045 | 2026-09-01 | 2026-09-07 | Responded
REH-MD01-MDU-SS-OC-Hil-1028-SCR-000017 | OC-SCR-001007 | 0 | REH-MD01-MDU -Wadi Yemm - Security System - Plot 1028 - Intercome telephone location | 1028 | 2026-09-01 | 2026-09-03 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000018 | OC-SCR-001014 | 0 | REH-MD01-MDU -Wadi Yemm - Apartment Typologies - First Floor - Plot 1028 | 1028 | 2026-09-02 | 2026-09-08 | Responded
REH-MD01-MDU-LI-OC-Hil-1044-SCR-000008 | OC-SCR-001020 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting System - Plot 1044 - Circuits Conflict | 1044 | 2026-09-02 | 2026-09-07 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000051 | OC-SCR-001035 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting control configuration in 6 plots. | XXXX | 2026-09-02 | 2026-09-08 | Responded
REH-MD01-MDU-LI-OC-Hil-1026-SCR-000016 | OC-SCR-001046 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Lighting Fixture - PLOT 1026-GROUND FLOOR | 1026 | 2026-09-05 | 2026-09-09 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000017 | OC-SCR-001048 | 0 | REH-MD01-MDU -Wadi Yemm - LIFE SAFETY Lighting does not match with Architectural ELEMENTS - GROUND FLOOR PLOT(1026) | 1026 | 2026-09-06 | 2026-09-10 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000052 | OC-SCR-001049 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification on Disconnect Switches, Industrial Sockets, and Outdoor/Life Safety Equipment Requirements (Shaker) | XXXX | 2026-09-06 | 2026-09-13 | Responded
REH-MD01-MDU-LI-OC-Hil-1045-SCR-000014 | OC-SCR-001060 | 0 | REH-MD01-MDU -Wadi Yemm - Swimming Pool & Water Fountain Lighting Power Supply - Plot 1045 | 1045 | 2026-09-06 | 2026-09-10 | Responded
REH-MD01-MDU-FA-OC-Hil-1045-SCR-000015 | OC-SCR-001063 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict Between Riser Diagram and IFC Drawings in Fire Alarm system of plot 1045 | 1045 | 2026-09-06 | 2026-09-10 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000019 | OC-SCR-001064 | 0 | REH-MD01-MDU -Wadi Yemm - Exit Sign Clarification-Plot 1028 | 1028 | 2026-09-06 | 2026-09-09 | Responded
REH-MD01-MDU-LI-OC-Hil-1018-SCR-000021 | OC-SCR-001071 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict Between Lighting Package and Exterior Lighting (Electrical Package) Layouts - plot 1018 | 1018 | 2026-09-07 | 2026-09-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1046-SCR-000005 | OC-SCR-001072 | 0 | REH-MD01-MDU -Wadi Yemm - Plot 1046- Life Safety Feeding panels | 1046 | 2026-09-07 | 2026-09-09 | Responded
REH-MD01-MDU-EL-OC-Hil-1046-SCR-000006 | OC-SCR-001074 | 0 | REH-MD01-MDU -Wadi Yemm - Plot 1046- Life Safety missing fixtures and Feeding panels conflict | 1046 | 2026-09-07 | 2026-09-10 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000007 | OC-SCR-001083 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting Fixture Circuit Clarification - PLOT 1046-GROUND FLOOR | 1046 | 2026-09-08 | 2026-09-10 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000008 | OC-SCR-001084 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification on Lighting Fixture Circuit Connection – Ground Floor - PLOT 1046-GROUND FLOOR | 1046 | 2026-09-08 | 2026-09-10 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000006 | OC-SCR-001095 | 0 | REH-MD01-MDU -Wadi Yemm - Missing panel in plot 1021 | 1021 | 2026-09-08 | 2026-09-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000007 | OC-SCR-001096 | 0 | REH-MD01-MDU -Wadi Yemm - Missing panel in plot 1021 | 1021 | 2026-09-08 | 2026-09-17 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000053 | OC-SCR-001097 | 0 | REH-MD01-MDU -Wadi Yemm - (HILL-ECG-SHAKER) Clarification about Home Automation System scope. | XXXX | 2026-09-08 | 2026-09-10 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000009 | OC-SCR-001098 | 0 | REH-MD01-MDU -Wadi Yemm - Request for Clarification – Lighting Circuit Connection - PLOT 1046 - GROUND FLOOR | 1046 | 2026-09-08 | 2026-09-15 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000008 | OC-SCR-001109 | 0 | REH-MD01-MDU -Wadi Yemm - Missing panel in plot 1021 | 1021 | 2026-09-09 | 2026-09-16 | Responded
REH-MD01-MDU-LI-OC-Hil-1046-SCR-000012 | OC-SCR-001110 | 0 | REH-MD01-MDU -Wadi Yemm - Lighting FIXTURE Location Confirmation- PLOT 1046-GROUND FLOOR | 1046 | 2026-09-09 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000004 | OC-SCR-001113 | 0 | REH-MD01-MDU -Wadi Yemm - Earth Pits Location for super plot 02 (SP-02) and sports club (1060) | 1060 | 2026-09-09 | 2026-09-14 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000020 | OC-SCR-001133 | 0 | REH-MD01-MDU -Wadi Yemm - Regarding Apartment Typologies in Plot 1028 First Floor | 1028 | 2026-09-13 | 2026-09-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1031-SCR-000002 | OC-SCR-001136 | 0 | REH-MD01-MDU -Wadi Yemm - Discrepancies Identified Between BOQ and SLD for SP02 | 1031 | 2026-09-13 | 2026-09-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1044-SCR-000009 | OC-SCR-001139 | 0 | REH-MD01-MDU -Wadi Yemm - Panel Discrepancy – Plot 1044 | 1044 | 2026-09-13 | 2026-09-16 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000021 | OC-SCR-001141 | 0 | REH-MD01-MDU -Wadi Yemm - Clash Between Cable Trench and Structure Column at Plot 1028 RMU Room | 1028 | 2026-09-13 | 2026-09-16 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000054 | OC-SCR-001142 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification on Lighting Control Philosophy for Common Areas – ECG vs. Shaker IFC Packages – (HILL) , (MODON) | XXXX | 2026-09-13 | 2026-09-23 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000055 | OC-SCR-001150 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required – Medium Voltage Cable Type Between RMU and Transformer (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-FA-OC-Hil-XXXX-SCR-000056 | OC-SCR-001151 | 0 | REH-MD01-MDU -Wadi Yemm - FACP Configuration (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000057 | OC-SCR-001152 | 0 | REH-MD01-MDU -Wadi Yemm - BMS Workstation Configuration (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000058 | OC-SCR-001153 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification for EMDB Diversity Factor (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000018 | OC-SCR-001166 | 0 | REH-MD01-MDU -Wadi Yemm - missing roof plans at IFC electrical package in plot (1026) | 1026 | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000019 | OC-SCR-001167 | 0 | REH-MD01-MDU -Wadi Yemm - missing floor boxes in BOQ - plot (1026) | 1026 | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-FA-OC-Hil-1025-SCR-000009 | OC-SCR-001168 | 0 | REH-MD01-MDU -Wadi Yemm - Difference between fire alarm third floor plan and riser diagram plot 1025. | 1025 | 2026-09-15 | 2026-09-16 | Responded
REH-MD01-MDU-FA-OC-Hil-1025-SCR-000010 | OC-SCR-001171 | 0 | REH-MD01-MDU -Wadi Yemm - conflict between fire fighting and fire alarm plot 1025 - Third Floor | 1025 | 2026-09-15 | 2026-09-21 | Responded
REH-MD01-MDU-LI-OC-Hil-1025-SCR-000011 | OC-SCR-001172 | 0 | REH-MD01-MDU -Wadi Yemm - Duplicated fixtures in life safety lighting plan plot 1025 - Third Floor | 1025 | 2026-09-15 | 2026-09-21 | Responded
REH-MD01-MDU-LI-OC-Hil-1025-SCR-000012 | OC-SCR-001179 | 0 | REH-MD01-MDU -Wadi Yemm - Missing fixtures in facade lighting plan plot 1025. | 1025 | 2026-09-15 | 2026-09-21 | Responded
REH-MD01-MDU-LI-OC-Hil-1025-SCR-000013 | OC-SCR-001184 | 0 | REH-MD01-MDU -Wadi Yemm - Interior lighting control in plot 1025 | 1025 | 2026-09-16 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000005 | OC-SCR-001187 | 0 | REH-MD01-MDU -Wadi Yemm - Missing panels in SP06 - plots (1018,1022,1045,1046) | 1022 | 2026-09-16 | 2026-09-20 | Responded
REH-MD01-MDU-EL-OC-Hil-1046-SCR-000013 | OC-SCR-001188 | 0 | REH-MD01-MDU -Wadi Yemm - Strucure cabling system Clarification - PLOT 1046-GROUND FLOOR | 1046 | 2026-09-16 | 2026-09-21 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000022 | OC-SCR-001189 | 0 | REH-MD01-MDU -Wadi Yemm - Life safety Circuit Coordination Discrepancy Between Second Floor, Staircase, and Basement - Plot 1028. | 1028 | 2026-09-16 | 2026-09-21 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000023 | OC-SCR-001194 | 0 | REH-MD01-MDU -Wadi Yemm - Life safety Circuit Discrepancy Between Second Floor, Staircase, and Basement - Plot 1028. | 1028 | 2026-09-16 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000009 | OC-SCR-001201 | 0 | REH-MD01-MDU -Wadi Yemm - Missing panels in SP04 - plot (1021) | 1021 | 2026-09-17 | 2026-09-20 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000006 | OC-SCR-001203 | 0 | REH-MD01-MDU -Wadi Yemm - EARTHING Clarification - SP06- plots (1018,1022,1045,1046)-FIRST BASEMENT&SECOND BASEMENT FLOOR | 1022 | 2026-09-17 | 2026-09-20 | Responded
REH-MD01-MDU-EL-OC-Hil-1031-SCR-000003 | OC-SCR-001204 | 0 | REH-MD01-MDU -Wadi Yemm - Panel Quantity Verification Against SLD – SP02 | 1031 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000024 | OC-SCR-001205 | 0 | REH-MD01-MDU -Wadi Yemm - FAÇADE LIGHTING DISCREPANCY – Second FLOOR – PLOT 1028 | 1028 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1018-SCR-000023 | OC-SCR-001207 | 0 | REH-MD01-MDU -Wadi Yemm - There are redundant switches that do not control or serve any lighting fixtures | 1018 | 2026-09-17 | 2026-09-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1018-SCR-000024 | OC-SCR-001208 | 0 | REH-MD01-MDU -Wadi Yemm - Conflict Between Lighting Package and Exterior Lighting (Electrical Package) Layouts | 1018 | 2026-09-17 | 2026-09-20 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000014 | OC-SCR-001209 | 0 | REH-MD01-MDU -Wadi Yemm - Missing power supply for racks in third floor plot 1025 | 1025 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1031-SCR-000004 | OC-SCR-001210 | 0 | REH-MD01-MDU -Wadi Yemm - Apartment Panel Type – SP02 | 1031 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1044-SCR-000010 | OC-SCR-001211 | 0 | REH-MD01-MDU -Wadi Yemm - Apartment Panel Type – Plot 1044 | 1044 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000018 | OC-SCR-001213 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on Exit Signs Requirement at Staircase Corridor in FIRST FLOOR LIFE Safety PLAN PLOT#1036 (Life Safety) | 1036 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000001 | OC-SCR-001215 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification Required on BOQ Panel Names – SP01 | 1029 | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000060 | OC-SCR-001221 | 0 | REH-MD01-MDU - Wadi Yemm - Missing Specification – Section 2625 00 (Low-Voltage Enclosed Bus Assemblies) in SHAKER IFC Package | XXXX | 2026-09-17 | 2026-10-01 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000061 | OC-SCR-001220 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on MCC and EMCC Panel names | XXXX | 2026-09-17 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000007 | OC-SCR-001223 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on missing BMS Layouts | 1022 | 2026-09-17 | 2026-09-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1046-SCR-000014 | OC-SCR-001222 | 0 | REH-MD01-MDU - Wadi Yemm - STRUCTURE CABLING Clarification -PLOT 1046 -GROUND FLOOR | 1046 | 2026-09-17 | 2026-09-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1023-SCR-000002 | OC-SCR-001226 | 0 | REH-MD01-MDU - Wadi Yemm - Unclear single line diagram - SP05 | 1023 | 2026-09-17 | 2026-09-24 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000027 | OC-SCR-001225 | 0 | REH-MD01-MDU - Wadi Yemm - SCR – Clarification Regarding Exit Sign Fixtures – Typical Floors – Plot 1024 | 1024 | 2026-09-17 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000019 | OC-SCR-001232 | 0 | REH-MD01-MDU - Wadi Yemm - SCR – Missing connection of lighting fixtures in first floor - plot 1036 (Lighting) | 1036 | 2026-09-19 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000020 | OC-SCR-001233 | 0 | REH-MD01-MDU - Wadi Yemm - SCR – Missing lighting fixtures in first floor - plot 1036 (Lighting) | 1036 | 2026-09-19 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000021 | OC-SCR-001234 | 0 | REH-MD01-MDU - Wadi Yemm - SCR – Lighting circuits arrangement in first floor - plot 1036 (Lighting) | 1036 | 2026-09-19 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000022 | OC-SCR-001235 | 0 | REH-MD01-MDU - Wadi Yemm - SCR – Missing lighting fixtures in first floor - plot 1036 - (Lighting) | 1036 | 2026-09-19 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000002 | OC-SCR-001237 | 0 | REH-MD01-MDU - Wadi Yemm - ONU BOX ENCLOSURE LOCATION IN LOBBY (TELECOMUNICATION) | 1029 | 2026-09-19 | 2026-09-24 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000062 | OC-SCR-001238 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification for Aluminum conduit Anodizing for Electrical Systems | XXXX | 2026-09-19 | 2026-09-27 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000023 | OC-SCR-001242 | 0 | REH-MD01-MDU - Wadi Yemm - Missing Audio Visual Rack in Plot 1036 | 1036 | 2026-09-20 | 2026-09-20 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000015 | OC-SCR-001246 | 0 | REH-MD01-MDU - Wadi Yemm - Missing FCU electrical circuit - PLOT 1025 - POWER | 1025 | 2026-09-20 | 2026-09-21 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000063 | OC-SCR-001247 | 0 | REH-MD01-MDU - Wadi Yemm - conflict between power and water supply in Q2_3 BHK-STANDARD_APARTMENT | XXXX | 2026-09-20 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000064 | OC-SCR-001248 | 0 | REH-MD01-MDU - Wadi Yemm - Missing outlets and circuits in Q2 4BHK-CORNER_APARTMENT small power plan. | XXXX | 2026-09-20 | 2026-09-22 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000025 | OC-SCR-001250 | 0 | REH-MD01-MDU - Wadi Yemm - Lighting Fixture Circuit Clarification - PLOT 1028 - SECOND FLOOR | 1028 | 2026-09-20 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000024 | OC-SCR-001251 | 0 | REH-MD01-MDU - Wadi Yemm - Conflict between Q2-3BHK APARTMENT STRUCTURED CABLING SYSTEM IFC Drawing and Overall Plan - PLOT-1036 (Telecom) | 1036 | 2026-09-20 |  | Pending
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000065 | OC-SCR-001260 | 0 | REH-MD01-MDU - Wadi Yemm - Conflict between power and water supply in Q2_4 BHK-STANDARD - OPTION 2_APARTMENT | XXXX | 2026-09-21 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000025 | OC-SCR-001261 | 0 | REH-MD01-MDU - Wadi Yemm - Unclear Outdoor Camera Location | 1036 | 2026-09-21 | 2026-09-22 | Responded
REH-MD01-MDU-EL-OC-Hil-1025-SCR-000016 | OC-SCR-001285 | 00 | REH-MD01-MDU - Wadi Yemm - MCC Panel Naming Discrepancy -- BOQ vs. SLD -- Plot 1025 | 1025 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000026 | OC-SCR-001286 | 00 | REH-MD01-MDU - Wadi Yemm - Missing MCC Panels in SLD -- RA02--Plot 1028 | 1028 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000026 | OC-SCR-001287 | 00 | REH-MD01-MDU - Wadi Yemm - MCC Panel Missing from BOQ -- Plot 1036 | 1036 | 2026-09-22 | 2026-09-27 | Responded
REH-MD01-MDU-EL-OC-Hil-1024-SCR-000028 | OC-SCR-001291 | 00 | REH-MD01-MDU - Wadi Yemm - MCC Panel Discrepancy Between BOQ and SLD -- RA06 -- Plot 1024 | 1024 | 2026-09-22 | 2026-09-27 | Responded
REH-MD01-MDU-EL-OC-Hil-1026-SCR-000020 | OC-SCR-001288 | 00 | REH-MD01-MDU - Wadi Yemm - MCC Panel Discrepancy Between BOQ and SLD – Plot 1026 | 1026 | 2026-09-22 | 2026-09-27 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000003 | OC-SCR-001290 | 00 | REH-MD01-MDU - Wadi Yemm - MCC Panel Discrepancy Between BOQ and SLD – SP01 (1029 - 1030 - 1034 - 1037 - 1035 | 1029 | 2026-09-22 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1031-SCR-000006 | OC-SCR-001289 | 00 | REH-MD01-MDU - Wadi Yemm - MCC Panel Discrepancy Between BOQ and SLD – SP02 (1031-1033 - 1032) | 1031 | 2026-09-22 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000067 | OC-SCR-001295 | 00 | REH-MD01-MDU - Wadi Yemm - Car Parking – Single Line Diagram Clarification ( ECG Package ) | XXXX | 2026-09-23 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000008 | OC-SCR-001302 | 00 | REH-MD01-MDU - Wadi Yemm - Missing panel and devices in the lighting control system- Plot 1022- First floor | 1022 | 2026-09-23 | 2026-09-30 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000068 | OC-SCR-001306 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict in IEB Rack Location between apartment & overall | XXXX | 2026-09-23 | 2026-09-24 | Responded
REH-MD01-MDU-LI-OC-Hil-1028-SCR-000027 | OC-SCR-001308 | 00 | REH-MD01-MDU - Wadi Yemm - Interior lighting control in plot 1028 | 1028 | 2026-09-23 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000009 | OC-SCR-001309 | 00 | REH-MD01-MDU - Wadi Yemm - Circuits fed from another buildings -PLOT-1022- FIRST FLOOR | 1022 | 2026-09-24 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000069 | OC-SCR-001310 | 00 | REH-MD01-MDU - Wadi Yemm - Missing outlet for water heater in Q2_3 BHK-SPECIAL UNIT_APARTMENT | XXXX | 2026-09-24 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000070 | OC-SCR-001311 | 00 | REH-MD01-MDU - Wadi Yemm - Type of Electrical Fixture Serving the Dishwasher in APARTMENT (Q2 4BHK-CORNER) | XXXX | 2026-09-24 | 2026-09-28 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000004 | OC-SCR-001314 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Components for ELV Systems – ONU, Volume Control & Smart Rack | 1029 | 2026-09-24 | 2026-09-29 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000071 | OC-SCR-001315 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Request – Drafting Issues Light Current Package – SP1"1029 | XXXX | 2026-09-24 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000010 | OC-SCR-001327 | 00 | REH-MD01-MDU - Wadi Yemm - Conflicts Between IFC and Riser diagrams in the First Floor -Plot 1022 | 1022 | 2026-09-24 | 2026-09-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000005 | OC-SCR-001336 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy Between IFC Drawings and Riser Diagrams – ONU Feeding Points and HDMI Outlet "1035" | 1029 | 2026-09-27 | 2026-09-29 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000011 | OC-SCR-001342 | 00 | REH-MD01-MDU - Wadi Yemm - the power circuits arrangement - plot 1022 | 1022 | 2026-09-27 | 2026-09-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000016 | OC-SCR-001343 | 00 | REH-MD01-MDU - Wadi Yemm - missing wall smoke detectors in first floor - plot 1045 | 1045 | 2026-09-27 | 2026-09-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000012 | OC-SCR-001344 | 00 | REH-MD01-MDU - Wadi Yemm - Missing CCTV Coverage for Two Staircases - First Floor, Plot 1022 | 1022 | 2026-09-28 | 2026-09-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1036-SCR-000027 | OC-SCR-001346 | 00 | REH-MD01-MDU - Wadi Yemm - Missing lighting fixtures in first floor - plot 1036 (Lighting) | 1036 | 2026-09-28 | 2026-09-29 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000072 | OC-SCR-001351 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification for Use of OKAIL Conduit EMT Accessories | XXXX | 2026-09-29 | 2026-09-29 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000013 | OC-SCR-001354 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Building Levels for Exterior Lighting – Level 01 - PLOT 1022-FIRST FLOOR | 1022 | 2026-09-29 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000073 | OC-SCR-001359 | 00 | REH-MD01-MDU - Wadi Yemm - conflict between IFC package and 3D model | XXXX | 2026-09-30 | 2026-09-30 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000014 | OC-SCR-001363 | 00 | REH-MD01-MDU - Wadi Yemm - Clarify adding and relocating monitor modules at fire alarm system - Plot 1022 | 1022 | 2026-09-30 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1018-SCR-000025 | OC-SCR-001369 | 00 | REH-MD01-MDU - Wadi Yemm - MISSING MONITOR MODULE FOR TAMPER SWITCH FOR EACH APPARTMENT OF BUILDING C- FIRST FLOOR - plot 1018 | 1018 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000015 | OC-SCR-001375 | 00 | REH-MD01-MDU - Wadi Yemm - Smoke Detector symbol not identified in Legend at fire alarm system at Plot 1022 | 1022 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1022-SCR-000016 | OC-SCR-001376 | 00 | REH-MD01-MDU - Wadi Yemm - Apartment Outlets Connection Clarification – SP06 | 1022 | 2026-10-01 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000010 | OC-SCR-001380 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy in Balcony Lighting Circuiting _ Building 1035 | 1029 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000017 | OC-SCR-001387 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of LCP Location- PLOT 1045-First Floor | 1045 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000018 | OC-SCR-001390 | 00 | REH-MD01-MDU-EL-OC-Hil-1045-SCR-000018- Clarification of Lighting Fixture Requirement- PLOT 1045-First Floor | 1045 | 2026-10-03 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000008 | OC-SCR-001382 | 00 | Fwd: REH-MD01-MDU-EL-OC-Hil-1029-SCR-000008 - External Light Fixtures Fed from Apartment Panel_Building 1035 | 1029 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000006 | OC-SCR-001384 | 00 | REH-MD01-MDU-EL-OC-Hil-1029-SCR-000006 - Missing Car Parking System – Building 1035 Basement Entrance | 1029 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000011 | OC-SCR-001385 | 00 | REH-MD01-MDU-EL-OC-Hil-1021-SCR-000011 - Conflict Between Electrical IFC and PLUMBING IFC in Ground - SP04 - Plot1021 -Parts A,B,C | 1021 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000009 | OC-SCR-001381 | 00 | REH-MD01-MDU-EL-OC-Hil-1029-SCR-000009 - Missing lighting fixtures at Balconies – Building 1035. | 1029 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000007 | OC-SCR-001383 | 00 | REH-MD01-MDU-EL-OC-Hil-1029-SCR-000007 - Access Control – Magnetic Locks / RTE / BTE Devices – Building 1035 | 1029 | 2026-10-01 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000010 | OC-SCR-001386 | 00 | REH-MD01-MDU-EL-OC-Hil-1021-SCR-000010 - Conflict Between Electrical IFC Package and HVAC IFC Package in Ground Floor - SP04 - Plot1021 | 1021 | 2026-10-01 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1018-SCR-000026 | OC-SCR-001388 | 00 | REH-MD01-MDU-EL-OC-Hil-1018-SCR-000026-MISSING MONITOR MODULES FOR ZONE CONTROL VALVE AT STAIRCASE OF BUILDING D -LEVEL 1- plot 1018 | 1018 | 2026-10-02 | 2026-10-05 | Responded
REH-MD01-MDU-LI-OC-Hil-1022-SCR-000017 | OC-SCR-001400 | 00 | REH-MD01-MDU-LI-OC-Hil-1022-SCR-000017-Clarification Required- SP06- plots (1018,1022,1045,1046)- for Life Safety Lighting Sensors at Stairs | 1022 | 2026-10-03 | 2026-10-05 | Responded
REH-MD01-MDU-ST-OC-Hil-1043-SCR-000034 | OC-SCR-001389 | 00 | REH-MD01-MDU-ST-OC-Hil-1043-SCR-000034 - Light house - SP07 - Stairs Descrapincies. | 1043 | 2026-10-03 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000019 | OC-SCR-001409 | 00 | REH-MD01-MDU-EL-OC-Hil-1045-SCR-000019 - Clarification of Lighting Fixture Requirement- PLOT 1045-First Floor | 1045 | 2026-10-04 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1018-SCR-000028 | OC-SCR-001415 | 00 | REH-MD01-MDU-EL-OC-Hil-1018-SCR-000028-Missing Emergency Lighting at Lift Lobby C18-1133 - PLOT#1018 - FIRST FLOOR | 1018 | 2026-10-05 | 2026-10-05 | Responded
REH-MD01-MDU-EL-OC-Hil-1045-SCR-000020 | OC-SCR-001418 | 00 | REH-MD01-MDU-EL-OC-Hil-1045-SCR-000020 - Discrepancy in Panel Locations – Plot 1045, Building B | 1045 | 2026-10-05 |  | Pending
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000074 | OC-SCR-001432 | 00 | REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000074 - missing connection of lighting fixtures of (Q2-3BHK-SPECIAL UNIT) | XXXX | 2026-10-06 |  | Pending
REH-MD01-RUS-EL-OC-Hil-XXXX-SCR-000002 | OC-SCR-001436 | 00 | REH-MD01-RUS-EL-OC-Hil-XXXX-SCR-000002 - Section 260533 – Conduits and Boxes is missed | XXXX | 2026-10-06 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1029-SCR-000013 | OC-SCR-001453 | 00 | REH-MD01-MDU-EL-OC-Hil-1029-SCR-000013-00 - Discrepancy in the Quantity of ONU Units at Ground Floor – Plot 1029 | 1029 | 2026-10-06 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000012 | OC-SCR-001466 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000012 - ICT Cable Tray Routing Through Electrical Shaft -- Plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-00001 | OC-SCR-001465 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000011 - Verification of Escalator MCCB Rating -- Plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000010 | OC-SCR-001464 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000010 - Issues Regarding Lighting Fixture Installation and Distribution in Fan Rooms -- Plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000009 | OC-SCR-001463 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000009 - Discrepancy between the SLD and Revit Model regarding the CRAH unit feeder -- plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000008 | OC-SCR-001462 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000008 - Missing Panels from Single line diagram -- Plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000007 | OC-SCR-001461 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000007 - Panel Schedule & Single line diagram Contradiction -- Plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1060-SCR-000006 | OC-SCR-001460 | 00 | REH-MD01-MDU-EL-OC-Hil-1060-SCR-000006 - Parking Slot / EV Charge Disconnector Coordination -- Plot 1060 | 1060 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-1021-SCR-000014 | OC-SCR-001472 | 00 | REH-MD01-MDU-EL-OC-Hil-1021-SCR-000014 - Conflict Between structured cabling Riser Diagram and IFC drawing- PLOT 1021 | 1021 | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000075 | OC-SCR-001473 | 00 | REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000075 - Missing Structural Provision for MV Cable Cellar IN (1024 , 1025 , 1026 , 1036) Plots | XXXX | 2026-10-07 |  | Pending
REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000076 | OC-SCR-001486 | 00 | REH-MD01-MDU-EL-OC-Hil-XXXX-SCR-000076-00 - Fire Alarm Detector Type for Retail Units – Design Discrepancy | XXXX | 2026-10-10 | 2026-10-11 | Responded
REH-MD01-MDU-EL-OC-Hil-1028-SCR-000028 | OC-SCR-001496 | 00 | REH-MD01-MDU-EL-OC-Hil-1028-SCR-000028 - Location Conflict between LCP-B2-2, Electrical/Low Current Fixtures, and Door Opening Zone in ELEC Room – Basement 02 – Plot 1028 | 1028 | 2026-10-11 |  | Pending
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Ras Al Hekma Cape, Egypt.
Employer:- MoDon
Lead Consultant:- SHAKER & ECG

## ME
Site Clarification Request ( Mechanical )
Ref. | Mail No | Rev. | Subject | Sub-Building | Issue Date | Received Date | Action
P0155-RA06-SCR-ME-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP Elevators Builder work at plot 1024 | RA06 | 2025-12-24 | 2026-03-15 | Responded
P0155-RA06-SCR-ME-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP SUMP PIT Builder work at plot 1024 | RA06 | 2025-12-24 | 2026-03-11 | Responded
P0155-RA06-SCR-ME-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP TANKS Builder work at plot 1024 | RA06 | 2025-12-24 | 2026-03-15 | Responded
P0155-RA06-SCR-ME-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP Grease Interceptors Builder work at plot 1024 | RA06 | 2025-12-24 | 2026-03-12 | Responded
P0155-RA04-SCR-ME-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP Elevators Builder work at plot 1025 | RA04 | 2025-12-25 | 2026-03-18 | Responded
P0155-RA04-SCR-ME-OC-DAR-000002 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP SUMP PIT Builder work at plot 1025 | RA04 | 2025-12-25 | 2026-03-18 | Responded
P0155-RA04-SCR-ME-OC-DAR-000003 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP TANKS Builder work at plot 1025 | RA04 | 2025-12-25 | 2026-03-18 | Responded
P0155-RA04-SCR-ME-OC-DAR-000004 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - MEP Grease Interceptors Builder work at plot 1025 | RA04 | 2025-12-25 | 2026-03-19 | Responded
P0155-RA06-SCR-ME-OC-DAR-000005 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Waste Pipes Slope and Invert Level at Plot 1024 | RA06 | 2026-01-01 | 2026-03-04 | Responded
P0155-RA06-SCR-ME-OC-DAR-000006 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Mechanical works retaining wall opening at Plot 1024 | RA06 | 2026-02-03 | 2026-02-15 | Responded
P0155-RA07-SCR-ME-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Sump Pits conflict at SP1 | RA07 | 2026-02-09 | 2026-02-19 | Responded
P0155-RA04-SCR-AC-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - AC duct conflict with ramp retaining wall at plot 1025 | RA04 | 2026-02-14 | 2026-03-04 | Responded
P0155-RA00-SCR-AC-OC-DAR-000001 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center - Sump Pits conflict at SP1, SP3 and SP4 | RA00 | 2026-02-17 | 2026-03-05 | Responded
P0155-RA04-SCR-ME-OC-DAR-000005 |  | 0 | P0155 - K00146 – REH Wadi Yemm - Sea Town Center -PARKING DRAIN ABOVEGROUND and Trench Drain at plote 1025 | RA04 | 2026-02-25 |  | Pending
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000001 |  | 0 | REH-MD01-MDU - Wadi Yemm - Sea Town Center - Tanks and pump rooms mechanical works | RA00 | 2026-03-02 | 2026-03-11 | Responded
REH-MD01-MDU-ME-OC-DAR-1025-SCR-000001 |  | 0 | REH-MD01-MDU - Wadi Yemm Combined fire and water tank at plot 1025 | 1025 | 2026-03-04 | 2026-03-06 | Responded
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000002 |  | 0 | REH-MD01-MDU - Wadi Yemm Tanks and pump rooms mechanical works at SP1, SP2, SP3, SP4 & SP6 | RA00 | 2026-03-09 | 2026-04-30 | Responded
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000003 |  | 0 | REH-MD01-MDU - Wadi Yemm H/L piping slopes and invert levels at ECG (RA01 : RA06) Plots | RA00 | 2026-03-09 | 2026-03-15 | Responded
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000004 |  | 0 | REH-MD01-MDU - Wadi Yemm H/L piping slopes and invert levels at SP1, SP2, SP3, SP4 & SP6 | RA00 | 2026-03-09 | 2026-04-30 | Responded
REH-MD01-MDU-ME-OC-DAR-1047-SCR-000001 |  | 0 | REH-MD01-MDU - Wadi Yemm Plot 1047 - Arch & Drainage conflict | 1047 | 2026-03-12 | 2026-03-16 | Responded
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000005 |  | 0 | REH-MD01-MDU - Wadi Yemm -Bathrooms waste drainage at basement 01(proposal) | RA00 | 2026-04-16 | 2026-04-23 | Responded
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000006 |  | 0 | REH-MD01-MDU - Wadi Yemm -Bathrooms waste drainage at basement 02(proposal) | RA00 | 2026-04-16 | 2026-04-23 | Responded
REH-MD01-MDU-ME-OC-DAR-XXXX-SCR-000007 |  | 0 | REH-MD01-MDU - Wadi Yemm - Tanks and pump rooms mechanical works | RA00 | 2026-04-19 | 2026-04-22 | Responded
REH-MD01-MDU-AC-OC-DAR-1025-SCR-000001 |  | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on Duct Material (Black Steel vs. Galvanized Steel) | 1025 | 2026-04-22 | 2026-05-11 | Responded
REH-MD01-MDU-ME-OC-DAR-1024-SCR-000001 |  | 0 | REH-MD01-MDU - Wadi Yemm - Conflict between drainage pipes and structural caps at plot 1024 | 1024 | 2026-04-23 | 2026-04-30 | Responded
REH-MD01-MDU-FS-OC-DAR-1036-SCR-000001 |  | 0 | REH-MD01-MDU - Wadi Yemm - Clarification Fire Hose Cabinet Location & Dimension at Stair Core | 1036 | 2026-04-26 | 2026-04-30 | Responded
REH-MD01-MDU-ME-OC-DAR-1024-SCR-000002 |  | 0 | REH-MD01-MDU - Wadi Yemm - Insufficient space between HVAC system and structure at plot 1024 | 1024 | 2026-04-26 | 2026-04-30 | Responded
REH-MD01-MDU-ME-OC-DAR-1024-SCR-000003 |  | 0 | REH-MD01-MDU - Wadi Yemm - Insufficient shaft opening for drainage pipes at plot 1024 | 1024 | 2026-04-26 | 2026-04-28 | Responded
REH-MD01-MDU-ME-OC-DAR-1025-SCR-000002 | REH-MD01-ME-OC-DAR-1025-SCR-02 | 0 | REH-MD01-MDU - Wadi Yemm - Insufficient cavity space behind plumbing fixtures for soil pipes at plot 1025 | 1025 | 2026-04-26 | 2026-04-29 | Responded
REH-MD01-MDU-FS-OC-DAR-1028-SCR-000001 | REH-MD01-FS-OC-DAR-1028-SCR-01 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on Domestic Pump Arrangement for plot 1028 (RA02) | 1028 | 2026-04-27 | 2026-04-30 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000001 | REH-MD01-ME-OC-Hil-1036-SCR-01 | 0 | REH-MD01-MDU - Wadi Yemm - Remark on Suction Line Arrangement, Tank Internal Walls, and Missing Drain – Fire Tank, Plot 1036 | 1036 | 2026-05-03 | 2026-05-06 | Responded
REH-MD01-MDU-ME-OC-Hil-1024-SCR-000001 | REH-MD01-ME-OC-Hil-1024-SCR-01 | 0 | REH-MD01-MDU - Wadi Yemm - Openings in Column Caps | 1024 | 2026-05-04 | 2026-05-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1024-SCR-000002 | REH-MD01-ME-OC-Hil-1024-SCR-02 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification of Shaft for Retails in RA06 | 1024 | 2026-05-04 | 2026-05-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000001 | REH-MD01-ME-OC-Hil-1025-SCR-01 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on irrigation water pipe Routing at Hardscape and Swimming pool area Plot RA04(1025) Ground Floor | 1025 | 2026-05-04 | 2026-05-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000002 | REH-MD01-ME-OC-Hil-1025-SCR-02 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification on Trench Darin Pipe Plot RA04(1025) Ground Floor | 1025 | 2026-05-04 | 2026-05-07 | Responded
REH-MD01-MDU-ME-OC-Hil-1028-SCR-000001 | REH-MD01-ME-OC-Hil-1028-SCR-01 | 0 | REH-MD01-MDU - Wadi Yemm - Architectural shafts, mechanical and drainage Works Clash | 1028 | 2026-05-04 | 2026-05-07 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000003 | REH-MD01-ME-OC-Hil-1025-SCR-03 | 0 | REH-MD01-MDU - Wadi Yemm - Changes in Openings Due to Coordination Conflicts | 1025 | 2026-05-05 | 2026-05-12 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000001 | REH-MD01-ME-OC-Hil-xxxx-SCR-01 | 0 | REH-MD01-MDU - Wadi Yemm - Floor Drain Openings | XXXX | 2026-05-05 | 2026-05-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1030-SCR-000001 | REH-MD01-ME-OC-Hil-1030-SCR-01 | 00 | REH-MD01-MDU - Wadi Yemm Request for Confirmation of Drainage Levels Relative to Road Level – Plot 1030 | 1030 | 2026-05-11 | 2026-06-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000004 | REH-MD01-ME-OC-Hil-1025-SCR-04 | 00 | REH-MD01-MDU - Wadi Yemm Request for Clarification – Missing Basement Groundwater & Rainwater Drainage Details Referenced in Structural Drawings | 1025 | 2026-05-12 | 2026-05-21 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000002 | OC-SCR-000025 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Gate Valve Provision Before Fire Hose Cabinet | XXXX | 2026-05-12 | 2026-05-16 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000003 | OC-SCR-000026 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy Between Fire Fighting Revit Model and General Detail Drawing for Zone Control Valve Set | XXXX | 2026-05-12 | 2026-05-13 | Responded
REH-MD01-MDU-ME-OC-Hil-1047-SCR-000001 | OC-SCR-000022 | 00 | REH-MD01-MDU - Wadi Yemm - Existing Openings In Structural Column Cap Openings (Plot -1047) | 1047 | 2026-05-12 | 2026-05-20 | Responded
REH-MD01-MDU-ME-OC-Hil-1047-SCR-000002 | OC-SCR-000023 | 00 | REH-MD01-MDU - Wadi Yemm - HVAC Duct Routing – Slab Openings Clarification - (Plot -1047) | 1047 | 2026-05-12 | 2026-05-18 | Responded
REH-MD01-MDU-ME-OC-Hil-1047-SCR-000003 | OC-SCR-000024 | 00 | REH-MD01-MDU - Wadi Yemm - Drainage Pipes at Ground Floor Passing Through Structural Column Cap. (Plot-1047) | 1047 | 2026-05-12 | 2026-05-14 | Responded
REH-MD01-MDU-ME-OC-Hil-1028-SCR-000002 | OC-SCR-000036 | 00 | REH-MD01-MDU - Wadi Yemm - Upper Floors Shaft Coordination Issue – Plot 1028 | 1028 | 2026-05-14 | 2026-06-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000001 | OC-SCR-000037 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Overflow Pipe Level at Irrigation Tank – Plot 1029 | 1029 | 2026-05-14 | 2026-06-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000002 | OC-SCR-000038 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Overflow Pipe Level at Domestic Pump Room 1 – Plot 1029 | 1029 | 2026-05-14 | 2026-06-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1047-SCR-000004 | OC-SCR-000059 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural Wall Conflict Within MEP Shaft - Ground Floor Slab - (Plot -1047). | 1047 | 2026-05-19 | 2026-05-21 | Responded
REH-MD01-MDU-ME-OC-Hil-1047-SCR-000005 | OC-SCR-000060 | 00 | REH-MD01-MDU - Wadi Yemm - Toilets Location above the column caps - Ground Floor Slab - (Plot -1047). | 1047 | 2026-05-19 | 2026-05-21 | Responded
REH-MD01-MDU-ME-OC-Hil-1047-SCR-000006 | OC-SCR-000061 | 00 | REH-MD01-MDU - Wadi Yemm - WC Drain Pipe Routing Issue - Ground Floor Slab - (Plot -1047). | 1047 | 2026-05-19 | 2026-05-21 | Responded
REH-MD01-MDU-ME-OC-Hil-1027-SCR-000001 | OC-SCR-000079 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between MEP and Structural Drawings for Sump Pit, Grease Interceptor & Sand Trap Locations at Plot 1027 | 1027 | 2026-05-20 | 2026-06-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000001 | OC-SCR-000143 | 00 | REH-MD01-MDU - Wadi Yemm - FLOOR DRAIN LOCATION CONFLICT BETWEEN DRAIN DRAWING & ID DRAWING | 1021 | 2026-06-04 | 2026-06-14 | Responded
REH-MD01-MDU-ME-OC-Hil-1041-SCR-000001 | OC-SCR-000170 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between MEP and Structural Drawings for Sump Pit, oil trap & Sand Trap Locations at Plot 1041 | 1041 | 2026-06-09 | 2026-06-18 | Responded
REH-MD01-MDU-ME-OC-Hil-1018-SCR-000001 | OC-SCR-000174 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Pressurization Shaft Locationl . (Plot-1018) | 1018 | 2026-06-09 | 2026-06-16 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000001 | OC-SCR-000193 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Sanitary Drainage Tie-In Connection (Plot-1022) | 1022 | 2026-06-11 | 2026-06-16 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000002 | OC-SCR-000194 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Drainage Shaft Locations (Plot-1018) | 1022 | 2026-06-11 | 2026-06-25 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000003 | OC-SCR-000195 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for HVAC Duct Conflict with Architectural/Structural Shaft (Building 1022) | 1022 | 2026-06-11 | 2026-06-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000004 | OC-SCR-000196 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Pressurization Shaft Locationl (Building 1022) | 1022 | 2026-06-11 | 2026-06-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1028-SCR-000003 | OC-SCR-000192 | 00 | REH-MD01-MDU - Wadi Yemm - Grid Discrepancncy Between Mechanical models and strucure model . (Plot-1028) | 1028 | 2026-06-11 | 2026-06-18 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000005 | OC-SCR-000199 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Screed Thickness Inside Tanks | 1022 | 2026-06-11 | 2026-06-25 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000004 | OC-SCR-000210 | 00 | REH-MD01-MDU - Wadi Yemm - Request for Client’s Decision Regarding Installation of Os & Y Gate Valve Provision Before Fire Hose Cabinets | XXXX | 2026-06-14 | 2026-07-05 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000005 | OC-SCR-000215 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Design Drawings and Data in Latest SUPER PLOTS 100% DD Package | XXXX | 2026-06-14 | 2026-06-16 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000003 | OC-SCR-000222 | 00 | REH-MD01-MDU - Wadi Yemm - Request for Clarification Regarding Pump Rooms at Levels 04 & 05 – Plot 1029 (SP-01) | 1029 | 2026-06-15 | 2026-07-05 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000006 | OC-SCR-000223 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Specifications for Tanks | XXXX | 2026-06-15 | 2026-06-23 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000007 | OC-SCR-000224 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification About Emergency Pump in Irrigation Pump Room in Plots RA01,RA02,RA03,RA04,RA05,RA06 | XXXX | 2026-06-15 | 2026-06-17 | Responded
REH-MD01-MDU-ME-OC-Hil-1028-SCR-000004 | OC-SCR-000234 | 00 | REH-MD01-MDU - Wadi Yemm - Remark on Suction Line Arrangement, Fire fighting Tank Internal Walls,Tank Drain Point Missing . Plot 1028 | 1028 | 2026-06-15 | 2026-06-16 | Responded
REH-MD01-MDU-ME-OC-Hil-1026-SCR-000001 | OC-SCR-000256 | 00 | REH-MD01-MDU - Wadi Yemm - Deleted shaft for mechacical works | 1026 | 2026-06-17 | 2026-06-21 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000008 | OC-SCR-000276 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification The Location of Floor Drain In all Building for Public Toilet | XXXX | 2026-06-21 | 2026-10-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000006 | OC-SCR-000311 | 00 | REH-MD01-MDU - Wadi Yemm - Drainage Shaft Openings Conflict with Retaining Wall | 1022 | 2026-06-25 | 2026-07-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000002 | OC-SCR-000314 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Fire Hose Cabinet Opening at Staircase Vertical Wall | 1036 | 2026-06-25 | 2026-06-25 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000004 | OC-SCR-000325 | 00 | REH-MD01-MDU - Wadi Yemm - Plot 1030 - Upper Ground - Openings . | 1029 | 2026-06-27 | 2026-07-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000007 | OC-SCR-000334 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Water Supply & Drainage Provision for Toilets | 1022 | 2026-06-29 | 2026-07-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000008 | OC-SCR-000336 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancies Between Structural, Architectural, and Mechanical Openings | 1022 | 2026-06-29 | 2026-07-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000001 | OC-SCR-000341 | 00 | REH-MD01-MDU - Wadi Yemm - Fresh Air Fans Connection Clarification for Basements | 1060 | 2026-06-30 | 2026-07-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000002 | OC-SCR-000342 | 00 | REH-MD01-MDU - Wadi Yemm - Confilation for Exhasut duct | 1060 | 2026-06-30 | 2026-07-02 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000003 | OC-SCR-000343 | 00 | REH-MD01-MDU - Wadi Yemm - Exhaust/Smoke & Fresh Air Duct Sizing | 1060 | 2026-06-30 | 2026-07-02 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000005 | OC-SCR-000356 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancies Between Structural, Architectural, and Mechanical Openings | 1029 | 2026-06-30 | 2026-07-15 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000009 | OC-SCR-000361 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Drainage Shaft and Structural Beam | 1022 | 2026-07-01 | 2026-07-15 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000002 | OC-SCR-000365 | 00 | REH-MD01-MDU - Wadi Yemm - Plot 1021 - Basement 01 - Openings . | 1021 | 2026-07-01 | 2026-07-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000010 | OC-SCR-000387 | 00 | REH-MD01-MDU - Wadi Yemm - Drainage Shaft Openings Clarification – Retaining Wall (Follow-up) | 1022 | 2026-07-05 | 2026-07-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000011 | OC-SCR-000393 | 00 | REH-MD01-MDU - Wadi Yemm - Conflicts Between Drainage System and Structural Elements | 1022 | 2026-07-06 | 2026-07-15 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000006 | OC-SCR-000396 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancies Between Structural, Architectural, and Mechanical Openings - Plot 1035 | 1029 | 2026-07-06 | 2026-07-14 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000012 | OC-SCR-000408 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Regarding Drainage Shafts Routing. | 1022 | 2026-07-07 | 2026-07-14 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000007 | OC-SCR-000411 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancies Between Structural, Architectural, and Mechanical Openings - Plot 1035 | 1029 | 2026-07-08 | 2026-07-15 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000009 | OC-SCR-000421 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Irrigation Models From Package 1B & 1C - 100% DD Submission Irrigation Package | XXXX | 2026-07-09 | 2026-07-26 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000008 | OC-SCR-000430 | 00 | REH-MD01-MDU - Wadi Yemm -Clarification Regarding Fresh & Exhaust Air Duct Shaft at Ground Floor - Plot 1029 | 1029 | 2026-07-11 | 2026-07-18 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000009 | OC-SCR-000455 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural/MEP Shaft and Structural Drawings Coordination Conflict | 1029 | 2026-07-14 | 2026-07-27 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000010 | OC-SCR-000456 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancies Between Structural, Architectural, and Mechanical Openings - Plot 1035 | 1029 | 2026-07-14 | 2026-07-26 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000011 | OC-SCR-000458 | 00 | REH-MD01-MDU - Wadi Yemm - The Contractor requests clarification regarding the coordination of the shaft with the structural beam | 1029 | 2026-07-14 | 2026-07-27 | Responded
REH-MD01-MDU-ME-OC-Hil-1024-SCR-000003 | OC-SCR-000467 | 00 | REH-MD01-MDU - Wadi Yemm - Conflicts Between Drainage System and Structural Elements | 1024 | 2026-07-15 | 2026-07-21 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000012 | OC-SCR-000489 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Shafts in Structural Drawings - PLOT 1037 | 1029 | 2026-07-16 | 2026-07-27 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000013 | OC-SCR-000493 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Screed Thickness Inside Tanks | 1022 | 2026-07-16 | 2026-07-26 | Responded
REH-MD01-MDU-ME-OC-Hil-1044-SCR-000001 | OC-SCR-000498 | 00 | REH-MD01-MDU - Wadi Yemm - Structural Clash Between AC Shaft Duct/Pipes and Basement 01 Attic Slab - Plot 1044 | 1044 | 2026-07-18 | 2026-07-28 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000010 | OC-SCR-000499 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Discrepancy Between BOQ Description and Specifications for Smoke Exhaust Duct Sheet Metal | XXXX | 2026-07-18 | 2026-07-26 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000014 | OC-SCR-000509 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Regarding Insufficient Wall Cavity for MEP Sleeves Installation | 1022 | 2026-07-19 | 2026-07-28 | Responded
REH-MD01-MDU-ME-OC-Hil-1044-SCR-000002 | OC-SCR-000510 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between drainge & structure (concrete slab & beam & coulms) | 1044 | 2026-07-19 | 2026-07-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1024-SCR-000004 | OC-SCR-000515 | 00 | REH-MD01-MDU - Wadi Yemm - Clash Between Drainage Pipes and (FIRE & DOMESTIC) Water TANK PLOT 1024 | 1024 | 2026-07-20 | 2026-07-22 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000011 | OC-SCR-000528 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Fire Hose Cabinet Installation | XXXX | 2026-07-21 | 2026-07-26 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000015 | OC-SCR-000529 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Opening and Architecture shaft opening for MEP services | 1022 | 2026-07-21 | 2026-07-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000016 | OC-SCR-000530 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Architecture Openings and for MEP Service | 1022 | 2026-07-21 | 2026-07-27 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000017 | OC-SCR-000531 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between Structure and Architecture Shaft opening for MEP Service | 1022 | 2026-07-21 | 2026-07-28 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000018 | OC-SCR-000532 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Openings and Beam Clashs with Architecture Shaft opening for MEP Service | 1022 | 2026-07-21 | 2026-07-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000019 | OC-SCR-000533 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Opening and Architecture shaft opening for MEP services | 1022 | 2026-07-21 | 2026-07-28 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000020 | OC-SCR-000534 | 00 | REH-MD01-MDU - Wadi Yemm - Water Meter Opening – Confirmation of Meter Room Access, Sleeve Width, and DCW Pipe Coordination | 1022 | 2026-07-21 | 2026-07-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000021 | OC-SCR-000535 | 00 | REH-MD01-MDU - Wadi Yemm - Water Meter Shaft Opening Clarification | 1022 | 2026-07-21 | 2026-07-28 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000022 | OC-SCR-000536 | 00 | REH-MD01-MDU - Wadi Yemm - Drainage Pipe Clash with Structural Element | 1022 | 2026-07-21 | 2026-07-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000003 | OC-SCR-000538 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification for Adding Double Wall in Toilets to Accommodate Water Supply and Drainage Pipes SP04 - 1021 | 1021 | 2026-07-22 | 2026-07-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000004 | OC-SCR-000539 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict in Planter Drain Locations Between Landscape and Drainage Drawings In Plot 1021 | 1021 | 2026-07-22 | 2026-08-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000013 | OC-SCR-000561 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Shafts in Structural Drawings - PLOT 1029 | 1029 | 2026-07-26 | 2026-07-30 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000023 | OC-SCR-000569 | 00 | REH-MD01-MDU - Wadi Yemm - No Structural Shaft Openings for MEP Services | 1022 | 2026-07-27 | 2026-08-02 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000024 | OC-SCR-000570 | 00 | REH-MD01-MDU - Wadi Yemm - Exposed Pipes Due to Misalignment Between Architectural Shaft Walls | 1022 | 2026-07-27 | 2026-08-06 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000025 | OC-SCR-000571 | 00 | REH-MD01-MDU - Wadi Yemm - Planter Drain Sleeve Clash with Shear Wall | 1022 | 2026-07-27 | 2026-08-06 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000012 | OC-SCR-000572 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Material Description for Smoke Exhaust Duct Sheet Metal /KITCHEN HOOD | XXXX | 2026-07-27 | 2026-08-02 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000013 | OC-SCR-000573 | 00 | REH-MD01-MDU - Wadi Yemm - CLARIFICATION REGARDING TO PUDDLE FLANGE’S MATERIAL FOR FIRE,WATER & IRRIGATION TANKS | XXXX | 2026-07-27 | 2026-08-02 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000005 | OC-SCR-000581 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Drainage Pipes and Beams at Attic Slab Above Basement 01- SP04 - 1021. | 1021 | 2026-07-28 | 2026-08-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000026 | OC-SCR-000584 | 00 | REH-MD01-MDU - Wadi Yemm - Conflicts Between Structural and MEP Services – Plot 1018 | 1022 | 2026-07-28 | 2026-08-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000027 | OC-SCR-000585 | 00 | REH-MD01-MDU - Wadi Yemm - Multiple Floor Drain Locations Inside the Same Toilet | 1022 | 2026-07-28 | 2026-08-02 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000028 | OC-SCR-000586 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Openings for Drain Pipes - PLOT 1045 | 1022 | 2026-07-28 | 2026-08-06 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000029 | OC-SCR-000587 | 00 | REH-MD01-MDU - Wadi Yemm - Coordination Issue Between Shaft Openings and Structural Beams - PLOT 1045 | 1022 | 2026-07-28 | 2026-08-06 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000030 | OC-SCR-000590 | 00 | REH-MD01-MDU - Wadi Yemm - REH-MD01-MDU-ME-OC-Hil-1022-SCR-000031-00 | 1022 | 2026-07-28 | 2026-08-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000031 | OC-SCR-000591 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification on Opening Requirement for Drain Pipes within Architectural Wall_SP06-Plot-1022-RA12-Part-2B-Ground Floor | 1022 | 2026-07-28 | 2026-08-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000032 | OC-SCR-000592 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Riser_SP06-Plot-1022-RA12-Part-2B-Ground Floor | 1022 | 2026-07-28 | 2026-08-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000006 | OC-SCR-000602 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Level of Tanks and Pump rooms in SP04 - 1021 in Basement 02 floor | 1021 | 2026-07-29 | 2026-08-05 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000007 | OC-SCR-000606 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Trench drain & drain system for ramp - 1021 in Basement 02 floor | 1021 | 2026-07-30 | 2026-08-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000008 | OC-SCR-000607 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Minimum Duct Elevation and clear height - 1021 in Basement 02 floor | 1021 | 2026-07-30 | 2026-08-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000033 | OC-SCR-000618 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required on Domestic, Irrigation, and Fire Pump Tanks Details-SP06-PLOT 1045 | 1022 | 2026-07-30 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000034 | OC-SCR-000645 | 00 | REH-MD01-MDU - Wadi Yemm - Coordination Issue Between Architectural/MEP Shaft and Structural Shaft – PLOT 1046 | 1022 | 2026-08-02 | 2026-08-09 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000035 | OC-SCR-000644 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Shaft Openings for Drainage Services | 1022 | 2026-08-02 | 2026-08-10 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000036 | OC-SCR-000643 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Drainage Arrangement for Back-to-Back WCs | 1022 | 2026-08-02 | 2026-08-10 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000014 | OC-SCR-000673 | 00 | REH-MD01-MDU - Wadi Yemm - Missing MEP Shafts on Structural Drawings - PLOT 1034 | 1029 | 2026-08-04 | 2026-08-10 | Responded
REH-MD01-MDU-FF-OC-Hil-1047-SCR-000001 | OC-SCR-000688 | 00 | REH-MD01-MDU - Wadi Yemm - Domestic Cold Water and fire Tank Capacity | 1047 | 2026-08-06 | 2026-08-09 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000037 | OC-SCR-000693 | 00 | REH-MD01-MDU - Wadi Yemm - Structural Framing Clash with Trench Pipe Sleeves and Shaft Openings SP06-Plot-1045-Part-16 | 1022 | 2026-08-06 | 2026-08-13 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000038 | OC-SCR-000694 | 00 | REH-MD01-MDU - Wadi Yemm - Shaft Opening Required Within Architectural Walls SP06-Plot-1045-Part-16 | 1022 | 2026-08-06 | 2026-08-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000039 | OC-SCR-000695 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Architectural Fixtures and Drainage Routing SP06-Plot-1045-Part-16 | 1022 | 2026-08-06 | 2026-08-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000040 | OC-SCR-000701 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Structural Opening and Architectural Shaft | 1022 | 2026-08-08 | 2026-08-13 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000003 | OC-SCR-000702 | 00 | REH-MD01-MDU - Wadi Yemm - Exposed Drainage Pipe - First Floor - (Plot -1036) | 1036 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000004 | OC-SCR-000703 | 00 | REH-MD01-MDU - Wadi Yemm - the floor drain location conflicts with the architectural wall - First Floor - (Plot -1036). | 1036 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000005 | OC-SCR-000704 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between Drain Pipes and Arch Blockwork wall - First Floor - (Plot -1036). | 1036 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000006 | OC-SCR-000705 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Structure Opening for Mep Pipes and Architecture Wall. - First Floor - (Plot -1036). | 1036 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000007 | OC-SCR-000706 | 00 | REH-MD01-MDU - Wadi Yemm - Firefighting pipes clash with the structural framing. - First Floor - (Plot -1036) | 1036 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000041 | OC-SCR-000707 | 00 | REH-MD01-MDU - Wadi Yemm - Coordination Conflict Between the Architectural, Structural, and MEP disciplines at Plot 1022 Part 01 – Ground Floor | 1022 | 2026-08-08 | 2026-08-13 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000042 | OC-SCR-000708 | 00 | REH-MD01-MDU - Wadi Yemm - Shaft Opening Missing for Drain stacks - SP06-Plot1022 - Part 01 - Ground Floor | 1022 | 2026-08-08 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000043 | OC-SCR-000709 | 00 | REH-MD01-MDU - Wadi Yemm - Shaft Location Confict Between Ground & First Floor - SP06 - Plot 1022 - Part 01- Ground Floor | 1022 | 2026-08-08 | 2026-08-10 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000044 | OC-SCR-000710 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Cavity Wall for Water Closet - SP06- Plot 1022 - Part 01- Ground Floor | 1022 | 2026-08-08 | 2026-08-17 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000045 | OC-SCR-000734 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structure or Architecture Openings for MEP Service SP06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-19 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000046 | OC-SCR-000735 | 00 | REH-MD01-MDU - Wadi Yemm - Openings at Ground floor Clash with Architectural Walls and Structural Beams of basement floor Sp06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000047 | OC-SCR-000736 | 00 | REH-MD01-MDU - Wadi Yemm - Plumbing Fixtures (Lavatory & Water Closet) Clashing with Structural Column at Ground Floor SP06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-17 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000048 | OC-SCR-000737 | 00 | REH-MD01-MDU - Wadi Yemm - ARCH Shaft are insufficient to accomodate duct work beside it clashes with STR Column SP06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-19 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000049 | OC-SCR-000738 | 00 | REH-MD01-MDU - Wadi Yemm - Omission of Drainage Pipes in Plumbing Model SP06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-17 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000050 | OC-SCR-000739 | 00 | REH-MD01-MDU - Wadi Yemm - Duct Size Discrepancy SP06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000051 | OC-SCR-000740 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural Shafts Size and Quantity Mismatch Between Basement and Ground Floor Levels for the same location at Sp06-1022-PART 3A | 1022 | 2026-08-09 | 2026-08-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1044-SCR-000003 | OC-SCR-000747 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between drainge & structure ( coulms) | 1044 | 2026-08-10 | 2026-08-12 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000015 | OC-SCR-000755 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q-1035) Issues for Ground Floor Builder Work | 1029 | 2026-08-10 | 2026-08-12 | Responded
REH-MD01-MDU-DR-OC-Hil-1026-SCR-000001 | OC-SCR-000767 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between drainge & structure ( beam) | 1026 | 2026-08-11 | 2026-08-12 | Responded
REH-MD01-MDU-AC-OC-Hil-1021-SCR-000001 | OC-SCR-000780 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about HVAC Clash With STR Beams - 1021 in Basement 02 floor | 1021 | 2026-08-12 | 2026-08-19 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000001 | OC-SCR-000782 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Drainage Pipes Clash With STR Beams - 1021 in Ground floor | 1021 | 2026-08-12 | 2026-08-19 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000001 | OC-SCR-000784 | 00 | REH-MD01-MDU - Wadi Yemm - Toilet Cavity Clash with Structural Beam Affecting MEP Coordination – Plot-1018 | 1022 | 2026-08-12 | 2026-08-17 | Responded
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000001 | OC-SCR-000781 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for WC and Floor Drain Drainage Routing | XXXX | 2026-08-12 | 2026-08-19 | Responded
REH-MD01-MDU-DR-OC-Hil-1024-SCR-000001 | OC-SCR-000788 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification on Elevator & Storage pit level and served systems - RA06 - plot 1024 | 1024 | 2026-08-12 | 2026-08-17 | Responded
REH-MD01-MDU-DR-OC-Hil-1044-SCR-000001 | OC-SCR-000793 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between drainge & structure ( coulms) | 1044 | 2026-08-13 | 2026-08-17 | Responded
REH-MD01-MDU-DR-OC-Hil-1044-SCR-000002 | OC-SCR-000815 | 00 | REH-MD01-MDU - Wadi Yemm - Missing (Oil Interceptor on Drawings) & (Grease Interceptor Sump pit & pipe connection | 1044 | 2026-08-16 | 2026-08-22 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000002 | OC-SCR-000837 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Missing Submersible Sewage Ejector Pump | 1022 | 2026-08-17 | 2026-08-25 | Responded
REH-MD01-MDU-AC-OC-Hil-XXXX-SCR-000001 | OC-SCR-000853 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Fabrication Description for Smoke Exhaust Duct Sheet Metal. | XXXX | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000003 | OC-SCR-000861 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Mechanical and Landscape IFC Models – Plot 1046 | 1022 | 2026-08-19 | 2026-08-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000004 | OC-SCR-000862 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural Cavity Opening Clashing with Structural Framing – SP06 Plot 1045 Part 18 | 1022 | 2026-08-19 | 2026-08-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000005 | OC-SCR-000875 | 00 | REH-MD01-MDU - Wadi Yemm - Rectangular Openings in Column Cap at Ground Floor – SP06-1046 – Part 23 | 1022 | 2026-08-19 | 2026-08-31 | Responded
REH-MD01-MDU-AC-OC-Hil-1021-SCR-000002 | OC-SCR-000896 | 00 | REH-MD01-MDU - Wadi Yemm -Clarification about Minimum Duct Elevation and clear height in basement - 1021 in Basement 02 floor | 1021 | 2026-08-20 | 2026-08-25 | Responded
REH-MD01-MDU-AC-OC-Hil-1022-SCR-000001 | OC-SCR-000897 | 00 | REH-MD01-MDU - Wadi Yemm -STRUCTURAL CLARIFICATIONS – Super Plot 06, Plot 1022 | 1022 | 2026-08-20 | 2026-08-26 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000006 | OC-SCR-000901 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Storm Drain, AC Condensate and Planter Drain Lines Routing | 1022 | 2026-08-22 | 2026-08-26 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000004 | OC-SCR-000913 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Drain Valve for Chilled Water Network and Floor Drain for Drainage Plot-1060 | 1060 | 2026-08-23 | 2026-08-24 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000005 | OC-SCR-000914 | 00 | REH-MD01-MDU - Wadi Yemm - Access Door Requirement for Shaft Opening Within Solid Structural Walls Plot-1060 | 1060 | 2026-08-23 | 2026-08-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000001 | OC-SCR-000927 | 00 | REH-MD01-MDU - Wadi Yemm - Misalignment Between Architectural Shaft Opening and Structural Opening -SP01-Plot1029 | 1029 | 2026-08-24 | 2026-09-02 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000002 | OC-SCR-000928 | 00 | REH-MD01-MDU - Wadi Yemm - Architechure Cavity Opening clashing with Strucutre beam-SP01-Plot1029 | 1029 | 2026-08-24 | 2026-09-02 | Responded
REH-MD01-MDU-AC-OC-Hil-1021-SCR-000003 | OC-SCR-000936 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Sound Attenuator (SAT) Of Ventilation Fans - 1021 in Basement 01 floor . | 1021 | 2026-08-25 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000007 | OC-SCR-000957 | 00 | REH-MD01-MDU - Wadi Yemm - Sump Pit Drainage and Submersible Pump Flow Rate – Irrigation & Fire Pump Rooms | 1022 | 2026-08-26 | 2026-09-03 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000003 | OC-SCR-000959 | 00 | REH-MD01-MDU - Wadi Yemm - Sump Pit Inlet Invert Level and Required Pit Depth | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000004 | OC-SCR-000960 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q-1029) Missing Floor Drain in Plumbing System | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000005 | OC-SCR-000961 | 00 | REH-MD01-MDU - Wadi Yemm - Floor Drain (FD) Locations Discrepancy | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000006 | OC-SCR-000962 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q-1029) Sump Pits Locations Discrepancy | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000007 | OC-SCR-000963 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q-1029) Clarification Required for Trench Drain Configuration at Ramp Ends (Arch. vs.Plumbing Drawings) | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000008 | OC-SCR-000964 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 - Clarification Required for Elevator Pit Drainage | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000009 | OC-SCR-000965 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 - Discrepancy in Number of Sump Pits | 1029 | 2026-08-29 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1031-SCR-000001 | OC-SCR-000971 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about conflict Between Drainage pipe network and vertical stack Conection- SP02- 1031&1032&1033 | 1031 | 2026-08-30 | 2026-09-03 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000010 | OC-SCR-000972 | 00 | REH-MD01-MDU - Wadi Yemm - Floor Drain Locations Clashing with Column Caps -SP01-Plot 1035 | 1029 | 2026-08-30 | 2026-08-31 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000011 | OC-SCR-000973 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between arch wall of ground floor and arch wall of basement floor -SP01-Plot 1035 | 1029 | 2026-08-30 | 2026-09-08 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000012 | OC-SCR-000974 | 00 | REH-MD01-MDU - Wadi Yemm - Clash Between MEP service opening and structural beam -SP01-Plot 1035 | 1029 | 2026-08-30 | 2026-09-01 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000013 | OC-SCR-000975 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Opening for MEP Service -SP01-Plot 1035 | 1029 | 2026-08-30 | 2026-09-03 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000014 | OC-SCR-000976 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between ground Floor I.D shaft walls and structural opening -SP01-Plot 1035 | 1029 | 2026-08-30 | 2026-09-08 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000015 | OC-SCR-000986 | 00 | REH-MD01-MDU - Wadi Yemm - SP01(Q3-1035) Lower Ground Missing Architectural Cavity Openings for Draiange pipes | 1029 | 2026-08-31 | 2026-09-03 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000016 | OC-SCR-000987 | 00 | REH-MD01-MDU - Wadi Yemm - SP01(Q3-1035) Lower Ground Architechure Cavity Opening clashing with Strucutre Beam | 1029 | 2026-08-31 | 2026-09-03 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000052 | OC-SCR-001002 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy in Tank Levels and Available Water Depth – Domestic, Irrigation & Fire Water Tanks | 1022 | 2026-09-01 | 2026-09-09 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000006 | OC-SCR-000999 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about suction Pit of Tanks (fire -domestic -irrigation ) in 1060 sport club B01. | 1060 | 2026-09-01 | 2026-09-02 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000002 | OC-SCR-001010 | 00 | REH-MD01-MDU - Wadi Yemm - Low Flow Velocity in Forced Main Pipe(Discharge pipe) SWP(11A&11B) for Condensate Drain Line - 1021 in B02 floor. | 1021 | 2026-09-02 | 2026-09-07 | Responded
REH-MD01-MDU-FF-OC-Hil-1024-SCR-000001 | OC-SCR-001012 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Suction Pit in Fire fighting & Domestic tank - 1024 | 1024 | 2026-09-02 | 2026-09-03 | Responded
REH-MD01-MDU-AC-OC-Hil-1021-SCR-000004 | OC-SCR-001021 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural shaftand and Structural Opening is not sufficient for duct at ground floor SP04-1021 | 1021 | 2026-09-02 | 2026-09-10 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000003 | OC-SCR-001022 | 00 | REH-MD01-MDU - Wadi Yemm - Openings at Ground Floor Clash with Architectural Walls and Structural Framings - Misalignment between Architectural and Structural Openings at ground floor SP04-1021 | 1021 | 2026-09-02 | 2026-09-09 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000004 | OC-SCR-001023 | 00 | REH-MD01-MDU - Wadi Yemm - Missing architectural cavities and structural openings required for MEP services at ground floor of SP04-1021 | 1021 | 2026-09-02 | 2026-09-15 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000005 | OC-SCR-001024 | 00 | REH-MD01-MDU - Wadi Yemm - Plumbing fixtures clashing with structural framing at ground floor SP04-1021 | 1021 | 2026-09-02 | 2026-09-10 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000006 | OC-SCR-001025 | 00 | REH-MD01-MDU - Wadi Yemm - Openings for MEP services are in column cap at ground floor SP04-1021 | 1021 | 2026-09-02 | 2026-09-10 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000007 | OC-SCR-001026 | 00 | REH-MD01-MDU - Wadi Yemm - Lavatory Drain Pipe Routing Conflict with Double Slab and Missing Cavity Wall at ground floor SP04-1021 | 1021 | 2026-09-02 | 2026-09-13 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000008 | OC-SCR-001027 | 00 | REH-MD01-MDU - Wadi Yemm -Missing Structural & Architectural Opening for MEP Services -SP04-Plot 1021-Basement 01 floor | 1021 | 2026-09-02 | 2026-09-10 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000009 | OC-SCR-001028 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict between Arch. & Str. & Plumbing -SP04-Plot 1021-Basement 01 floor | 1021 | 2026-09-02 | 2026-09-13 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000010 | OC-SCR-001029 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Arch cavity for water closet-SP04-Plot 1021-Basement 01 floor | 1021 | 2026-09-02 | 2026-09-15 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000017 | OC-SCR-001019 | 00 | REH-MD01-MDU - Wadi Yemm - Misalignment Between Architectural Shaft Opening and Structural Opening -SP01-Plot1029 | 1029 | 2026-09-02 | 2026-09-15 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000018 | OC-SCR-001018 | 00 | REH-MD01-MDU - Wadi Yemm - Architechure Cavity Opening clashing with Strucutre beam-SP01-Plot1029 | 1029 | 2026-09-02 | 2026-09-15 | Responded
REH-MD01-MDU-FF-OC-Hil-1024-SCR-000002 | OC-SCR-001017 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification About the Levels of the Tank rooms and pump rooms & Missing drainage line- RA06 - 1024 | 1024 | 2026-09-02 | 2026-09-06 | Responded
REH-MD01-MDU-FF-OC-Hil-1027-SCR-000001 | OC-SCR-001016 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Fire Hose Cabinet Installation – Basement | 1027 | 2026-09-02 | 2026-09-07 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000014 | OC-SCR-001013 | 00 | REH-MD01-MDU - Wadi Yemm - IRRIGATION TANK EMERGENCY PUMP REQUIREMENT | XXXX | 2026-09-02 | 2026-09-06 | Responded
REH-MD01-MDU-ME-OC-Hil-1027-SCR-000002 | OC-SCR-001033 | 00 | REH-MD01-MDU - Wadi Yemm - Misalignment Between Mechanical Models and Architectural Model – Fortaleza – Plot 1027 | 1027 | 2026-09-02 | 2026-09-08 | Responded
REH-MD01-MDU-ME-OC-Hil-1027-SCR-000003 |  | 00 | REH-MD01-MDU - Wadi Yemm - MEP Services Clashes with Structural & Architectural Elements – PLOT 1027 | 1027 | 2026-09-02 | 2026-09-10 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000011 | OC-SCR-001045 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy in Inlet Invert Level Clearance & Sump Pit Height Calculation - 1021 in B02 floor . | 1021 | 2026-09-05 | 2026-09-13 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000008 |  | 00 | REH-MD01-MDU - Wadi Yemm -Conflict Between Previous SCR Response and IFC Drawings – Drainage Shaft and Structural Beam | 1022 | 2026-09-05 | 2026-09-13 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000009 | OC-SCR-001065 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Structural Opening and Architecture shaft opening for Drainage services | 1022 | 2026-09-06 | 2026-09-15 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000010 | OC-SCR-001069 | 00 | REH-MD01-MDU - Wadi Yemm - Opening Clash With Structural Framing – SP06 – Plot 1022 – Part 04 | 1022 | 2026-09-06 | 2026-09-15 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000011 | OC-SCR-001068 | 00 | REH-MD01-MDU - Wadi Yemm - Planter Drain Not Provided in Landscape Model – SP06 – Plot 1022 – Part 04 | 1022 | 2026-09-06 | 2026-09-16 | Responded
REH-MD01-MDU-FS-OC-Hil-XXXX-SCR-000001 | OC-SCR-001081 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Fire Fighting Pipe Fittings Material | XXXX | 2026-09-07 | 2026-09-16 | Responded
REH-MD01-MDU-DR-OC-Hil-1028-SCR-000001 | OC-SCR-001085 | 00 | REH-MD01-MDU - Wadi Yemm - Stracture shaft opening clashes with Architectural wall -RA-02-Plot1028-ground floor | 1028 | 2026-09-08 | 2026-09-09 | Responded
REH-MD01-MDU-DR-OC-Hil-1028-SCR-000002 | OC-SCR-001086 | 00 | REH-MD01-MDU - Wadi Yemm - Structural shaft Opening in Column Cap RA-02-Plot1028-ground floor | 1028 | 2026-09-08 | 2026-09-09 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000012 | OC-SCR-001094 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural Cavity Opening Clashing with Structural Beam – SP06-Plot 1018-Part 10 | 1022 | 2026-09-08 | 2026-09-16 | Responded
REH-MD01-MDU-FS-OC-Hil-1027-SCR-000002 | OC-SCR-001093 | 00 | REH-MD01-MDU - Wadi Yemm - FHC Cavities and Shaft Coordination – Fortaleza – Plot 1027 Basement 02 & 01 | 1027 | 2026-09-08 | 2026-09-10 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000053 | OC-SCR-001092 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy Between IFC Landscape and IFC Swimming Pool Drawings – Pipes penetrating the Main Slab | 1022 | 2026-09-08 | 2026-09-15 | Responded
REH-MD01-MDU-ME-OC-Hil-1022-SCR-000054 | OC-SCR-001119 | 00 | REH-MD01-MDU - Wadi Yemm - Missing vacuum line in main swimming pool in ifc package -SP06-Plot1045- Part 17 | 1022 | 2026-09-09 | 2026-09-17 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000013 | OC-SCR-001118 | 00 | REH-MD01-MDU - Wadi Yemm - Planter Drain Not Provided in Landscape Model -SP06-Plot1045-Part 17 | 1022 | 2026-09-09 | 2026-09-21 | Responded
REH-MD01-MDU-DR-OC-Hil-1031-SCR-000002 | OC-SCR-001131 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Drainage Pipes and Beams at Attic Slab below lower ground slab - SP02- 1031 | 1031 | 2026-09-13 | 2026-09-15 | Responded
REH-MD01-MDU-FS-OC-Hil-1021-SCR-000001 | OC-SCR-001132 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about FHC Class II& FHC Class III in basement floors- 1021 in Basement 02 &01 | 1021 | 2026-09-13 | 2026-09-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000014 | OC-SCR-001144 | 00 | REH-MD01-MDU - Wadi Yemm - Drainage Pipes Routing – Grid 46C-9 & 46C-C | 1022 | 2026-09-13 | 2026-09-16 | Responded
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000002 | OC-SCR-001145 | 00 | REH-MD01-MDU - Wadi Yemm - Submersible Pump Capacity Discrepancy Between RA06 (1024) and RA01 to RA05 in Case of (fire scenario) | XXXX | 2026-09-13 | 2026-09-24 | Responded
REH-MD01-MDU-AC-OC-Hil-XXXX-SCR-000002 | OC-SCR-001155 | 00 | REH-MD01-MDU - Wadi Yemm - FCU Return Duct (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-20 | Responded
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000003 | OC-SCR-001156 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification and Unification of Calculation Criteria for Submersible Sewage Pumps | XXXX | 2026-09-14 | 2026-09-27 | Responded
REH-MD01-MDU-FS-OC-Hil-XXXX-SCR-000002 | OC-SCR-001157 | 00 | REH-MD01-MDU - Wadi Yemm - OS&Y gate valve located at the fire tie in of the apartment (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000015 | OC-SCR-001158 | 00 | REH-MD01-MDU - Wadi Yemm - Water heater configuration concept for the apartments (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-17 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000016 | OC-SCR-001159 | 00 | REH-MD01-MDU - Wadi Yemm - Water hammer arrestor configuration concept for the apartments (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-27 | Responded
REH-MD01-MDU-AC-OC-Hil-1027-SCR-000001 | OC-SCR-001160 | 00 | REH-MD01-MDU - Wadi Yemm - HVAC Duct Clash with Structural Framing - Fortaleza - Plot1027 | 1027 | 2026-09-14 | 2026-09-28 | Responded
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000004 | OC-SCR-001161 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Request for Routing Last Bathroom Drainage pipes to Drainage Network via Sleeves | XXXX | 2026-09-14 | 2026-09-17 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000015 | OC-SCR-001164 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural Cavity Conflict with Structural Framing – SP06-Plot 1046-Part 19 | 1022 | 2026-09-14 | 2026-09-17 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000017 | OC-SCR-001165 | 00 | REH-MD01-MDU - Wadi Yemm - IRRIGATION TANK EMERGENCY PUMP REQUIREMENT (Shaker). | XXXX | 2026-09-14 | 2026-09-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1023-SCR-000001 | OC-SCR-001178 | 00 | REH-MD01-MDU - Wadi Yemm - Trench Drain Location Above Water Supply Tank - 1st Basement Floor Slab - (Plot -1023). | 1023 | 2026-09-15 | 2026-09-23 | Responded
REH-MD01-MDU-DR-OC-Hil-1021-SCR-000012 | OC-SCR-001180 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about Accessibility of Drainage Pipes within the Attic Slab - 1021 in Ground floor . | 1021 | 2026-09-15 | 2026-09-23 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000016 | OC-SCR-001181 | 00 | REH-MD01-MDU - Wadi Yemm - Mep Service Clash With Structure Framing and column caps -SP06-Plot1045-Part 17 | 1022 | 2026-09-15 | 2026-09-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1031-SCR-000003 | OC-SCR-001182 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification for Adding Double Wall in handicap Toilets to Accommodate Water Supply and Drainage Pipes SP02 - 103 | 1031 | 2026-09-15 | 2026-09-24 | Responded
REH-MD01-MDU-AC-OC-Hil-XXXX-SCR-000003 | OC-SCR-001190 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Specification and HVAC Data (ECG Package) | XXXX | 2026-09-17 | 2026-09-20 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000019 | OC-SCR-001192 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q4-1037) 1st Floor Conflict between ARCH model with Pluming Opening | 1029 | 2026-09-16 | 2026-09-21 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000020 | OC-SCR-001193 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q4-1037) 1st Floor Missing Storm Floor Drain Piping | 1029 | 2026-09-16 | 2026-09-21 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000016 | OC-SCR-001195 | 00 | REH-MD01-MDU - Wadi Yemm - A Conflict Between ID and ST and ARCH Openings for Drainage and Gas Pipes in Kitchen Shafts – SP01-plot 1035 | 1029 | 2026-09-16 | 2026-09-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000017 | OC-SCR-001196 | 00 | REH-MD01-MDU - Wadi Yemm - A Conflict Between Structure and Arch opening and structure framing below – SP01-plot 1035 | 1029 | 2026-09-16 | 2026-09-24 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000018 | OC-SCR-001197 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Tank Circulation Pump Schedule | XXXX | 2026-09-16 | 2026-09-20 | Responded
REH-MD01-MDU-SP-OC-Hil-1029-SCR-000001 | OC-SCR-001198 | 00 | REH-MD01-MDU - Wadi Yemm - SP01 (Q4-1037) Conflict between Heat Pump Piping and Pressurized HVAC Opening | 1029 | 2026-09-16 | 2026-09-29 | Responded
REH-MD01-MDU-AC-OC-Hil-1025-SCR-000002 | OC-SCR-001216 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification on Supply and Exhaust Air Duct Dimensions – Plot 1025 – Fourth Floor | 1025 | 2026-09-17 | 2026-09-20 | Responded
REH-MD01-MDU-SP-OC-Hil-1022-SCR-000001 | OC-SCR-001218 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy Between IFC Landscape and IFC Swimming Pool Drawings – Pipes penetrating the Main Slab | 1022 | 2026-09-17 | 2026-09-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000005 | OC-SCR-001236 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Architecture and Strucutre Openings for MEP Service-RA-04-Plot1025-4th floor | 1025 | 2026-09-19 | 2026-09-22 | Responded
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000005 | OC-SCR-001252 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Sand Interseptor Design Flow Rate (ECG Plots | XXXX | 2026-09-20 | 2026-09-21 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000017 | OC-SCR-001254 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Drain Pipes Within Cavity Walls and Structural Framing Plot-1046 Part-21 | 1022 | 2026-09-20 | 2026-09-24 | Responded
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000006 | OC-SCR-001258 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Oil/Sand Interceptor Requirement | XXXX | 2026-09-20 | 2026-09-27 | Responded
REH-MD01-MDU-DR-OC-Hil-1031-SCR-000004 | OC-SCR-001268 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification aboyt Conflict Between Architectural Cavity Opening and Structural Beam-SP02-Plot1031-Ground floor | 1031 | 2026-09-21 | 2026-09-29 | Responded
REH-MD01-MDU-ME-OC-Hil-1031-SCR-000001 | OC-SCR-001269 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Swimming Pool Mechanical Pipe and Structural Slab at Swimming Pool Area -SP02-Plot1031-GF | 1031 | 2026-09-21 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1031-SCR-000002 | OC-SCR-001270 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict Between Swimming Pool Mechanical Pipe and Structural beam at Swimming Pool Area -SP02-Plot1031-GF | 1031 | 2026-09-21 | 2026-10-06 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000019 | OC-SCR-001271 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Fire Hose Cabinet Installation | XXXX | 2026-09-21 | 2026-09-30 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000020 | OC-SCR-001273 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification for Aboveground Water Supply Pipe Material for Diameters Exceeding 100 mm (4") | XXXX | 2026-09-21 | 2026-09-24 | Responded
REH-MD01-MDU-DR-OC-Hil-1027-SCR-000001 | OC-SCR-001274 | 00 | REH-MD01-MDU - Wadi Yemm - Discrepancy Between Architectural Bathroom Fixtures and Drainage Connections | 1027 | 2026-09-21 | 2026-09-28 | Responded
REH-MD01-MDU-ME-OC-Hil-1027-SCR-000004 | OC-SCR-001276 | 00 | REH-MD01-MDU - Wadi Yemm - Missing MEP Shaft for Water Supply Pipes – Plot 1027 | 1027 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-DR-OC-Hil-1026-SCR-000002 | OC-SCR-001278 | 00 | REH-MD01-MDU - Wadi Yemm - Missing Balacony drain and Planter Drain -RA-04-Plot1026-First Floor Level | 1026 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000006 | OC-SCR-001279 | 00 | REH-MD01-MDU - Wadi Yemm - Basement Sprinkler Zone Control Valve Arrangement – Basement 02 | 1025 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1025-SCR-000007 | OC-SCR-001280 | 00 | REH-MD01-MDU - Wadi Yemm - Basement 02 Fire Protection Area Exceeding ZCV Limit | 1025 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1028-SCR-000005 | OC-SCR-001292 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Required CO₂ Capacity for Fire Suppression System – LV Room, Basement 01, Plot 1028 | 1028 | 2026-09-22 | 2026-09-23 | Responded
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000009 | OC-SCR-001298 | 00 | REH-MD01-MDU - Wadi Yemm - HVAC Ducts, Drain Pipes Clash with Structural Plans in Basement 02 - SP04 - Plot1021 | 1021 | 2026-09-23 | 2026-09-29 | Responded
REH-MD01-MDU-SP-OC-Hil-1043-SCR-000001 | OC-SCR-001299 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification balancing tanks Dimensions of SP07-1043 swimming pools. | 1043 | 2026-09-23 | 2026-10-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1023-SCR-000001 | OC-SCR-001304 | 00 | REH-MD01-MDU - Wadi Yemm - Irrigation Tank Compartment Configuration - Basement 02 – Plot 1023 | 1023 | 2026-09-23 | 2026-10-01 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000018 | OC-SCR-001312 | 00 | REH-MD01-MDU - Wadi Yemm - Architectural and Structural Conflict Affecting MEP Pipe Routing – SP06 – Plot 1046 | 1022 | 2026-09-24 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000019 | OC-SCR-001313 | 00 | REH-MD01-MDU - Wadi Yemm - Shower Drain Not Provided in Drainage Drawings -SP06-Plot1046-Part 22-(T.O.C +19.60) | 1022 | 2026-09-24 |  | Pending
REH-MD01-MDU-AC-OC-Hil-1025-SCR-000003 | OC-SCR-001322 | 00 | REH-MD01-MDU - Wadi Yemm - Sand Trap Louver Area and Design Face Velocity | 1025 | 2026-09-24 | 2026-09-29 | Responded
REH-MD01-MDU-DR-OC-Hil-1044-SCR-000003 | OC-SCR-001324 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Required for Grease Interceptor Connections and Drainage System Layout | 1044 | 2026-09-24 | 2026-09-30 | Responded
REH-MD01-MDU-DR-OC-Hil-1044-SCR-000004 | OC-SCR-001325 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Irrigation Pump Flow Rate | 1044 | 2026-09-24 | 2026-10-01 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000020 | OC-SCR-001328 | 00 | REH-MD01-MDU - Wadi Yemm - Floor Drain Provision for Intake Courtyard and Fan Rooms | 1022 | 2026-09-26 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000021 | OC-SCR-001329 | 00 | REH-MD01-MDU - Wadi Yemm - Basement 02 Sump Pit Drainage Connection | 1022 | 2026-09-26 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000022 | OC-SCR-001330 | 00 | REH-MD01-MDU - Wadi Yemm - Ejector Pit Inlet Arrangement and Waste Line Connection Clarification | 1022 | 2026-09-26 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000023 | OC-SCR-001331 | 00 | REH-MD01-MDU - Wadi Yemm - Ejector Pump Schedule Discrepancy | 1022 | 2026-09-26 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000008 | OC-SCR-001332 | 00 | REH-MD01-MDU - Wadi Yemm - Conflict in Garbage choute shaft in third floor with the lower levels -Plot 1036 - Third floor | 1036 | 2026-09-26 | 2026-09-27 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000009 | OC-SCR-001333 | 00 | REH-MD01-MDU - Wadi Yemm - Exposed drain pipes & opening clashes with Arch. Walls -Plot 1036 - Third floor | 1036 | 2026-09-26 | 2026-09-27 | Responded
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000010 | OC-SCR-001334 | 00 | REH-MD01-MDU - Wadi Yemm - Openings for MEP services are in column cap -Plot 1036 - Third floor | 1036 | 2026-09-26 | 2026-09-27 | Responded
REH-MD01-MDU-DR-OC-Hil-1022-SCR-000024 | OC-SCR-001338 | 00 | REH-MD01-MDU - Wadi Yemm - Swimming Pool Room Drainage - SP06 | 1022 | 2026-09-27 |  | Pending
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000007 | OC-SCR-001347 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification of Oil/Sand Interceptor Requirement (To ECG, SHAKER, MODON & HILL) | XXXX | 2026-09-28 | 2026-09-29 | Responded
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000021 | OC-SCR-001358 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification on Water Supply Pipe Diameter size | XXXX | 2026-09-29 | 2026-10-01 | Responded
REH-MD01-MDU-ME-OC-Hil-1031-SCR-000003 | OC-SCR-001365 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification about conflict Between Fire fighting pipe and vertical Beam - SP02 - 1032 basement 01 floor . | 1031 | 2026-09-30 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1031-SCR-000002 | OC-SCR-001399 | 00 | REH-MD01-MDU-ME-OC-Hil-1031-SCR-000002 - Conflict Between Swimming Pool Mechanical Pipe and Structural beam at Swimming Pool Area -SP02-Plot1031-GF | 1031 | 2026-10-04 | 2026-10-04 | Responded
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000021 | OC-SCR-001395 | 00 | REH-MD01-MDU-DR-OC-Hil-1029-SCR-000021 - Conflict Between Structure and Arch opening and structure framing below - Plot 1035 | 1035 | 2026-10-04 | 2026-10-04 | Responded
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000018 | OC-SCR-001396 | 00 | REH-MD01-MDU-ME-OC-Hil-1029-SCR-000018 - Missing MEP Openings in Structural Column Cap - Plot 1035 | 1029 | 2026-10-04 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000019 | OC-SCR-001397 | 00 | REH-MD01-MDU-ME-OC-Hil-1029-SCR-000019 - Conflict Between ID and ST and ARCH Openings for Drainage and Gas Pipes in Kitchen Shafts – Plot 1035 | 1035 | 2026-10-04 | 2026-10-05 | Responded
REH-MD01-RUS-ME-OC-Hil-XXXX-SCR-000001 | OC-SCR-001422 | 00 | REH-MD01-RUS-ME-OC-Hil-XXXX-SCR-000001 - Ground Level On Promenade Area | xxxx | 2026-10-05 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1025-SCR-000001 | OC-SCR-001429 | 00 | REH-MD01-MDU-DR-OC-Hil-1025-SCR-000001-00 - Missing Landscape Levels for Inspection Chambers – Plot 1025 | 1025 | 2026-10-05 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1029-SCR-000025 | OC-SCR-001471 | 00 | REH-MD01-MDU-DR-OC-Hil-1029-SCR-000025 - Clarification Required for Sanitary Drainage Pipes Routing Through F&B Area - Plot 1034 | 1029 | 2026-10-07 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1036-SCR-000011 | OC-SCR-001484 | 00 | REH-MD01-MDU-ME-OC-Hil-1036-SCR-000011-Clarification of Level Difference Between Irrigation Tank and Pump Room - Plot 1036 | 1036 | 2026-10-07 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1029-SCR-000022 | OC-SCR-001488 | 00 | REH-MD01-MDU-ME-OC-Hil-1029-SCR-000022 - Clarification Request for MISSING PART AT AC PACKAGE | 1029 | 2026-10-10 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000010 | OC-SCR-001502 | 00 | REH-MD01-MDU-ME-OC-Hil-1021-SCR-000010 - Clarification of Level Difference Between Irrigation Tank and Pump Room - Plot 1021 | 1021 | 2026-10-11 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1021-SCR-000011 | OC-SCR-001505 | 00 | REH-MD01-MDU-ME-OC-Hil-1021-SCR-000011 - Clarification of Level Difference Between Irrigation Tank and Pump Room - Plot 1021 | 1021 | 2026-10-11 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1025-SCR-000002 | OC-SCR-001506 | 00 | REH-MD01-MDU-DR-OC-Hil-1025-SCR-000002 - Clarification Required – Stack Drain Pipes Roof Slab Openings -1025 | 1025 | 2026-10-11 |  | Pending
REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000008 | OC-SCR-001501 | 00 | REH-MD01-MDU-DR-OC-Hil-XXXX-SCR-000008 - Clarification Request for Kitchen Floor Drain Location SP 01 | xxxx | 2026-10-11 | 2026-10-11 | Responded
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000008 | OC-SCR-001509 | 00 | REH-MD01-MDU-ME-OC-Hil-1060-SCR-000008 - Architechure Cavity Opening clashing with Strucutre beam -Plot 1060 | 1060 | 2026-10-11 |  | Pending
REH-MD01-MDU-ME-OC-Hil-1060-SCR-000007 | OC-SCR-001508 | 00 | REH-MD01-MDU-ME-OC-Hil-1060-SCR-000007 - MEP Service Opening clashing with Strucutre beam-Plot 1060 | 1060 | 2026-10-11 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1031-SCR-000006 | OC-SCR-001507 | 00 | REH-MD01-MDU-DR-OC-Hil-1031-SCR-000006 - Clarification about Reroute the Drainage pipes to change invert level of inlet pipes of this sump pit no 02 at SP02- 1033 BASEMENT 01 | 1031 | 2026-10-11 |  | Pending
REH-MD01-MDU-DR-OC-Hil-1060-SCR-000001 | OC-SCR-001514 | 00 | REH-MD01-MDU-DR-OC-Hil-1060-SCR-000001-00 - Architechure Cavity Opening clashing with Strucutre beam -Plot 1060 | 1060 | 2026-10-11 |  | Pending
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000022 | OC-SCR-001515 | 0 | REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000022-00 - Clarification of LPG Piping Distribution Concept and Request for LPG Design Package - for 6 plots (ECG | XXXX | 2026-10-11 |  | Pending
REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000022 | OC-SCR-001515 | 0 | REH-MD01-MDU-ME-OC-Hil-XXXX-SCR-000022-00 - Clarification of LPG Piping Distribution Concept and Request for LPG Design Package - for 6 plots (ECG | XXXX | 2026-10-11 |  | Pending
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Ras Al Hekma Cape, Egypt.
Employer:- MoDon.
Lead Consultant:- SHAKER & ECG

## Telecom
Site Clarification Request ( Telecommunication )
Ref. | Mail No | Rev. | Subject | Sub-Building | Issue Date | Received Date | Action
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000032 | OC-SCR-000790 | 0 | REH-MD01-MDU -Wadi Yemm - ONT/ONU Conduit For Incoming Cable Conflication | XXXX | 2026-08-13 | 2026-08-17 | Responded
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000033 | OC-SCR-000808 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required for Disabled Toilet Alarm system (System Configuration - Control Panel Capacity) | XXXX | 2026-08-13 | 2026-08-17 | Responded
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000034 | OC-SCR-000809 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification Required for Disabled Toilet Alarm system ( Spare Parts - UL Approval - Emergency Power Supply ) | XXXX | 2026-08-13 | 2026-08-19 | Responded
REH-MD01-MDU-TE-OC-Hil-1044-SCR-000005 | OC-SCR-000810 | 0 | REH-MD01-MDU -Wadi Yemm - AV SYSTEM OF KIDS ROOM - GROUND FLOOR - 1044 | 1044 | 2026-08-13 | 2026-08-19 | Responded
REH-MD01-MDU-TE-OC-Hil-1018-SCR-000001 | OC-SCR-000820 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Data Outlet for LCP at Plot 1018 | 1018 | 2026-08-17 | 2026-08-23 | Responded
REH-MD01-MDU-TE-OC-Hil-1018-SCR-000002 | OC-SCR-000831 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Fiber Optic Rack for ONU at Ground Floor FTR Room in Plot 1018 | 1018 | 2026-08-17 | 2026-08-23 | Responded
REH-MD01-MDU-TE-OC-Hil-1022-SCR-000004 | OC-SCR-000832 | 0 | REH-MD01-MDU -Wadi Yemm - Access Control Devices Installation at Entrance Gate -Plot 1022 | 1022 | 2026-08-17 | 2026-08-24 | Responded
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000038 | OC-SCR-000842 | 0 | REH-MD01-MDU -Wadi Yemm - DAS Room Minimum Space Requirement – Clarification Request | XXXX | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-TE-OC-Hil-1018-SCR-000005 | OC-SCR-000847 | 0 | REH-MD01-MDU -Wadi Yemm - LOCATION OF IT RACK IN MULTIPURPOSE ROOM - Plot 1018 | 1018 | 2026-08-18 | 2026-08-24 | Responded
REH-MD01-MDU-TE-OC-Hil-1045-SCR-000008 | OC-SCR-000877 | 0 | REH-MD01-MDU -Wadi Yemm - AV System – Speaker Quantity & AV Wall Outlet Coordination - 1045 | 1045 | 2026-08-19 | 2026-08-25 | Responded
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000041 | OC-SCR-000885 | 0 | REH-MD01-MDU -Wadi Yemm - Different Design Details in LC SLDs – Clarification Request | XXXX | 2026-08-20 | 2026-08-26 | Responded
REH-MD01-MDU-TE-OC-Hil-1026-SCR-000014 | OC-SCR-000990 | 0 | REH-MD01-MDU -Wadi Yemm - Missing Door Controller panels and Data Points & Level Discrepancy in IFC/PDF drawings - ground floor plot (1026) | 1026 | 2026-08-31 | 2026-09-01 | Responded
REH-MD01-MDU-TE-OC-Hil-1046-SCR-000010 | OC-SCR-001099 | 0 | REH-MD01-MDU -Wadi Yemm - Floor boxes Clarification - Plot 1046-Ground floor | 1046 | 2026-09-08 | 2026-09-15 | Responded
REH-MD01-MDU-TE-OC-Hil-1046-SCR-000011 | OC-SCR-001100 | 0 | REH-MD01-MDU -Wadi Yemm - Volume control Clarification - Plot 1046-Ground floor | 1046 | 2026-09-08 | 2026-09-15 | Responded
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000059 | OC-SCR-001154 | 0 | REH-MD01-MDU -Wadi Yemm - Clarification for Telecommunication – External Interface (HILL/MODON) | XXXX | 2026-09-14 | 2026-09-21 | Responded
REH-MD01-MDU-TE-OC-Hil-1018-SCR-000022 | OC-SCR-001163 | 0 | REH-MD01-MDU -Wadi Yemm - RACK AND SLAB OPENING Clarification - PLOT 1018-FIRST BASEMENT&GROUND FLOOR | 1018 | 2026-09-14 | 2026-09-17 | Responded
REH-MD01-MDU-TE-OC-Hil-1023-SCR-000001 | OC-SCR-001177 | 0 | REH-MD01-MDU -Wadi Yemm - CHANGE THE SHAFT LOCATION FOR LIGHT CURRENT | 1023 | 2026-09-15 | 2026-09-29 | Responded
REH-MD01-MDU-TE-OC-Hil-XXXX-SCR-000066 | OC-SCR-001275 | 0 | REH-MD01-MDU - Wadi Yemm - Clarification of Our Scope Regarding Low Current Systems Components (ECG/Shaker) | XXXX | 2026-09-21 |  | Pending
REH-MD01-MDU-TE-OC-Hil-1031-SCR-000005 | OC-SCR-001277 | 00 | REH-MD01-MDU - Wadi Yemm - Clarification Regarding AMENITIES Telecom Single Line Diagram System - SP02 | 1031 | 2026-09-22 | 2026-09-24 | Responded
REH-MD01-MDU-TE-OC-Hil-1046-SCR-000015 | OC-SCR-001457 | 00 | REH-MD01-MDU-TE-OC-Hil-1046-SCR-000015 - Clarification of Apartment Type Discrepancy - PLOT 1046-FIRST FLOOR | 1046 | 2026-10-07 |  | Pending
REH-MD01-MDU-TE-OC-Hil-1046-SCR-000016 | OC-SCR-001475 | 00 | REH-MD01-MDU-TE-OC-Hil-1046-SCR-000016 - Clarification of Camera Data Outlets - PLOT 1046-FIRST FLOOR | 1046 | 2026-10-07 |  | Pending
Project Name:- REH Wadi Yemm DP01 - Sea Town Center
Location:- Ras Al Hekma Cape, Egypt.
Employer:- MoDon
Lead Consultant:- SHAKER & ECG