## RFI Action Register
RFI Action Register – Airport Project
Total RFIs | 249 | Open | 3 | 245 | TBC Route |  | #REF! |  |  |  |  | Overdue | 3
Purpose: keep the log simple — who does what, by when, and through which Aconex record.
drop down NACO / HILL
RFI No | REF | Subject | Discipline | Action By | Required Action / Next Action | Creation Date | Due Date | Date reply | Date Sent to NACO | NACO Due Date | NACO Date Reply | Aconex Ref. | Status | Mail no | Remarks
RFI-REH-AR01-OC-MOD-AR-0001 | 0 | P0153-K00146-REH International Airport Project – Missing Standing Seam layers Specifications | AR |  | Closed / no action | 2025-12-24 | 2025-12-27 | 2026-03-07 |  |  |  | 0 | Closed | MOD-RTRFI-000250 |  | NACO input required | NACO | Waiting NACO responded
RFI-REH-AR01-OC-MOD-AR-0002 | 0 | P0153-K00146-REH International Airport Project – SANITARY DETAIL in the ABLUTION | AR |  | Closed / no action | 2026-01-02 | 2026-01-05 | 2026-01-20 |  |  |  | 0 | Closed |  |  | Hill to Respond | HILL | NACO responded
RFI-REH-AR01-OC-MOD-AR-0003 | 0 | P0153-K00146-REH International Airport Project – Lighting poles RAL color | AR |  | Closed / no action | 2026-01-29 | 2026-02-01 | 2026-02-10 |  |  |  | 0 | Closed | MOD-RTRFI-000250 |  |  |  | Waiting HILL responded
RFI-REH-AR01-OC-MOD-AR-0004 | 0 | P0153-K00146-REH International Airport Project – Reduction for Doors dimension | AR |  | Closed / no action | 2026-02-01 | 2026-02-04 | 2026-03-07 |  |  |  | 0 | Closed | HillInt-RTRFI-000026 |  |  |  | Hill Responded
RFI-REH-AR01-OC-MOD-AR-0005 | 0 | REH International Airport Project – Missing structure support | AR |  | Closed / no action | 2026-02-11 | 2026-02-14 | 2026-03-01 |  |  |  | 0 | Closed | HillInt-RTRFI-000020
RFI-REH-AR01-OC-MOD-AR-0005 | 1 | REH International Airport Project – Missing structure support | AR |  | Closed / no action | 2026-03-05 | 2026-03-08 | 2026-03-17 |  |  |  | 1 | Closed | HillInt-RTRFI-000048
RFI-REH-AR01-OC-MOD-AR-0006 | 0 | REH International Airport Project – ARFF Station, Block Work Sizes | AR |  | Closed / no action | 2026-02-11 | 2026-02-14 | 2026-02-25 |  |  |  | 0 | Closed | HillInt-RTRFI-000009
RFI-REH-AR01-OC-MOD-AR-0007 | 0 | REH International Airport Project – TPO Roof Waterproofing | AR |  | Closed / no action | 2026-02-14 | 2026-02-17 | 2026-03-01 |  |  |  | 0 | Closed | HillInt-RTRFI-000023
RFI-REH-AR01-OC-MOD-AR-0008 | 0 | REH International Airport Project – Gate house 3 – louvers | AR |  | Closed / no action | 2026-02-15 | 2026-02-18 | 2026-02-25 |  |  |  | 0 | Closed | HillInt-RTRFI-000008
RFI-REH-AR01-OC-MOD-AR-0009 | 0 | REH International Airport Project – Screed Layer | AR |  | Closed / no action | 2026-03-04 | 2026-03-07 | 2026-03-26 |  |  |  | 0 | Closed | HillInt-RTRFI-000058
RFI-REH-AR01-OC-MOD-AR-0009 | 1 | REH International Airport Project – Screed Layer | AR |  | Closed / no action | 2026-05-17 | 2026-05-20 | 2026-05-21 |  |  |  | 1 | Closed | HillInt-RTRFI-000439
RFI-REH-AR01-OC-MOD-AR-0010 | 0 | REH International Airport Project – Rockwool façade insulation clarification | AR |  | Closed / no action | 2026-03-08 | 2026-03-11 | 2026-03-26 |  |  |  | 0 | Closed | HillInt-RTRFI-000057
RFI-REH-AR01-OC-MOD-AR-0011 | 0 | REH International Airport Project – screed – general inquiry | AR |  | Closed / no action | 2026-03-15 | 2026-03-18 | 2026-03-17 |  |  |  | 0 | Closed | HillInt-RTRFI-000046
RFI-REH-AR01-OC-MOD-AR-0012 | 0 | REH International Airport Project – External Static Pressure calculations for Gate 01 & 03 & 04 & Substation01 and 02 buildings | AR |  | Closed / no action | 2026-03-15 | 2026-03-18 | 2026-03-17 |  |  |  | 0 | Closed | HillInt-RTRFI-000044
RFI-REH-AR01-OC-MOD-AR-0013 | 0 | REH International Airport Project – lav. tap conflict with the window | AR |  | Closed / no action | 2026-03-15 | 2026-03-18 | 2026-03-17 |  |  |  | 0 | Closed | HillInt-RTRFI-000043
RFI-REH-AR01-OC-MOD-AR-0014 | 0 | REH International Airport Project – ARFF - Water Sprinkler System in ATM MER room MODIFICATION | AR |  | Closed / no action | 2026-03-15 | 2026-03-18 | 2026-03-17 |  |  |  | 0 | Closed | HillInt-RTRFI-000045
RFI-REH-AR01-OC-MOD-AR-0015 | 0 | REH International Airport Project – Roller Shutter Doors Clarifications | AR |  | Closed / no action | 2026-03-26 | 2026-03-29 | 2026-04-05 |  |  |  | 0 | Closed | HillInt-RTRFI-000085
RFI-REH-AR01-OC-MOD-AR-0016 | 00 | RFI-REH-AR01-OC-MOD-AR-0016-00 - REH International Airport Project – Fire Hose Cabinet | AR |  | Closed / no action | 2026-04-22 | 2026-04-25 | 2026-04-30 |  |  |  | 00 | Closed | HillInt-RTRFI-000331
RFI-REH-AR01-OC-MOD-AR-0017 | 0 | RFI-REH-AR01-OC-MOD-AR-0017-00 - REH International Airport Project – Discrepancy in heights of parapet walls at VVIP First floor | AR |  | Closed / no action | 2026-04-26 | 2026-04-29 | 2026-05-06 |  |  |  | 0 | Closed | HillInt-RTRFI-000358
RFI-REH-AR01-OC-MOD-AR-0018 | 0 | REH International Airport Project – VVIP TERMINAL Finishing | AR | NACO | NACO responded | 2026-04-28 | 2026-05-01 |  |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-AR-0019 | 0 | RFI-REH-AR01-OC-MOD-AR-0019-00 - REH International Airport Project - ARFFS Finishing | AR |  | Closed / no action | 2026-04-28 | 2026-05-01 | 2026-05-10 |  |  |  | 0 | Closed | HillInt-RTRFI-000363
RFI-REH-AR01-OC-MOD-AR-0020 | 0 | REH International Airport Project - Roofing and Coping and Façade System | AR | NACO | NACO responded | 2026-04-29 | 2026-05-02 | 2026-06-30 | 2026-05-21 | 2026-05-22 | 2026-06-29 |  | Closed | HillInt-RTRFI-000660 | To be categorized and assigned
RFI-REH-AR01-OC-MOD-AR-0021 | 0 | REH International Airport Project - VVIP Stone Cladding Below Signage | AR |  | NACO responded | 2026-05-02 | 2026-05-05 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-AR-0022 | 0 | REH International Airport Project - Aluminum Curtain Wall | AR |  | NACO responded | 2026-05-05 | 2026-05-08 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-AR-0023 | 0 | REH International Airport Project – Laminate HPL | AR |  | NACO responded | 2026-05-10 | 2026-05-13 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-AR-0023 | 1 | REH International Airport Project – Laminate HPL | AR | NACO | NACO responded | 2026-06-13 | 2026-06-16 | [5 empty] | Closed
RFI-REH-AR01-OC-MOD-AR-0023 | 2 | REH International Airport Project – Laminate HPL | AR | NACO | NACO responded | 2026-07-12 | 2026-07-15 | 2026-07-14 | 2026-07-12 | 2026-07-13 | 2026-07-14 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0024 | 0 | RFI-REH-AR01-OC-MOD-AR-0024-00 - REH International Airport Project – Clash between the ceiling level and the louver | AR | Hill | Review and assign next action | 2026-05-17 | 2026-05-20 | 2026-05-18 |  |  |  | 0 | Closed | HillInt-RTRFI-000420 | To be categorized and assigned
RFI-REH-AR01-OC-MOD-AR-0025 | 0 | RFI-REH-AR01-OC-MOD-AR-0025-00 - REH International Airport Project – missed door (FSD01-1) for VVIP TERMINAL package-260505 | AR | NACO |  | 2026-05-18 | 2026-05-21 | 2026-05-19 |  |  |  | 0 | Closed | HillInt-RTRFI-000425
RFI-REH-AR01-OC-MOD-AR-0026 | 0 | RFI-REH-AR01-OC-MOD-AR-0026-00 - REH International Airport Project – Finish and Foundation Coordination – VVIP Terminal - Basement Entrance | AR | NACO | NACO responded | 2026-05-21 | 2026-05-24 |  |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-AR-0027 | 0 | REH International Airport Project – Technical Coordination: Pavements, Waterproofing, and Slopes | AR | Hill |  | 2026-05-24 | 2026-05-27 | 2026-06-03 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-AR-0028 | 0 | RFI-REH-AR01-OC-MOD-AR-0028-00 - REH International Airport Project – Clash between ARCH-ID & DOORS packages (STD01-1.pf) | AR | NACO | NACO responded | 2026-05-25 | 2026-05-28 |  |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-AR-0029 | 0 | REH International Airport Project – GUTTER NEW DIMENSIONS | AR | NACO | NACO responded | 2026-06-01 | 2026-06-04 |  |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-AR-0030 | 0 | REH International Airport Project – Queries regarding Landscape Design | AR | NACO | NACO responded | 2026-06-01 | 2026-06-04 | 2026-07-01 | 2026-06-01 | 2026-06-02 |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0031 | 0 | REH International Airport Project – Roofing Type for ARFF station & Gatehouses | AR | Hill |  | 2026-06-02 | 2026-06-05 | 2026-06-02 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-AR-0032 | 0 | REH International Airport Project – Request for Approval to Replace Tilt-Up Door with Sectional Door | AR | NACO | NACO responded | 2026-06-07 | 2026-06-10 | 2026-06-23 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0033 | 0 | REH International Airport Project – Replace the honeycomb stone cladding for doors to painting | AR | Hill | Hill Responded | 2026-06-18 | 2026-06-21 | 2026-06-23 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0034 | 0 | RFI-REH-AR01-OC-MOD-AR-0034-00 - REH International Airport Project - Clarification of Wall Type & Flooring and Material Specification at Patio Area. IN (ARFFS) | AR | NACO | NACO responded | 2026-06-17 | 2026-06-20 |  | 2026-06-23 | 2026-06-24 |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0035 | 0 | RFI-REH-AR01-OC-MOD-AR-0035-00 - REH International Airport Project - Missing Ceiling Details and Specification Verification at External Area on axis (VP-X) / between (VP16) (VP17) in VVIP TERMINAL BUILDING | AR | NACO | NACO responded | 2026-06-23 | 2026-06-26 |  | 2026-06-25 | 2026-06-26 |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0036 | 0 | RFI-REH-AR01-OC-MOD-AR-0036-00 - REH International Airport Project - Lighting units around the VVIP building | AR | NACO | NACO responded | 2026-06-24 | 2026-06-27 |  | 2026-06-29 | 2026-06-30 | 2026-07-07 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0037 | 0 | RFI-REH-AR01-OC-MOD-AR-0037-00 - REH International Airport Project - Corner Washbasin for the ADA toilet at the ARFFS building and Washbasins for Gate House 3 and Chiller Plant | AR | NACO | NACO responded | 2026-06-24 | 2026-06-27 | 2026-07-09 | 2026-07-05 | 2026-07-06 | 2026-07-08 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0038 | 0 | RFI-REH-AR01-OC-MOD-AR-0038-00 - REH International Airport Project - Discrepancy Between Design Drawing and Authority Requirement for Escape Stair Width- ARRFS | AR | NACO | Closed / no action | 2026-06-25 | 2026-06-28 |  | 2026-07-05 | 2026-07-06 | 2026-07-06 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0038 | 1 | RFI-REH-AR01-OC-MOD-AR-0038-01 - REH International Airport Project - Discrepancy Between Design Drawing and Authority Requirement for Escape Stair Width- ARRFS | AR | NACO | NACO responded | 2026-07-09 | 2026-07-12 | 2026-07-19 | 2026-07-13 | 2026-07-14 | 2026-07-19 | HillInt-RTRFI-000827 | Closed
RFI-REH-AR01-OC-MOD-AR-0039 | 0 | RFI-REH-AR01-OC-MOD-AR-0039-00 - REH International Airport Project - Discrepancy Between Shower Door Handle provided by Aedes and handle specified in HW schedules | AR | NACO | NACO responded | 2026-07-01 | 2026-07-04 |  | 2026-07-05 | 2026-07-06 | 2026-07-08 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0040 | 0 | RFI-REH-AR01-OC-MOD-AR-0040-00 - REH International Airport Project - Proposal to Revise Accessible Roof Build-Up for Protection of TPO Waterproofing | AR | NACO | NACO responded | 2026-07-05 | 2026-07-08 | 2026-07-08 | 2026-07-10 | 2026-07-11 | 2026-07-09 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0041 | 0 | RFI-REH-AR01-OC-MOD-AR-0041-00 - REH International Airport Project - VVIP Terminal – DOORS IN ESCAPE ROUTE | AR | NACO | NACO responded | 2026-07-10 | 2026-07-13 |  | 2026-07-13 | 2026-07-14 | 2026-07-14 | 2026-07-14 | Closed
RFI-REH-AR01-OC-MOD-AR-0042 | 0 | RFI-REH-AR01-OC-MOD-AR-0042-00 - REH International Airport Project - VVIP Terminal – TIMBER DOORS – Perforated laser patterns | AR | Hill | Hill Responded | 2026-07-10 | 2026-07-13 | 2026-07-13 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0042 | 1 | RFI-REH-AR01-OC-MOD-AR-0042-00 - REH International Airport Project - VVIP Terminal – TIMBER DOORS – Perforated laser patterns | AR | Hill | Hill Responded | 2026-07-15 | 2026-07-18 | 2026-07-21 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0043 | 0 | RFI-REH-AR01-OC-MOD-AR-0043-00 - REH International Airport Project - VVIP Terminal - Compact wall-mounted unit with a Z-fold paper towel | AR | Hill | Hill Responded | 2026-07-29 | 2026-08-01 | 2026-08-02 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0044 | 0 | RFI-REH-AR01-OC-MOD-AR-0044-00 - REH International Airport Project - Stainless-Steel Door Hardware | AR | Hill | Hill Responded | 2026-08-13 | 2026-08-16 | 2026-08-16 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-AR-0045 | 0 | RFI-REH-AR01-OC-MOD-AR-0045-00 - REH International Airport Project – Missing Wall Finishes | AR | NACO | NACO responded | 2026-08-17 | 2026-08-20 |  | 2026-08-25 | 2026-08-26 | 2026-08-31 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0045 | 1 | RFI-REH-AR01-OC-MOD-AR-0045-00 - REH International Airport Project – Missing Wall Finishes | AR | NACO | NACO responded | 2026-09-08 | 2026-09-11 |  | 2026-09-09 | 2026-09-10 | 2026-09-15 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0046 | 0 | Curtains, Ceiling and Wall Finishes | AR | NACO | NACO responded | 2026-08-23 | 2026-08-26 |  | 2026-08-25 | 2026-08-26 | 2026-08-28 |  | Closed
RFI-REH-AR01-OC-MOD-AR-0047 | 0 | VVIP Terminal Ground Floor Expansion Joint | AR | Hill | Hill Responded | 2026-09-07 | 2026-09-10 | 2026-09-08 |  |  |  | HillInt-RTRFI-001235 | Closed
RFI-REH-AR01-OC-MOD-AR-0048 | 0 | Landscape Planter Boxes | AR | NACO | Waiting NACO responded | 2026-10-03 | 2026-10-06 |  | 2026-10-04 | 2026-10-05 |  |  | Open
RFI-REH-AR01-OC-MOD-AR-0049 | 0 | VVIP TERMINAL (Main building) – ISSUING INTERIOR DESIGN - (Table description LO-04 / LO-04A) | AR | NACO | NACO responded | 2026-10-10 | 2026-10-13 |  | 2026-10-11 | 2026-10-12 | 2026-10-11 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0001 | 0 | P0153-K00146-REH International Airport Project - AGL manhole base and level | EL |  | Closed / no action | 2025-10-24 | 2025-10-27 | 2025-10-29 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0002 | 0 | P0153-K00146-REH International Airport Project - M.V Switchgear Clarifications | EL |  | Closed / no action | 2025-12-24 | 2025-12-27 | 2026-01-12 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0003 | 0 | P0153-K00146-REH International Airport Project - Insulation class for Standby generators | EL |  | Closed / no action | 2025-12-28 | 2025-12-31 | 2026-01-12 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0004 | 0 | P0153-K00146-REH International Airport Project - Dry type transformers | EL |  | Closed / no action | 2026-01-05 | 2026-01-08 | 2026-01-12 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0005 | 0 | P0153-K00146-REH International Airport Project - MV Network clarifications | EL |  | Closed / no action | 2026-01-19 | 2026-01-22 | 2026-01-29 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0005 | 1 | REH International Airport Project - MV Network clarifications | EL |  | Closed / no action | 2026-03-16 | 2026-03-19 | 2026-03-18 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-EL-0006 | 0 | P0153-K00146-REH International Airport Project - M.V Cables | EL |  | Closed / no action | 2026-02-03 | 2026-02-06 | 2026-02-05 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0007 | 0 | P0153-K00146-REH International Airport Project - ATS Ratings Availability | EL |  | Closed / no action | 2026-02-04 | 2026-02-07 | 2026-02-10 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0008 | 0 | REH International Airport Project - ATS Ratings Availability | EL |  | Closed / no action | 2026-02-11 | 2026-02-14 | 2026-02-25 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0009 | 0 | REH International Airport Project - Main Distribution Panel Final Design | EL |  | Closed / no action | 2026-02-11 | 2026-02-14 | 2026-02-25 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0010 | 0 | REH International Airport Project - Lighting Fixture Clarifications | EL |  | Closed / no action | 2026-02-11 | 2026-02-14 | 2026-03-07 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0011 | 0 | REH International Airport Project - ( 20 - 22 ) Workshop Follow up (Elec Items) | EL |  | Closed / no action | 2026-02-15 | 2026-02-18 | 2026-03-07 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0011 | 1 | RFI-REH-AR01-OC-MOD-EL-0011-01 - REH International Airport Project – Missing Electrical Information's | EL | NACO | NACO responded | 2026-05-19 | 2026-05-22 | 2026-06-04 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-EL-0012 | 0 | REH International Airport Project - Bus way - New added item | EL |  | Closed / no action | 2026-02-17 | 2026-02-20 | 2026-03-01 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0013 | 0 | REH International Airport Project - poles lighting fixtures | EL |  | Closed / no action | 2026-02-22 | 2026-02-25 | 2026-03-24 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0014 | 0 | REH International Airport Project –Lighting control system | EL |  | Closed / no action | 2026-02-22 | 2026-02-25 | 2026-04-02 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0014 | 1 | RFI-REH-AR01-OC-MOD-EL-0014-01 - REH International Airport Project – Lighting Control System | EL | NACO | NACO responded | 2026-05-25 | 2026-05-28 | [5 empty] | Closed
RFI-REH-AR01-OC-MOD-EL-0015 | 0 | REH International Airport Project –Chiller plant electrical clarifications | EL |  | Closed / no action | 2026-03-16 | 2026-03-19 | 2026-03-24 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0016 | 0 | RFI-REH-AR01-OC-MOD-EL-0016-00 - REH International Airport Project - Cable trays and Cable Trunks – Cables Arrangement | EL |  | Closed / no action | 2026-04-01 | 2026-04-04 | 26-4-2026 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0017 | 0 | RFI-REH-AR01-OC-MOD-EL-0017-00 - REH International Airport Project - UPS centralized monitoring system | EL |  | Closed / no action | 2026-04-02 | 2026-04-05 | 21-4-2026 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0018 | 0 | RFI-REH-AR01-OC-MOD-EL-0018-00 - REH International Airport Project - Electric Conduits – GI Conduits categorization | EL |  | Closed / no action | 2026-04-09 | 2026-04-12 | 20-4-2026 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0019 | 0 | RFI-REH-AR01-OC-MOD-EL-0019+A61+C61:M92+A61+C61:M92+A61+C61:M92+C61:N92+A61+C61:M92 | EL | NACO | NACO responded | 2026-04-11 | 2026-04-14 |  |  |  |  | 0 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-EL-0019 | 1 | RFI-REH-AR01-OC-MOD-EL-0019-01 - REH International Airport Project - Missing Information and design discrepancies in Main Intake Substation | EL | Hill | NACO responded | 2026-08-03 | 2026-08-06 |  | 2026-08-05 |  | 2026-08-12 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0019 | 2 | RFI-REH-AR01-OC-MOD-EL-0019-01 - REH International Airport Project - Missing Information and design discrepancies in Main Intake Substation | EL | NACO | NACO responded | 2026-08-25 | 2026-08-28 |  | 2026-08-25 | 2026-08-26 | 2026-08-30 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0020 | 0 | RFI-REH-AR01-OC-MOD-EL-0020-00 - REH International Airport Project - Generator Room Ventilation Openings at Main Intake Substation & Canopy cancellation in all indoor substations | EL |  | Closed / no action | 2026-04-14 | 2026-04-17 | 2026-04-29 |  |  |  | 0 | Closed | HillInt-RTRFI-000311
RFI-REH-AR01-OC-MOD-EL-0021 | 0 | RFI-REH-AR01-OC-MOD-EL-0021-00 - REH International Airport Project - Optical Fiber backbone Network | EL |  | Closed / no action | 2026-04-14 | 2026-04-17 | 22-4-2026 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0022 | 0 | RFI-REH-AR01-OC-MOD-EL-0022-00 - REH International Airport Project – UPS ratings | EL |  | Closed / no action | 2026-04-23 | 2026-04-26 | 2026-05-03 |  |  |  | 0 | Closed | HillInt-RTRFI-000332
RFI-REH-AR01-OC-MOD-EL-0023 | 0 | RFI-REH-AR01-OC-MOD-EL-0023-00 - REH International Airport Project – MV Cable Routing | EL |  | Closed / no action | 2026-04-25 | 2026-04-28 | 2026-04-29 |  |  |  | 0 | Closed | HillInt-RTRFI-000276
RFI-REH-AR01-OC-MOD-EL-0024 | 0 | RFI-REH-AR01-OC-MOD-EL-0024-00 - REH International Airport Project – REH International Airport Project – camera poles clarifications | EL |  | Closed / no action | 2026-04-26 | 2026-04-29 | 2026-05-10 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-EL-0025 | 0 | RFI-REH-AR01-OC-MOD-EL-0025-00 - REH International Airport Project – ATS 400A integration with DB-UPS panels | EL | NACO | NACO responded | 2026-05-03 | 2026-05-06 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-EL-0026 | 0 | REH International Airport Project – Overall Telecommunication Network | EL |  | Closed / no action | 2026-05-05 | 2026-05-08 | 2026-05-13 |  |  |  | 0 | Closed | HillInt-RTRFI-000385
RFI-REH-AR01-OC-MOD-EL-0027 | 0 | Missing Conduit Path of Telecommunication Network at Airside | EL |  | Closed / no action | 2026-05-07 | 2026-05-10 | 2026-05-17 |  |  |  | 0 | Closed | HillInt-RTRFI-000393
RFI-REH-AR01-OC-MOD-EL-0028 | 0 | RFI-REH-AR01-OC-MOD-EL-0028-00 - REH International Airport Project – Electrical & ICT Rooms Issues at ARFF Building | EL |  | Closed / no action | 2026-05-11 | 2026-05-14 | 2026-05-16 |  |  |  | 0 | Closed | HillInt-RTRFI-000392
RFI-REH-AR01-OC-MOD-EL-0028 | 1 | Electrical Room Issues at ARFF Building | EL | NACO | Waiting NACO responded | 2026-09-02 | 2026-09-05 |  | 2026-09-07 | 2026-09-08 | 2026-10-04 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0029 | 0 | RFI-REH-AR01-OC-MOD-EL-0029-00 - REH International Airport Project – Missing BOH & VVIP Roof Lighting fixtures cut sheets | EL | NACO | NACO responded | 2026-05-13 | 2026-05-16 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-EL-0030 | 0 | RFI-REH-AR01-OC-MOD-EL-0030-00 - REH International Airport Project – Outdoor ATS Units Locations | EL | Hill |  | 2026-05-17 | 2026-05-20 | 2026-05-19 |  |  |  | 0 | Closed | HillInt-RTRFI-000422
RFI-REH-AR01-OC-MOD-EL-0031 | 0 | RFI-REH-AR01-OC-MOD-EL-0031-00 - REH International Airport Project – Clarification on Protection Device Ratings and Cable Sizing Discrepancies | El | NACO | NACO responded | 2026-05-21 | 2026-05-24 |  | 2026-05-21 | 2026-05-22 | 2026-06-26 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0032 | 0 | RFI-REH-AR01-OC-MOD-EL-0032-00 - REH International Airport Project – Proposed Use of Direct Buried Conduits Instead of Cable Tray/Cladding Arrangement | EL | NACO | NACO responded | 2026-05-26 | 2026-05-29 | 2026-06-23 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0033 | 0 | REH International Airport Project – Missing Service Sockets at Main Intake Substation | EL | NACO | Closed / no action | 2026-06-03 | 2026-06-06 |  |  |  |  | 2026-06-17 | Closed |  | Closed by mail by metting NACO
RFI-REH-AR01-OC-MOD-EL-0034 | 0 | Missing Electrical Information's in Airside Substation 1 | EL | NACO | NACO responded | 2026-06-10 | 2026-06-13 | 2026-06-23 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0034 | 1 | Missing Electrical Information's in Airside Substation 1&2 | EL | NACO | NACO responded | 2026-09-02 | 2026-09-05 |  | 2026-09-08 | 2026-09-09 | 2026-09-11 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0035 | 0 | RFI-REH-AR01-OC-MOD-EL-0035-00 - REH International Airport Project – Missing panel schedules in VVIP TERMINAL | EL | NACO | NACO responded | 2026-06-16 | 2026-06-19 | 2026-07-05 | 2026-06-29 | 2026-06-30 | 2026-06-29 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0036 | 0 | RFI-REH-AR01-OC-MOD-EL-0036-00 - REH International Airport Project - Separate Earthing Systems for LV and MV Network as per BEDC Report | EL | NACO | NACO responded | 2026-06-16 | 2026-06-19 | 2026-07-15 | 2026-06-22 | 2026-06-23 | 2026-07-14 | 2026-07-14 | Closed
RFI-REH-AR01-OC-MOD-EL-0037 | 0 | RFI-REH-AR01-OC-MOD-EL-0037-00 - REH International Airport Project - DB-P.K Panel in VVIP TERMINAL | EL | Hill | Hill Responded | 2026-06-16 | 2026-06-19 | 2026-06-29 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0038 | 0 | RFI-REH-AR01-OC-MOD-EL-0038-00 - REH International Airport Project - Location of ACC cabinets and required connections to TI and VDGS poles | EL | NACO | NACO responded | 2026-06-17 | 2026-06-20 | 2026-07-10 | 2026-06-29 | 2026-06-30 | 2026-07-09 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0038 | 1 | RFI-REH-AR01-OC-MOD-EL-0038-01 - REH International Airport Project - Location of ACC cabinets and required connections to TI and VDGS poles | EL | NACO | NACO responded | 2026-07-23 | 2026-07-26 |  | 2026-07-27 | 2026-07-28 | 2026-08-05 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0039 | 0 | RFI-REH-AR01-OC-MOD-EL-0039-00 - REH International Airport Project - Lightning Protection Copper Tape Routing Below Canopy / Shed | EL | Hill | Closed / no action | 2026-06-23 | 2026-06-26 | 2026-06-25 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0040 | 0 | RFI-REH-AR01-OC-MOD-EL-0040-00 - REH International Airport Project - Clarification on Single-Phase UPS | EL | NACO | NACO responded | 2026-06-25 | 2026-06-28 |  | 2026-06-29 | 2026-06-30 | 2026-07-16 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0041 | 0 | RFI-REH-AR01-OC-MOD-EL-0041-00 - REH International Airport Project - Clarification of Power Supply Source for Secondary Chilled Water Pumps | EL | NACO | Closed / no action | 2026-06-25 | 2026-06-28 |  | 2026-06-28 | 2026-06-29 | 2026-07-06 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0042 | 0 | REH International Airport Project - Required Clarifications for LS1 | EL | NACO | NACO responded | 2026-06-29 | 2026-07-02 | 2026-07-15 | 2026-06-29 | 2026-06-30 | 2026-07-14 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0042 | 1 | RFI-REH-AR01-OC-MOD-EL-0042-01 - REH International Airport Project - Required Clarifications for LS1 | EL | NACO | NACO responded | 2026-07-21 | 2026-07-24 |  | 2026-07-21 | 2026-07-22 | 2026-07-27 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0043 | 0 | REH International Airport Project - Lighting Control Clarifications | EL | Hill | Closed / no action | 2026-06-29 | 2026-07-02 | 2026-07-07 | 2026-07-05 | 2026-07-06 |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0044 | 0 | REH International Airport Project - Clarification Required for LVDB-LS-PS3 Power Source and Connected Load | EL | NACO | NACO responded | 2026-06-30 | 2026-07-03 | 2026-07-10 | 2026-07-05 | 2026-07-06 | 2026-07-08 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0044 | 1 | Clarification Required for LVDB-LS-PS3 Power Source and Connected Load | EL | NACO | NACO responded | 2026-08-16 | 2026-08-19 |  | 2026-08-16 | 2026-08-17 | 2026-08-23 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0044 | 2 | Clarification Required for 10 kVA UPS Associated with LVDBLS- PS2 & LVDB-LS-PS3 | EL | NACO | NACO responded | 2026-09-07 | 2026-09-10 |  | 2026-09-08 | 2026-09-09 | 2026-09-11 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0045 | 0 | REH International Airport Project - Clarification of LV Cable Insulation Type for Apron Area | EL | Hill | Hill Responded | 2026-06-30 | 2026-07-03 | 2026-07-05 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0046 | 0 | RFI-REH-AR01-OC-MOD-EL-0046-00 - REH International Airport Project - FOH Wiring Devices | EL | NACO | NACO responded | 2026-07-06 | 2026-07-09 |  | 2026-07-09 | 2026-07-10 | 2026-07-15 | 2026-07-16 | Closed
RFI-REH-AR01-OC-MOD-EL-0047 | 0 | RFI-REH-AR01-OC-MOD-EL-0047-00 - REH International Airport Project - Lightning Cable size Conflict at VVIP Terminal, Gate 3 and 4 | EL | NACO | NACO responded | 2026-07-06 | 2026-07-09 | 2026-07-15 | 2026-07-09 | 2026-07-10 | 2026-07-14 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0048 | 0 | RFI-REH-AR01-OC-MOD-EL-0048-00 - REH International Airport Project - Clarification of Power Cable Construction Requirements | EL | NACO | NACO responded | 2026-07-06 | 2026-07-09 |  | 2026-07-07 | 2026-07-08 | 2026-07-09 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0049 | 0 | RFI-REH-AR01-OC-MOD-EL-0049-00 - REH International Airport Project - Missing Main Intake Substation Updated Drawings | EL | NACO | NACO responded | 2026-07-08 | 2026-07-11 | 2026-07-14 | 2026-07-12 | 2026-07-13 | 2026-07-14 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0050 | 0 | RFI-REH-AR01-OC-MOD-EL-0050-00 - REH International Airport Project - Chiller Planet MCC (Sec. Pumps) | EL | NACO | NACO responded | 2026-07-10 | 2026-07-13 | 2026-07-13 | 2026-07-12 | 2026-07-13 | 2026-07-13 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0051 | 0 | RFI-REH-AR01-OC-MOD-EL-0051-00 - REH International Airport Project - Fire Pump Connection in PUMP STATION | EL | Hill | Hill Responded | 2026-07-10 | 2026-07-13 | 2026-07-12 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0051 | 1 | REH International Airport Project - Fire Pump Connection in PUMP STATION | EL | NACO | NACO responded | 2026-07-13 | 2026-07-16 |  | 2026-07-13 | 2026-07-14 | 2026-07-29 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0051 | 2 | RFI-REH-AR01-OC-MOD-EL-0051-02 - REH International Airport Project - Fire Pump Connection in PUMP STATION | EL | Hill | Hill Responded | 2026-08-03 | 2026-08-06 | 2026-08-05 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0052 | 0 | REH International Airport Project - Clarification Required for AGL Panels Supply at Substations 1 & 2 | EL | Hill | Hill Responded | 2026-07-13 | 2026-07-16 | [5 empty] | Closed
RFI-REH-AR01-OC-MOD-EL-0053 | 0 | REH International Airport Project - CCR ROOM & ICT ROOM ACCESS CONTROL SYSTEM | EL | Hill | Hill Responded | 2026-08-10 | 2026-08-13 | 2026-09-10 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0054 | 0 | RFI-REH-AR01-OC-MOD-EL-0054-00 - REH International Airport Project - PENSTOCK & Spindle Valve Electrical Requirements | EL | NACO | NACO responded | 2026-08-12 | 2026-08-15 |  | 2026-08-13 | 2026-08-14 | 2026-08-17 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0055 | 0 | Landscape & Facade Lighting Scope Clarification – VVIP TERMINAL | EL | NACO | NACO responded | 2026-08-22 | 2026-08-25 |  | 2026-08-23 | 2026-08-24 | 2026-08-24 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0055 | 1 | Landscape & Facade Lighting Scope Clarification - VVIP TERMINAL | EL | NACO | NACO responded | 2026-09-08 | 2026-09-11 |  | 2026-09-08 | 2026-09-09 | 2026-09-15 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0056 | 0 | PRELIMINARY CONCEPT FOR LANDSCAPE LIGHTING SHOPDRAWING | EL | Hill | Hill Responded | 2026-08-31 | 2026-09-03 | 2026-09-01 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0057 | 0 | Clarification Required MEF ACCESS CONTROL SYSTEM | EL | NACO | NACO responded | 2026-09-01 | 2026-09-04 |  | 2026-09-02 | 2026-09-03 | 2026-09-09 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0058 | 0 | Discrepancies in lighting Design between Electrical and architectural design drawings | EL | NACO | NACO responded | 2026-09-03 | 2026-09-06 |  | 2026-09-08 | 2026-09-09 | 2026-09-15 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0058 | 1 | Discrepancies in lighting Design between Electrical and architectural design drawings | EL | NACO | NACO responded | 2026-09-21 | 2026-09-24 |  | 2026-09-22 | 2026-09-23 | 2026-09-25 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0059 | 0 | Clarification on Air Terminals Arrangement – Gate 1 & Gate 2 Lightning System | EL | NACO | NACO responded | 2026-09-05 | 2026-09-08 |  | 2026-09-08 | 2026-09-09 | 2026-09-10 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0060 | 0 | Clarification about Lift Stations Interface with BMS | EL | NACO | NACO responded | 2026-09-08 | 2026-09-11 |  | 2026-09-08 | 2026-09-09 | 2026-09-11 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0061 | 0 | Clarification About Master Clock System -VVIP Building | EL | Hill | Hill Responded | 2026-09-08 | 2026-09-11 | 2026-09-08 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0062 | 0 | Clarification about Fire Alarm, Gas Supersession and BMS | EL | NACO | NACO responded | 2026-09-15 | 2026-09-18 |  | 2026-09-15 | 2026-09-16 | 2026-09-18 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0063 | 0 | Modification of Street Lighting Poles Due to Road Layout Modification | EL | NACO | NACO responded | 2026-09-17 | 2026-09-20 |  | 2026-09-17 | 2026-09-18 | 2026-09-22 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0064 | 0 | Clarification on PE Cable Insulation | EL | NACO | NACO responded | 2026-09-17 | 2026-09-20 |  | 2026-09-17 | 2026-09-18 | 2026-09-28 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0065 | 0 | Conflict between Approved Manufacturing shop drawings and BEDC Approval | EL | Hill | Hill Responded | 2026-09-19 | 2026-09-22 | 2026-09-20 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0066 | 0 | Clarification on Electrical SLD - ATS Panels | EL | NACO | NACO responded | 2026-09-22 | 2026-09-25 |  | 2026-09-22 | 2026-09-23 | 2026-09-29 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0067 | 0 | BMS Network Connection to LS1 | EL | Hill | Hill Responded | 2026-09-22 | 2026-09-25 | 2026-09-24 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0068 | 0 | Electrical Room Issues at Gatehouse VVIP Person (GH3) | EL | NACO | NACO responded | 2026-09-22 | 2026-09-25 |  | 2026-09-24 | 2026-09-25 | 2026-10-02 |  | Closed
RFI-REH-AR01-OC-MOD-EL-0069 | 0 | Clarification about fire alarm above-ceiling detectors | EL | Hill | Hill Responded | 2026-09-27 | 2026-09-30 | 2026-09-28 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-EL-0069 | 1 | Clarification about fire alarm above-ceiling detectors | EL | NACO | Waiting NACO responded | 2026-09-30 | 2026-10-03 |  | 2026-10-01 | 2026-10-02 |  |  | Open
RFI-REH-AR01-OC-MOD-EL-0070 | 0 | Electrical Supply for Kitchen, Laundry and Pantry Loads | EL | NACO | Waiting NACO responded | 2026-09-30 | 2026-10-03 |  | 2026-10-01 | 2026-10-02 |  |  | Open
RFI-REH-AR01-OC-MOD-EL-0071 | 0 | Clarification of FCP Locations and usage at ARFF | EL | NACO | NACO responded | 2026-10-05 | 2026-10-08 |  | 2026-10-05 | 2026-10-06 | 2026-10-07 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0001 | 0 | P0153-K00146-REH International Airport Project - Basement Floor Fire Hydrant | ME |  | Closed / no action | 2025-10-19 | 2025-10-22 | 2025-10-28 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0002 | 0 | P0153-K00146-REH International Airport Project - Replacement of Fire Fighting Pipes | ME |  | Closed / no action | 2025-10-20 | 2025-10-23 | 2025-11-06 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0003 | 0 | P0153-K00146-REH International Airport Project - Replacement of Drainage Pipes Sizes | ME |  | Closed / no action | 2025-10-20 | 2025-10-23 | 2025-11-04 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0004 | 0 | P0153-K00146-REH International Airport Project - 20% FCU units Increased capacity | ME |  | Closed / no action | 2025-12-28 | 2025-12-31 | 2026-01-03 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0005 | 0 | P0153-K00146-REH International Airport Project - Hydraulic re-calculation of primary chilled water pumps | ME |  | Closed / no action | 2026-01-28 | 2026-01-31 | 2026-02-06 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0006 | 0 | P0153-K00146-REH International Airport Project - changing storm connection pipe material | ME |  | Closed / no action | 2026-02-01 | 2026-02-04 | 2026-02-03 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0007 | 0 | P0153-K00146-REH International Airport Project - Conflict in BoQ quantities | ME |  | Closed / no action | 2026-02-04 | 2026-02-07 | 2026-02-10 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0008 | 0 | P0153-K00146-REH International Airport Project - Cavity for drainage pipe | ME |  | Closed / no action | 2026-02-07 | 2026-02-10 | 2026-02-25 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0009 | 0 | P0153-K00146-REH International Airport Project - Adding 150mm cavity wall | ME |  | Closed / no action | 2026-02-09 | 2026-02-12 | 2026-02-25 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0010 | 0 | P0153-K00146-REH International Airport Project - Adding 150mm cavity wall | ME |  | Closed / no action | 2026-02-09 | 2026-02-12 | 2026-02-26 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0011 | 0 | REH International Airport Project - Storm Drainage Clashing with Basement Walls | ME |  | Closed / no action | 2026-02-10 | 2026-02-13 | 2026-03-01 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0012 | 00 | REH International Airport Project - Hydraulic calculations for Chilled hot water Secondary and primary pumps – HVAC. | ME |  | Closed / no action | 2026-02-17 | 2026-02-20 | 2026-02-26 |  |  |  | 00 | Closed
RFI-REH-AR01-OC-MOD-ME-0013 | 00 | RFI-REH-AR01-OC-MOD-ME-0013-00 - REH International Airport Project – Airside Storm Ditch Conflict | ME |  | Closed / no action | 2026-04-08 | 2026-04-11 | 2026-04-26 |  |  |  | 00 | Closed
RFI-REH-AR01-OC-MOD-ME-0014 | 0 | RFI-REH-AR01-OC-MOD-ME-0014-00 - REH International Airport Project – Ambient Air Temperatures | ME |  | Closed / no action | 2026-04-09 | 2026-04-12 | 2026-04-12 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0015 | 00 | RFI-REH-AR01-OC-MOD-ME-0015-00 - REH International Airport Project – Fire Pump | ME |  | Closed / no action | 2026-04-09 | 2026-04-12 | 22-4-2026 |  |  |  | 00 | Closed
RFI-REH-AR01-OC-MOD-ME-0016 | 00 | REH International Airport Project - VVIP – Additional lavatories drainage pipes at basement | ME |  | Closed / no action | 2026-04-18 | 2026-04-21 | 2026-05-05 |  |  |  | 00 | Closed
RFI-REH-AR01-OC-MOD-ME-0017 | 00 | REH International Airport Project – proposal of some unconnected storm pipes- VVIP building | ME | NACO | NACO responded | 2026-04-18 | 2026-04-21 | 2026-06-03 |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0018 | 00 | REH International Airport Project – VVIP Terminal – Buffer Tank at Ground Floor | ME |  | Closed / no action | 2026-04-20 | 2026-04-23 | 2026-04-30 |  |  |  | 00 | Closed | HillInt-RTRFI-000330
RFI-REH-AR01-OC-MOD-ME-0019 | 00 | REH International Airport Project – ESP- VVIP building | ME | NACO | NACO responded | 2026-04-20 | 2026-04-23 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0020 | 00 | REH International Airport Project – ESP- Chiller plant | ME | NACO | NACO responded | 2026-04-20 | 2026-04-23 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0021 | 00 | REH International Airport Project – ESP- Main Entry Facility | ME | NACO | NACO responded | 2026-04-20 | 2026-04-23 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0022 | 00 | REH International Airport Project – ESP- Pump station | ME | NACO | NACO responded | 2026-04-20 | 2026-04-23 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0023 | 00 | REH International Airport Project – ESP- Main Intake Substation Fans, AHUs and RTU units | ME | NACO | NACO responded | 2026-04-20 | 2026-04-23 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0024 | 00 | REH International Airport Project – ESP- ARFFS Building for CRAC, Fans and DOAS Units | ME | NACO | NACO responded | 2026-04-20 | 2026-04-23 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0025 | 00 | REH International Airport Project – STORM WATER DRAINAGE PIPE NETWORK MATERIAL REPLACEMENT (using pipe HDPE PN10 instead of PN16) | ME |  | Closed / no action | 2026-04-22 | 2026-04-25 | 2026-04-30 |  |  |  | 00 | Closed | HillInt-RTRFI-000329
RFI-REH-AR01-OC-MOD-ME-0026 | 00 | REH International Airport Project - VVIP - Emergency Siphonic System Issue | ME |  | Closed / no action | 2026-04-26 | 2026-04-29 | 2026-05-04 |  |  |  | 00 | Closed | HillInt-RTRFI-000341
RFI-REH-AR01-OC-MOD-ME-0027 | 00 | REH International Airport Project - Lift station data and storm water Ti-in issues | ME | NACO | NACO responded | 2026-04-30 | 2026-05-03 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0028 | 00 | REH International Airport Project - SEWAGE NETWORK STILLING BASIN | ME | NACO | Review and assign next action | 2026-04-30 | 2026-05-03 |  |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0029 | 0 | REH International Airport Project - Mechanical clarification and issues inside Pump Station building | ME | NACO | Closed / no action | 2026-04-30 | 2026-05-03 |  | 2026-06-04 | 2026-06-05 | 2026-07-07 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0030 | 00 | REH International Airport Project - Hydraulic calculations of Distribution chilled Cold and hot water pumps | ME |  | Review and assign next action | 2026-05-06 | 2026-05-09 | 2026-05-24 |  |  |  | 00 | Closed |  | To be categorized and assigned
RFI-REH-AR01-OC-MOD-ME-0030 | 01 | RFI-REH-AR01-OC-MOD-ME-0030-01 - REH International Airport Project - Updated Hydraulic calculations for distribution chilled cold and hot water pumps | ME | NACO | NACO responded | 2026-07-07 | 2026-07-10 |  | 2026-07-09 | 2026-07-10 | 2026-09-07 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0031 | 00 | REH International Airport Project - VVIP AC AIR TERMINAL CLASHES ISSUE - ROOMS G1.18 & G1.25 | ME |  | NACO responded | 2026-05-07 | 2026-05-10 | 2026-06-01 |  |  |  | 00 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-ME-0032 | 0 | RFI-REH-AR01-OC-MOD-ME-0032-00 - REH International Airport Project - VVIP Storm network connection with the infra network | ME | NACO | NACO responded | 2026-05-14 | 2026-05-17 |  |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-ME-0033 | 0 | RFI-REH-AR01-OC-MOD-ME-0033-00 - REH International Airport Project - Airside Storm Network Queries | ME | NACO | NACO responded | 2026-05-23 | 2026-05-26 | 2026-06-03 |  |  |  | HillInt-RTRFI-000494 | Closed
RFI-REH-AR01-OC-MOD-ME-0034 | 0 | RFI-REH-AR01-OC-MOD-ME-0034-00 - REH International Airport Project - Connection between Gutter and Manhole | ME | Hill | send to naco | 2026-05-24 | 2026-05-27 | [5 empty] | Closed
RFI-REH-AR01-OC-MOD-ME-0035 | 0 | RFI-REH-AR01-OC-MOD-ME-0035-00 - REH International Airport Project - Changing storm drainage connection pipe material | ME | NACO | NACO responded | 2026-05-24 | 2026-05-27 | 2026-06-11 |  |  |  |  | Closed | HillInt-RTRFI-000531
RFI-REH-AR01-OC-MOD-ME-0036 | 0 | RFI-REH-AR01-OC-MOD-ME-0036-00 - REH International Airport Project - Replacement of Stainless Steel Pipes with Galvanized Steel Pipes | ME | NACO | NACO responded | 2026-06-09 | 2026-06-12 | [5 empty] | Closed | HillInt-RTRFI-000540
RFI-REH-AR01-OC-MOD-ME-0037 | 0 | RFI-REH-AR01-OC-MOD-ME-0037-00 - REH International Airport Project - Hydraulic calculation of secondary chilled cold-water pumps | ME | NACO | NACO responded | 2026-06-17 | 2026-06-20 |  | 2026-06-22 | 2026-06-23 | 2026-06-26 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0038 | 0 | RFI-REH-AR01-OC-MOD-ME-0038-00 - REH International Airport Project - Clarification on BMS Requirement for Sitewide Reservoir and Pump Station | ME | NACO | NACO responded | 2026-06-23 | 2026-06-26 |  | 2026-06-29 | 2026-06-30 | 2026-07-01 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0039 | 0 | RFI-REH-AR01-OC-MOD-ME-0039-00 - REH International Airport Project - Inquiring About Wingwalls Function | ME | NACO | NACO responded | 2026-06-30 | 2026-07-03 |  | 2026-07-09 | 2026-07-10 | 2026-07-09 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0040 | 0 | Stormwater Drainage Discharge for SUB-01 & SUB-02 | ME | Hill | Hill Responded | 2026-08-01 | 2026-08-04 | 2026-08-05 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-ME-0041 | 0 | Inquiring about manholes cover and step ladder | ME | Hill | Hill Responded | 2026-08-20 | 2026-08-23 | 2026-08-25 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-ME-0041 | 1 | Inquiring about manholes cover and step ladder | ME | Hill | Hill Responded | 2026-09-06 | 2026-09-09 | 2026-09-07 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-ME-0042 | 0 | updated External Static Pressure Calculations for CRAC Units in VVIP Building | ME | NACO | NACO responded | 2026-08-23 | 2026-08-26 | 2026-08-26 | 2026-08-24 | 2026-08-25 |  |  | Closed
RFI-REH-AR01-OC-MOD-ME-0043 | 0 | contradictions between the sand trap louvers in Arch.Drawings and the Mechanical drawings | ME | NACO | NACO responded | 2026-09-07 | 2026-09-10 |  | 2026-09-15 | 2026-09-16 | 2026-09-15 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0044 | 0 | Main Intake Substation, the louvers schedules aremissing in Mechanical design drawings. | ME | NACO | NACO responded | 2026-09-07 | 2026-09-10 |  | 2026-09-08 | 2026-09-09 | 2026-09-11 |  | Closed
RFI-REH-AR01-OC-MOD-ME-0045 | 0 | Mismatch between the capacities of the indoor and outdoor DX units in Main Intake Substation & Main entry facility and Chiller plant buildings | ME | Hill | Hill Responded | 2026-09-08 | 2026-09-11 | 2026-09-15 |  |  |  | HillInt-GNC-003713 | Closed
RFI-REH-AR01-OC-MOD-ME-0046 | 0 | Split air conditioner units at all buildings | ME | Hill | Hill Responded | 2026-09-15 | 2026-09-18 | 2026-09-16 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-ME-0047 | 0 | Automatic fire protection system Missing in the generator rooms at Main Intake Substation, Substation 01 and Substation 02 buildings | ME | Hill | Hill Responded | 2026-09-16 | 2026-09-19 | 2026-09-28 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-ME-0048 | 0 | Scour Valve Drainage | ME | Hill | Hill Responded | 2026-09-21 | 2026-09-24 | 2026-09-28 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-CI-0001 | 0 | Gypsum Content in the Proposed fill material | Structural |  | Closed / no action | 2025-06-30 | 2025-07-03 | 2025-07-21 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0001 | 1 | P0153-K00146-REH International Airport Project - Gypsum Content in the Proposed fill material | Structural |  | Closed / no action | 2025-07-22 | 2025-07-25 | 2025-07-23 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-CI-0002 | 0 | P0153-K00146-REH International Airport Project - Asphalt Surface Preliminary Material Acceptance | Structural |  | Cancelled | 2025-08-07 | 2025-08-10 | 2025-09-21 |  |  |  | 0 | Cancelled
RFI-REH-AR01-OC-MOD-CI-0003 | 0 | P0153-K00146-REH International Airport Project – Local Bituminous Base Material Test Results | Structural |  | Closed / no action | 2025-09-13 | 2025-09-16 | 2025-09-22 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0004 | 0 | P0153-K00146-REH International Airport Project – Substitution of Waterproofing Material | Structural |  | Closed / no action | 2025-09-16 | 2025-09-19 | 2025-09-17 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0005 | 0 | P0153-K00146-REH International Airport Project – Proposal to Unify PMA Performance Grade for Asphalt Base and Surface Courses | Structural |  | Closed / no action | 2025-09-20 | 2025-09-23 | 2025-09-25 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0006 | 0 | P0153-K00146-REH International Airport Project – Precast Concrete Pipes for Future Utilities Runway Crossings | Structural |  | Closed / no action | 2025-10-07 | 2025-10-10 | 2025-11-05 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0007 | 0 | P0153-K00146-REH International Airport Project – Civil Works– AGL Duct Banks | Structural |  | Closed / no action | 2025-10-13 | 2025-10-16 | 2025-11-13 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0008 | 0 | P0153-K00146-REH International Airport Project – Cable Conduit Installation within Concrete Pavement for 8” AGL Fixtures | Structural |  | Closed / no action | 2025-10-15 | 2025-10-18 | 2025-11-05 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0009 | 0 | P0153-K00146-REH International Airport Project – Backstay at Chain Link fencing | Structural |  | Closed / no action | 2025-10-15 | 2025-10-18 | 2025-11-05 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0010 | 0 | P0153-K00146-REH International Airport Project – Excavation and Fill for Buildings Specification test frequencies | Structural |  | Closed / no action | 2025-10-20 | 2025-10-23 | 2025-11-10 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0011 | 0 | P0153-K00146-REH International Airport Project – Airside Substation Buildings floor finish level | Structural |  | Closed / no action | 2025-10-21 | 2025-10-24 | 2025-11-06 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0012 | 0 | P0153-K00146-REH International Airport Project – Proposal of Waterproofing Material | Structural |  | Closed / no action | 2025-11-01 | 2025-11-04 | 2025-11-13 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0013 | 0 | P0153-K00146-REH International Airport Project – Airside/Landside Gatehouse01&02 profile substitution | Structural |  | Closed / no action | 2025-11-13 | 2025-11-16 | 2025-12-06 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0013 | 1 | P0153-K00146-REH International Airport Project – Airside/Landside Gatehouse01&02 profile substitution | Structural |  | Closed / no action | 2025-12-14 | 2025-12-17 | 2026-01-20 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-CI-0014 | 0 | P0153-K00146-REH International Airport Project – Gatehouses and ARFF painting system | Structural |  | Closed / no action | 2025-11-26 | 2025-11-29 | 2025-12-17 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0014 | 1 | P0153-K00146-REH International Airport Project – RAL NO. FOR STEEL STRUCTURES | Structural |  | Closed / no action | 2025-12-22 | 2025-12-25 | 2025-12-30 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-CI-0015 | 0 | P0153-K00146-REH International Airport Project – Gatehouse - PIPE 139.7 X 5mm profile substitution | Structural |  | Closed / no action | 2025-11-30 | 2025-12-03 | 2025-12-03 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0016 | 0 | P0153-K00146-REH International Airport Project – GATHOUSE - VVIP STAFF AND GOODS (G4) profile substitution | Structural |  | Closed / no action | 2025-12-15 | 2025-12-18 | 2026-01-15 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0017 | 0 | P0153-K00146-REH International Airport Project – Confining Walls for Backfilling | Structural |  | Closed / no action | 2025-12-15 | 2025-12-18 | 2026-01-27 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0018 | 0 | P0153-K00146-REH International Airport Project – FS1 Slab Water Proofing | Structural |  | Closed / no action | 2025-12-28 | 2025-12-31 | 2026-01-20 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0019 | 0 | P0153-K00146-REH International Airport Project – Missing RFT details for concrete beam | Structural |  | Closed / no action | 2025-12-28 | 2025-12-31 | 2026-01-26 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0020 | 0 | P0153-K00146-REH International Airport Project – Alternative Proposals for Ground Floor Suspended Slab | Structural |  | Closed / no action | 2025-12-30 | 2026-01-02 | 2025-12-30 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0020 | 1 | P0153-K00146-REH International Airport Project – Alternative Proposals for Ground Floor Suspended Slab | Structural |  | Closed / no action | 2025-12-31 | 2026-01-03 | 2026-01-27 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-CI-0021 | 0 | P0153-K00146-REH International Airport Project – Alternative Proposals for Apron Storm Drainage | Structural |  | Closed / no action | 2026-01-05 | 2026-01-08 | 2026-01-15 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0022 | 0 | P0153-K00146-REH International Airport Project – Missing Vertical Stirrups in Corbel Reinforcement | Structural |  | Closed / no action | 2026-01-06 | 2026-01-09 | 2026-01-22 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0023 | 0 | P0153-K00146-REH International Airport Project – VVIP-terminal Steel Structure Fire Protection Requirements | Structural |  | Closed / no action | 2026-01-19 | 2026-01-22 | 2026-01-27 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0023 | 1 | REH International Airport Project – Fireproofing Clarification (Gatehouses & ARFF) | Structural |  | Closed / no action | 2026-02-17 | 2026-02-20 | 2026-03-07 |  |  |  | 1 | Closed
RFI-REH-AR01-OC-MOD-CI-0024 | 0 | P0153-K00146-REH International Airport Project – Query to extend the Raft underneath the cable trench and proposal for isolate the Ground slab from the Cable trench | Structural |  | Closed / no action | 2026-01-20 | 2026-01-23 | 2026-01-26 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0025 | 0 | P0153-K00146-REH International Airport Project – Ablution Area Grating Drop Not Reflected in Structural DWG | Structural |  | Closed / no action | 2026-01-21 | 2026-01-24 | 2026-01-29 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0026 | 0 | P0153-K00146-REH International Airport Project – Landside Bill of Quantities comments | Structural |  | Closed / no action | 2026-01-21 | 2026-01-24 | 2026-01-27 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0027 | 0 | P0153-K00146-REH International Airport Project – finishes for roof support | Structural |  | Closed / no action | 2026-01-29 | 2026-02-01 | 2026-02-05 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0028 | 0 | P0153-K00146-REH International Airport Project – VVIP TERMINAL GATEHOUSE - VVIP PERSON (G3) anchors shifting | Structural |  | Closed / no action | 2026-01-29 | 2026-02-01 | 2026-01-29 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0029 | 0 | P0153-K00146-REH International Airport Project – Missing Details of Apron Storm Drainage | Structural |  | Closed / no action | 2026-02-03 | 2026-02-06 | 2026-02-06 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0030 | 0 | P0153-K00146-REH International Airport Project – Pavement Marking Draft Specifications Comments | Structural |  | Closed / no action | 2026-02-07 | 2026-02-10 | 2026-02-25 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0031 | 0 | REH International Airport Project – Main Intake Substation – Multiple Queries | Structural |  | Closed / no action | 2026-03-02 | 2026-03-05 | 2026-03-18 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0032 | 0 | REH International Airport Project – Site Drainage Works – Conflicts in Details | Structural |  | Closed / no action | 2026-03-11 | 2026-03-14 | 2026-03-17 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0033 | 0 | REH International Airport Project – Climate Conditions in Joint Sealant Specifications | Structural |  | Closed / no action | 2026-03-15 | 2026-03-18 | 2026-03-17 |  |  |  | 0 | Closed
RFI-REH-AR01-OC-MOD-CI-0034 | 00 | RFI-REH-AR01-OC-MOD-CI-0034-00 - REH International Airport Project – Chiller Plant - Staircase Structural Clarifications | Structural |  | Closed / no action | 2026-05-04 | 2026-05-07 | 26-4-2026 |  |  |  | 00 | Closed
RFI-REH-AR01-OC-MOD-CI-0035 | 00 | RFI-REH-AR01-OC-MOD-CI-0035-00 - REH International Airport Project – Storm Concrete Ditch Missing Information | Structural |  | Closed / no action | 2026-05-04 | 2026-05-07 | 26-4-2026 |  |  |  | 00 | Closed
RFI-REH-AR01-OC-MOD-CI-0036 | 00 | REH International Airport Project - gatehouse 03&04- proposed connection for G03&G04 NACO update | Structural |  | Closed / no action | 2026-04-18 | 2026-04-21 | 2026-04-20 |  |  |  | 00 | Closed | HillInt-RTRFI-000209
RFI-REH-AR01-OC-MOD-CI-0037 | 00 | REH International Airport Project – Missing Details for Wing Walls | Structural |  | Closed / no action | 2026-04-18 | 2026-04-21 | 26-4-2026 |  |  |  | 00 | Closed | HillInt-RTRFI-000272
RFI-REH-AR01-OC-MOD-CI-0038 | 00 | REH International Airport Project – AGL at Runway Over-Run Parts | Structural |  | Closed / no action | 2026-04-19 | 2026-04-22 | 2026-04-29 |  |  |  | 00 | Closed | HillInt-RTRFI-000315
RFI-REH-AR01-OC-MOD-CI-0039 | 00 | REH International Airport Project – Discrepancy in Wing Wall Details | Structural |  | Closed / no action | 2026-04-21 | 2026-04-24 | 2026-05-05 |  |  |  | 00 | Closed | HillInt-RTRFI-000345
RFI-REH-AR01-OC-MOD-CI-0040 | 00 | REH International Airport Project – Perimeter Wall Fence | Structural |  | Closed / no action | 2026-04-21 | 2026-04-24 | 2026-05-04 |  |  |  | 00 | Closed | HillInt-RTRFI-000340
RFI-REH-AR01-OC-MOD-CI-0040-01 | 1 | REH International Airport Project – Perimeter Wall Fence | Structural |  | NACO responded | 2026-05-06 | 2026-05-09 |  |  |  |  | 1 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-CI-0041 | 0 | REH International Airport Project – VVIP Terminal Building Expansion Joint Location | Structural |  | Review and assign next action | 2026-05-01 | 2026-05-04 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-CI-0042 | 0 | REH International Airport Project – Material Specifications Clarification | Structural |  | NACO responded | 2026-05-02 | 2026-05-05 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-CI-0043 | 0 | RFI-REH-AR01-OC-MOD-CI-0043-00 - REH International Airport Project – Queries regarding Civil Works for Site Utilities | Structural | Hill | Hill Responded | 2026-05-14 | 2026-05-17 | 2026-05-20 |  |  |  | 0 | Closed | HillInt-RTRFI-000437
RFI-REH-AR01-OC-MOD-CI-0044 | 0 | RFI-REH-AR01-OC-MOD-CI-0044-00 - REH International Airport Project – Missing Stair in STR Drawing | Structural |  | NACO responded | 2026-05-18 | 2026-05-21 |  |  |  |  | 0 | Closed |  | Waiting Hill responded
RFI-REH-AR01-OC-MOD-CI-0045 | 0 | RFI-REH-AR01-OC-MOD-CI-0045-00 - REH International Airport Project – Site modifications | Structural | Hill | Hill Responded | 2026-05-21 | 2026-05-24 | 2026-05-24 |  |  |  | 0 | Closed | HillInt-RTRFI-000451
RFI-REH-AR01-OC-MOD-CI-0046 | 0 | RFI-REH-AR01-OC-MOD-CI-0046-00 - REH International Airport Project – Clarification Required for Wing Wall for Ditches Airside | Structural | Hill | Hill Responded | 2026-08-12 | 2026-08-15 | 2026-08-14 |  |  |  |  | Closed
RFI-REH-AR01-OC-MOD-CI-0047 | 0 | Missing Reinforcement Details for Various Elements | Structural | NACO | NACO responded | 2026-08-19 | 2026-08-22 |  | 2026-08-24 | 2026-08-25 | 2026-09-01 |  | Closed
RFI-REH-AR01-OC-MOD-CI-0048 | 0 | Clash Between VVIP Wing Wall 01 Foundation and Landscape Retaining Wall | Structural | NACO | NACO responded | 2026-08-19 | 2026-08-22 |  | 2026-08-25 | 2026-08-26 | 2026-09-01 |  | Closed
RFI-REH-AR01-OC-MOD-CI-0049 | 0 | RFI-REH-AR01-OC-MOD-CI-0049-00 - REH International Airport Project – Replacing Reinforcement Diameter for Various Elements | Structural | Hill | Hill Responded | 2026-08-19 | 2026-08-22 | 2026-08-23 | 2026-08-23 |  |  |  | Closed
RFI-REH-AR01-OC-MOD-CI-0050 | 0 | Storm Water Drainage Outfall Structure Detail for (CD-MH-312, CD-MH-313 & CD-MH-353) | Structural | Hill | Waiting HILL responded | 2026-10-08 | 2026-10-11 | 2026-10-11 |  |  |  |  | Closed
Formulas:
Due Date = RFIActionRegister[[#This Row],[Creation Date]]+3
NACO Due Date = IF(RFIActionRegister[[#This Row],[Date Sent to NACO]]="","",RFIActionRegister[[#This Row],[Date Sent to NACO]]+1)
Date reply = RFIActionRegister[[#This Row],[Creation Date]]+3
Date reply = RFIActionRegister[[#This Row],[Due Date]]+3
NACO Date Reply = IF(RFIActionRegister[[#This Row],[Date Sent to NACO]]="","",RFIActionRegister[[#This Row],[Date Sent to NACO]]+1)

## Original Source
Request For Information Log Airport Project | [11 empty] | Response | 110
[12 empty] | Open | 22
[7 empty] | HILL To NACO |  | Hill to OC |  | Response by | All | 132
Mail No | RFI No | Rev. | Subject | Received Date | Discipline | Priority | Mail No | Issue Date | Mail No | Issue Date |  | Statuse
CCCEGY-RFI-000001 | RFI-REH-AR01-OC-MOD-CI-0001 | 0 | P0153-K00146-REH International Airport Project - Gypsum Content in the Proposed fill material | 45838 | Structural |  |  |  |  | 45859 |  | Response
CCCEGY-RFI-000002 | RFI-REH-AR01-OC-MOD-CI-0001 | 1 | P0153-K00146-REH International Airport Project - Gypsum Content in the Proposed fill material | 45860 | Structural |  |  |  |  | 45861 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0002 | 0 | P0153-K00146-REH International Airport Project - Asphalt Surface Preliminary Material Acceptance | 45876 | Structural |  |  |  |  | 45921 |  | Cancelled
| RFI-REH-AR01-OC-MOD-CI-0003 | 0 | P0153-K00146-REH International Airport Project – Local Bituminous Base Material Test Results | 45913 | Structural |  |  |  |  | 45922 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0004 | 0 | P0153-K00146-REH International Airport Project – Substitution of Waterproofing Material | 45916 | Structural |  |  |  |  | 45917 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0005 | 0 | P0153-K00146-REH International Airport Project – Proposal to Unify PMA Performance Grade for Asphalt Base and Surface Courses | 45920 | Structural |  |  |  |  | 45925 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0006 | 0 | P0153-K00146-REH International Airport Project – Precast Concrete Pipes for Future Utilities Runway Crossings | 45937 | Structural |  |  |  |  | 45966 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0007 | 0 | P0153-K00146-REH International Airport Project – Civil Works– AGL Duct Banks | 45943 | Structural |  |  |  |  | 45974 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0008 | 0 | P0153-K00146-REH International Airport Project – Cable Conduit Installation within Concrete Pavement for 8” AGL Fixtures | 45945 | Structural |  |  |  |  | 45966 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0009 | 0 | P0153-K00146-REH International Airport Project – Backstay at Chain Link fencing | 45945 | Structural |  |  |  |  | 45966 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0010 | 0 | P0153-K00146-REH International Airport Project – Excavation and Fill for Buildings Specification test frequencies | 45950 | Structural |  |  |  |  | 45971 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0011 | 0 | P0153-K00146-REH International Airport Project – Airside Substation Buildings floor finish level | 45951 | Structural |  |  |  |  | 45967 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0012 | 0 | P0153-K00146-REH International Airport Project – Proposal of Waterproofing Material | 45962 | Structural |  |  |  |  | 45974 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0013 | 0 | P0153-K00146-REH International Airport Project – Airside/Landside Gatehouse01&02 profile substitution | 45974 | Structural |  |  |  |  | 45997 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0013 | 1 | P0153-K00146-REH International Airport Project – Airside/Landside Gatehouse01&02 profile substitution | 46005 | Structural |  |  |  |  | 46042 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0014 | 0 | P0153-K00146-REH International Airport Project – Gatehouses and ARFF painting system | 45987 | Structural |  |  |  |  | 46008 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0014 | 1 | P0153-K00146-REH International Airport Project – RAL NO. FOR STEEL STRUCTURES | 46013 | Structural |  |  |  |  | 46021 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0015 | 0 | P0153-K00146-REH International Airport Project – Gatehouse - PIPE 139.7 X 5mm profile substitution | 45991 | Structural |  |  |  |  | 45994 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0016 | 0 | P0153-K00146-REH International Airport Project – GATHOUSE - VVIP STAFF AND GOODS (G4) profile substitution | 46006 | Structural |  |  |  |  | 46037 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0017 | 0 | P0153-K00146-REH International Airport Project – Confining Walls for Backfilling | 46006 | Structural |  |  |  |  | 46049 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0018 | 0 | P0153-K00146-REH International Airport Project – FS1 Slab Water Proofing | 46019 | Structural |  |  |  |  | 46042 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0019 | 0 | P0153-K00146-REH International Airport Project – Missing RFT details for concrete beam | 46019 | Structural |  |  |  |  | 46048 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0020 | 0 | P0153-K00146-REH International Airport Project – Alternative Proposals for Ground Floor Suspended Slab | 46021 | Structural |  |  |  |  | 46021 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0020 | 1 | P0153-K00146-REH International Airport Project – Alternative Proposals for Ground Floor Suspended Slab | 46022 | Structural |  |  |  |  | 46049 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0021 | 0 | P0153-K00146-REH International Airport Project – Alternative Proposals for Apron Storm Drainage | 46027 | Structural |  |  |  |  | 46037 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0022 | 0 | P0153-K00146-REH International Airport Project – Missing Vertical Stirrups in Corbel Reinforcement | 46028 | Structural |  |  |  |  | 46044 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0023 | 0 | P0153-K00146-REH International Airport Project – VVIP-terminal Steel Structure Fire Protection Requirements | 46041 | Structural |  |  |  |  | 46049 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0023 | 1 | REH International Airport Project – Fireproofing Clarification (Gatehouses & ARFF) | 46070 | Structural |  |  |  |  | 46088 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0024 | 0 | P0153-K00146-REH International Airport Project – Query to extend the Raft underneath the cable trench and proposal for isolate the Ground slab from the Cable trench | 46042 | Structural |  |  |  |  | 46048 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0025 | 0 | P0153-K00146-REH International Airport Project – Ablution Area Grating Drop Not Reflected in Structural DWG | 46043 | Structural |  |  |  |  | 46051 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0026 | 0 | P0153-K00146-REH International Airport Project – Landside Bill of Quantities comments | 46043 | Structural |  |  |  |  | 46049 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0027 | 0 | P0153-K00146-REH International Airport Project – finishes for roof support | 46051 | Structural |  |  |  |  | 46058 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0028 | 0 | P0153-K00146-REH International Airport Project – VVIP TERMINAL GATEHOUSE - VVIP PERSON (G3) anchors shifting | 46051 | Structural |  |  |  |  | 46051 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0029 | 0 | P0153-K00146-REH International Airport Project – Missing Details of Apron Storm Drainage | 46056 | Structural |  |  |  |  | 46059 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0030 | 0 | P0153-K00146-REH International Airport Project – Pavement Marking Draft Specifications Comments | 46060 | Structural |  |  |  |  | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0031 | 0 | REH International Airport Project – Main Intake Substation – Multiple Queries | 46083 | Structural |  |  |  |  | 46099 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0032 | 0 | REH International Airport Project – Site Drainage Works – Conflicts in Details | 46092 | Structural |  |  |  |  | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0033 | 0 | REH International Airport Project – Climate Conditions in Joint Sealant Specifications | 46096 | Structural |  |  |  |  | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0034 | 00 | RFI-REH-AR01-OC-MOD-CI-0034-00 - REH International Airport Project – Chiller Plant - Staircase Structural Clarifications | 46146 | Structural |  |  |  |  | 26-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0035 | 00 | RFI-REH-AR01-OC-MOD-CI-0035-00 - REH International Airport Project – Storm Concrete Ditch Missing Information | 46146 | Structural |  |  |  |  | 26-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0036 | 00 | REH International Airport Project - gatehouse 03&04- proposed connection for G03&G04 NACO update | 46130 | Structural |  |  |  | HillInt-RTRFI-000209 | 46132 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0037 | 00 | REH International Airport Project – Missing Details for Wing Walls | 46130 | Structural |  |  |  | HillInt-RTRFI-000272 | 26-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0038 | 00 | REH International Airport Project – AGL at Runway Over-Run Parts | 46131 | Structural |  |  |  | HillInt-RTRFI-000315 | 46141 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0039 | 00 | REH International Airport Project – Discrepancy in Wing Wall Details | 46133 | Structural |  |  |  | HillInt-RTRFI-000345 | 46147 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0040 | 00 | REH International Airport Project – Perimeter Wall Fence | 46133 | Structural |  |  |  | HillInt-RTRFI-000340 | 46146 |  | Response
| RFI-REH-AR01-OC-MOD-CI-0040 | 1 | REH International Airport Project – Perimeter Wall Fence | 46148 | Structural | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-CI-0041 | 0 | REH International Airport Project – VVIP Terminal Building Expansion Joint Location | 46143 | Structural | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-CI-0042 | 0 | REH International Airport Project – Material Specifications Clarification | 46144 | Structural | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0001 | 0 | P0153-K00146-REH International Airport Project - Basement Floor Fire Hydrant | 45949 | ME |  |  |  |  | 45958 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0002 | 0 | P0153-K00146-REH International Airport Project - Replacement of Fire Fighting Pipes | 45950 | ME |  |  |  |  | 45967 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0003 | 0 | P0153-K00146-REH International Airport Project - Replacement of Drainage Pipes Sizes | 45950 | ME |  |  |  |  | 45965 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0004 | 0 | P0153-K00146-REH International Airport Project - 20% FCU units Increased capacity | 46019 | ME |  |  |  |  | 46025 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0005 | 0 | P0153-K00146-REH International Airport Project - Hydraulic re-calculation of primary chilled water pumps | 46050 | ME |  |  |  |  | 46059 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0006 | 0 | P0153-K00146-REH International Airport Project - changing storm connection pipe material | 46054 | ME |  |  |  |  | 46056 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0007 | 0 | P0153-K00146-REH International Airport Project - Conflict in BoQ quantities | 46057 | ME |  |  |  |  | 46063 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0008 | 0 | P0153-K00146-REH International Airport Project - Cavity for drainage pipe | 46060 | ME |  |  |  |  | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0009 | 0 | P0153-K00146-REH International Airport Project - Adding 150mm cavity wall | 46062 | ME |  |  |  |  | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0010 | 0 | P0153-K00146-REH International Airport Project - Adding 150mm cavity wall | 46062 | ME |  |  |  |  | 46079 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0011 | 0 | REH International Airport Project - Storm Drainage Clashing with Basement Walls | 46063 | ME |  |  |  |  | 46082 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0012 | 00 | REH International Airport Project - Hydraulic calculations for Chilled hot water Secondary and primary pumps – HVAC. | 46070 | ME |  |  |  |  | 46079 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0013 | 00 | RFI-REH-AR01-OC-MOD-ME-0013-00 - REH International Airport Project – Airside Storm Ditch Conflict | 46120 | ME |  |  |  |  | 46138 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0014 | 0 | RFI-REH-AR01-OC-MOD-ME-0014-00 - REH International Airport Project – Ambient Air Temperatures | 46121 | ME |  |  |  |  | 46124 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0015 | 00 | RFI-REH-AR01-OC-MOD-ME-0015-00 - REH International Airport Project – Fire Pump | 46121 | ME |  |  |  |  | 22-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0016 | 00 | REH International Airport Project - VVIP – Additional lavatories drainage pipes at basement | 46130 | ME |  |  |  |  | 46147 |  | Response | NACO
| RFI-REH-AR01-OC-MOD-ME-0017 | 00 | REH International Airport Project – proposal of some unconnected storm pipes- VVIP building | 46130 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0018 | 00 | REH International Airport Project – VVIP Terminal – Buffer Tank at Ground Floor | 46132 | ME |  |  |  | HillInt-RTRFI-000330 | 46142 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0019 | 00 | REH International Airport Project – ESP- VVIP building | 46132 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0020 | 00 | REH International Airport Project – ESP- Chiller plant | 46132 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0021 | 00 | REH International Airport Project – ESP- Main Entry Facility | 46132 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0022 | 00 | REH International Airport Project – ESP- Pump station | 46132 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0023 | 00 | REH International Airport Project – ESP- Main Intake Substation Fans, AHUs and RTU units | 46132 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0024 | 00 | REH International Airport Project – ESP- ARFFS Building for CRAC, Fans and DOAS Units | 46132 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0025 | 00 | REH International Airport Project – STORM WATER DRAINAGE PIPE NETWORK MATERIAL REPLACEMENT (using pipe HDPE PN10 instead of PN16) | 46134 | ME |  |  |  | HillInt-RTRFI-000329 | 46142 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0026 | 00 | REH International Airport Project - VVIP - Emergency Siphonic System Issue | 46138 | ME |  |  |  | HillInt-RTRFI-000341 | 46146 |  | Response
| RFI-REH-AR01-OC-MOD-ME-0027 | 00 | REH International Airport Project - Lift station data and storm water Ti-in issues | 46142 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0028 | 00 | REH International Airport Project - SEWAGE NETWORK STILLING BASIN | 46142 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0029 | 0 | REH International Airport Project - Mechanical clarification and issues inside Pump Station building | 46142 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0030 | 00 | REH International Airport Project - Hydraulic calculations of Distribution chilled Cold and hot water pumps | 46148 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-ME-0031 | 00 | REH International Airport Project - VVIP AC AIR TERMINAL CLASHES ISSUE - ROOMS G1.18 & G1.25 | 46149 | ME | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-EL-0001 | 0 | P0153-K00146-REH International Airport Project - AGL manhole base and level | 45954 | EL |  |  |  |  | 45959 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0002 | 0 | P0153-K00146-REH International Airport Project - M.V Switchgear Clarifications | 46015 | EL |  |  |  |  | 46034 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0003 | 0 | P0153-K00146-REH International Airport Project - Insulation class for Standby generators | 46019 | EL |  |  |  |  | 46034 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0004 | 0 | P0153-K00146-REH International Airport Project - Dry type transformers | 46027 | EL |  |  |  |  | 46034 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0005 | 0 | P0153-K00146-REH International Airport Project - MV Network clarifications | 46041 | EL |  |  |  |  | 46051 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0005 | 1 | REH International Airport Project - MV Network clarifications | 46097 | EL |  |  |  |  | 46099 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0006 | 0 | P0153-K00146-REH International Airport Project - M.V Cables | 46056 | EL |  |  |  |  | 46058 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0007 | 0 | P0153-K00146-REH International Airport Project - ATS Ratings Availability | 46057 | EL |  |  |  |  | 46063 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0008 | 0 | REH International Airport Project - ATS Ratings Availability | 46064 | EL |  |  |  |  | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0009 | 0 | REH International Airport Project - Main Distribution Panel Final Design | 46064 | EL |  |  |  |  | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0010 | 0 | REH International Airport Project - Lighting Fixture Clarifications | 46064 | EL |  |  |  |  | 46088 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0011 | 0 | REH International Airport Project - ( 20 - 22 ) Workshop Follow up (Elec Items) | 46068 | EL |  |  |  |  | 46088 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0012 | 0 | REH International Airport Project - Bus way - New added item | 46070 | EL |  |  |  |  | 46082 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0013 | 0 | REH International Airport Project - poles lighting fixtures | 46075 | EL |  |  |  |  | 46105 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0014 | 0 | REH International Airport Project –Lighting control system | 46075 | EL |  |  |  |  | 46114 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0015 | 0 | REH International Airport Project –Chiller plant electrical clarifications | 46097 | EL |  |  |  |  | 46105 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0016 | 0 | RFI-REH-AR01-OC-MOD-EL-0016-00 - REH International Airport Project - Cable trays and Cable Trunks – Cables Arrangement | 46113 | EL |  |  |  |  | 26-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0017 | 0 | RFI-REH-AR01-OC-MOD-EL-0017-00 - REH International Airport Project - UPS centralized monitoring system | 46114 | EL |  |  |  |  | 21-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0018 | 0 | RFI-REH-AR01-OC-MOD-EL-0018-00 - REH International Airport Project - Electric Conduits – GI Conduits categorization | 46121 | EL |  |  |  |  | 20-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0019 | 0 | RFI-REH-AR01-OC-MOD-EL-0019-00 - REH International Airport Project - Missing Information and design discrepancies in Main Intake Substation | 46123 | EL | [6 empty] | Open
| RFI-REH-AR01-OC-MOD-EL-0020 | 0 | RFI-REH-AR01-OC-MOD-EL-0020-00 - REH International Airport Project - Generator Room Ventilation Openings at Main Intake Substation & Canopy cancellation in all indoor substations | 46126 | EL |  |  |  | HillInt-RTRFI-000311 | 46141 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0021 | 0 | RFI-REH-AR01-OC-MOD-EL-0021-00 - REH International Airport Project - Optical Fiber backbone Network | 46126 | EL |  |  |  |  | 22-4-2026 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0022 | 0 | RFI-REH-AR01-OC-MOD-EL-0022-00 - REH International Airport Project – UPS ratings | 46135 | EL |  |  |  | HillInt-RTRFI-000332 | 46145 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0023 | 0 | RFI-REH-AR01-OC-MOD-EL-0023-00 - REH International Airport Project – MV Cable Routing | 46137 | EL |  |  |  | HillInt-RTRFI-000276 | 46141 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0024 | 0 | RFI-REH-AR01-OC-MOD-EL-0024-00 - REH International Airport Project – REH International Airport Project – camera poles clarifications | 46138 | EL |  |  |  |  | 46152 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0025 | 0 | RFI-REH-AR01-OC-MOD-EL-0025-00 - REH International Airport Project – ATS 400A integration with DB-UPS panels | 46145 | EL | [6 empty] | OPEN
| RFI-REH-AR01-OC-MOD-EL-0026 | 0 | REH International Airport Project – Overall Telecommunication Network | 46147 | EL |  |  |  | HillInt-RTRFI-000385 | 46155 |  | Response
| RFI-REH-AR01-OC-MOD-EL-0027 | 0 | Missing Conduit Path of Telecommunication Network at Airside | 46149 | EL |  |  |  | HillInt-RTRFI-000393 | 46159 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0001 | 0 | P0153-K00146-REH International Airport Project – Missing Standing Seam layers Specifications | 46015 | AR |  |  |  | MOD-RTRFI-000250 | 46088 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0002 | 0 | P0153-K00146-REH International Airport Project – SANITARY DETAIL in the ABLUTION | 46024 | AR |  |  |  |  | 46042 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0003 | 0 | P0153-K00146-REH International Airport Project – Lighting poles RAL color | 46051 | AR |  |  |  | MOD-RTRFI-000250 | 46063 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0004 | 0 | P0153-K00146-REH International Airport Project – Reduction for Doors dimension | 46054 | AR |  |  |  | HillInt-RTRFI-000026 | 46088 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0005 | 0 | REH International Airport Project – Missing structure support | 46064 | AR |  |  |  | HillInt-RTRFI-000020 | 46082 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0005 | 1 | REH International Airport Project – Missing structure support | 46086 | AR |  |  |  | HillInt-RTRFI-000048 | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0006 | 0 | REH International Airport Project – ARFF Station, Block Work Sizes | 46064 | AR |  |  |  | HillInt-RTRFI-000009 | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0007 | 0 | REH International Airport Project – TPO Roof Waterproofing | 46067 | AR |  |  |  | HillInt-RTRFI-000023 | 46082 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0008 | 0 | REH International Airport Project – Gate house 3 – louvers | 46068 | AR |  |  |  | HillInt-RTRFI-000008 | 46078 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0009 | 0 | REH International Airport Project – Screed Layer | 46085 | AR |  |  |  | HillInt-RTRFI-000058 | 46107 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0010 | 0 | REH International Airport Project – Rockwool façade insulation clarification | 46089 | AR |  |  |  | HillInt-RTRFI-000057 | 46107 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0011 | 0 | REH International Airport Project – screed – general inquiry | 46096 | AR |  |  |  | HillInt-RTRFI-000046 | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0012 | 0 | REH International Airport Project – External Static Pressure calculations for Gate 01 & 03 & 04 & Substation01 and 02 buildings | 46096 | AR |  |  |  | HillInt-RTRFI-000044 | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0013 | 0 | REH International Airport Project – lav. tap conflict with the window | 46096 | AR |  |  |  | HillInt-RTRFI-000043 | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0014 | 0 | REH International Airport Project – ARFF - Water Sprinkler System in ATM MER room MODIFICATION | 46096 | AR |  |  |  | HillInt-RTRFI-000045 | 46098 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0015 | 0 | REH International Airport Project – Roller Shutter Doors Clarifications | 46107 | AR |  |  |  | HillInt-RTRFI-000085 | 46117 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0016 | 00 | RFI-REH-AR01-OC-MOD-AR-0016-00 - REH International Airport Project – Fire Hose Cabinet | 46134 | AR |  |  |  | HillInt-RTRFI-000331 | 46142 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0017 | 0 | RFI-REH-AR01-OC-MOD-AR-0017-00 - REH International Airport Project – Discrepancy in heights of parapet walls at VVIP First floor | 46138 | AR |  |  |  | HillInt-RTRFI-000358 | 46148 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0018 | 0 | REH International Airport Project – VVIP TERMINAL Finishing | 46140 | AR |  |  |  | HillInt-RTRFI-000313 | 46141 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0019 | 0 | RFI-REH-AR01-OC-MOD-AR-0019-00 - REH International Airport Project - ARFFS Finishing | 46140 | AR |  |  |  | HillInt-RTRFI-000363 | 46152 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0020 | 0 | REH International Airport Project - Roofing and Coping and Façade System | 46141 | AR | [6 empty] | OPEN
| RFI-REH-AR01-OC-MOD-AR-0021 | 0 | REH International Airport Project - VVIP Stone Cladding Below Signage | 46144 | AR | [6 empty] | OPEN
| RFI-REH-AR01-OC-MOD-AR-0022 | 0 | REH International Airport Project - Aluminum Curtain Wall | 46147 | AR | [6 empty] | OPEN
| RFI-REH-AR01-OC-MOD-AR-0023 | 0 | REH International Airport Project – Laminate HPL | 46152 | AR | [6 empty] | OPEN
| RFI-REH-AR01-OC-MOD-EL-0028 | 0 | RFI-REH-AR01-OC-MOD-EL-0028-00 - REH International Airport Project – Electrical & ICT Rooms Issues at ARFF Building | 46153 | EL |  |  |  | HillInt-RTRFI-000392 | 46158 |  | Response
| RFI-REH-AR01-OC-MOD-AR-0024-00 |  | RFI-REH-AR01-OC-MOD-AR-0024-00 - REH International Airport Project – Clash between the ceiling level and the louver | 46159 | AR | [5 empty] | Eng.Menna Eng.a.salama Eng. Ramy | Open