## Canal Beach West
Request For Information Log form West Canal Project | [8 empty] | ALL | 14
[9 empty] | Response | 11
OrascomTO HILL | [6 empty] | Hill to Orascom |  | Open | 0
Mail No | RFI No | Rev. | Discipline | Mail No | Subject | Date | Mail No | Date
CCCEGY-RFI-000001 | P1201-MD07-CW-OC-HILL-RFI-000001 | 00 | Civil Work | P1201-MD07-CW-OC-HILL-RFI-0001 | RFI No.: P1201-MD07-CW-OC-HILL-RFI-000001-00, P1201 REH-Canal Beach West – Request for Information – Civil Works – Relocating the dumping area | 2026-03-25 | HillInt-RTRFI-000303 | 2026-04-28 | Response
| P1201-MD07-CW-OC-HILL-RFI-000001 | 01 | Civil Work | OC-HILL-RFI-0001-01 | Re: P1201 REH-Canal Beach West – Request for Information – Civil Works – 0001 R1 - Relocating the dumping area | 2026-05-02 | HillInt-RTRFI-000356 | 2026-05-06 | Response
CCCEGY-RFI-000002 | P1201-MD07-CW-OC-HILL-RFI-000002 | 00 | Civil Work | P1201-MD07-CW-OC-HILL-RFI-0002 | RFI No.: P1201-MD07-CW-OC-HILL-RFI-000002-00, P1201 REH-Canal Beach West – Request for Information – Civil Works – Stockpiles location proposal | 2026-04-07 | HillInt-RTRFI-000223 | 2026-04-21 | Response
CCCEGY-RFI-000003 | P1201-MD07-CW-OC-HILL-RFI-000002 | 01 | Civil Work | OC-RFI-000002 | RFI No.: P1201-MD07-CW-OC-HILL-RFI-000002-00, P1201 REH-Canal Beach West – Request for Information – Civil Works – 00002 R1 - Stockpiles location proposal | 2026-04-27 | HillInt-RTRFI-000304 | 2026-04-28 | Response
CCCEGY-RFI-000004 | P1201-MD07-CW-OC-HILL-RFI-000002 | 02 | Civil Work | OC-RFI-000003 | P1201 REH-Canal Beach West – Request for Information – Civil Works – 00002 R2 - Stockpiles location proposal | 2026-04-29 | HillInt-RTRFI-000352 | 2026-05-05 | Response
| P1201-MD07-CW-OC-HILL-RFI-000002 | 03 | Civil Work | OC-HILL-RFI-0002-03 | P1201 REH-Canal Beach West – Request for Information – Civil Works – 00002 R3 - Stockpiles location proposal | 2026-05-05 | HillInt-RTRFI-000380 | 2026-05-12 | Response
| P1201-MD07-CW-OC-HILL-RFI-000002 | 04 | Civil Work | OC-HILL-RFI-0002-04 | P1201 REH-Canal Beach West – Request for Information – Civil Works – 00002 R4 - Stockpiles location proposal | 2026-05-13 | HillInt-RTRFI-000389 | 2026-05-14 | Response
| P1201-MD07-CW-OC-HILL-RFI-000002 | 05 | Civil Work | OC-HILL-RFI-0002-05 | P1201 REH-Canal Beach West – Request for Information – Civil Works – 00002 R5 - Stockpiles location proposal | 2026-05-16 | HillInt-RTRFI-000440 | 2026-05-21 | Response
CCCEGY-RFI-000005 | P1201-MD07-CW-OC-HILL-RFI-000003 | 00 | Civil Work | P1201-MD07-CW-OC-HILL-RFI-0003 | P1201 REH-Canal Beach West – Request for Information – Civil Works – Hold Areas | 2026-05-07 | HillInt-RTRFI-000381 | 2026-05-12 | Response
| P1201-MD07-CW-OC-HILL-RFI-000004 | 00 | Civil Work | P1201-MD07-CW-OC-HILL-RFI-0004 | P1201 REH-Canal Beach West – Request for Information – Civil Works – 0004 R0 - Storage and stockpiling strategy | 2026-05-16 | HillInt-RTRFI-000418 | 2026-05-18 | Response
CCCEGY-RFI-000006 | P1201-MD07-BK-OC-HILL-RFI-000001 | 00 | Bulk Work | OC-RFI-000005 | P1201 REH-Canal Beach West – Request for Information – West Canal excavation limit at interface with phase 1 A | 2026-07-09 | HillInt-RTRFI-000840 | 2026-07-21 | Response
CCCEGY-RFI-000007
CCCEGY-RFI-000008
CCCEGY-RFI-000009
CCCEGY-RFI-000010
CCCEGY-RFI-000011
CCCEGY-RFI-000057
CCCEGY-RFI-000012
CCCEGY-RFI-000055
CCCEGY-RFI-000013
CCCEGY-RFI-000014
CCCEGY-RFI-000015
CCCEGY-RFI-000067
CCCEGY-RFI-000016
CCCEGY-RFI-000017
CCCEGY-RFI-000018
CCCEGY-RFI-000019
CCCEGY-RFI-000020
CCCEGY-RFI-000068
CCCEGY-RFI-000021
CCCEGY-RFI-000022
CCCEGY-RFI-000023
CCCEGY-RFI-000024
CCCEGY-RFI-000025
CCCEGY-RFI-000026
CCCEGY-RFI-000027
CCCEGY-RFI-000028
CCCEGY-RFI-000029
CCCEGY-RFI-000030
CCCEGY-RFI-000069
CCCEGY-RFI-000031
CCCEGY-RFI-000032
CCCEGY-RFI-000033
CCCEGY-RFI-000038
CCCEGY-RFI-000034
CCCEGY-RFI-000037
CCCEGY-RFI-000035
CCCEGY-RFI-000036
CCCEGY-RFI-000039
CCCEGY-RFI-000040
CCCEGY-RFI-000041
CCCEGY-RFI-000042
CCCEGY-RFI-000043
CCCEGY-RFI-000044
CCCEGY-RFI-000045
CCCEGY-RFI-000046
CCCEGY-RFI-000047
CCCEGY-RFI-000048
CCCEGY-RFI-000049
CCCEGY-RFI-000050
CCCEGY-RFI-000051
CCCEGY-RFI-000052
CCCEGY-RFI-000053
CCCEGY-RFI-000054
CCCEGY-RFI-000056
CCCEGY-RFI-000058
CCCEGY-RFI-000059
CCCEGY-RFI-000060
CCCEGY-RFI-000061
CCCEGY-RFI-000062
CCCEGY-RFI-000063
CCCEGY-RFI-000064
CCCEGY-RFI-000065
CCCEGY-RFI-000066
CCCEGY-RFI-000070
CCCEGY-RFI-000071
CCCEGY-RFI-000072
CCCEGY-RFI-000073
CCCEGY-RFI-000074
CCCEGY-RFI-000075
CCCEGY-RFI-000076
CCCEGY-RFI-000077
CCCEGY-RFI-000078
CCCEGY-RFI-000079
CCCEGY-RFI-000080
CCCEGY-RFI-000081
CCCEGY-RFI-000082
CCCEGY-RFI-000098
CCCEGY-RFI-000099
CCCEGY-RFI-000100
CCCEGY-RFI-000101
CCCEGY-RFI-000083
CCCEGY-RFI-000084
CCCEGY-RFI-000085
CCCEGY-RFI-000086
CCCEGY-RFI-000087
CCCEGY-RFI-000088
CCCEGY-RFI-000089
CCCEGY-RFI-000090
CCCEGY-RFI-000091
CCCEGY-RFI-000092
CCCEGY-RFI-000093
CCCEGY-RFI-000094
CCCEGY-RFI-000095
CCCEGY-RFI-000096
CCCEGY-RFI-000097